## Global_WBS
Content.Division | Content.Customer | Content.Integ | Content.Name | Content.System | Content.Task Category | Content.Area | Content.Deliverable | Content.Status | Content.Review Date | Content.Due Date | Content.Project Lead | Content.Area Owner | Content.Execution Owner | Content.Comments | Name
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-06-16 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DGajjar WK 24 - All Documents | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-11-20 | Deep Gajjar | Deep Gajjar | Deep Gajjar | ME 11-20-25 - All Documents | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-12-10 | Deep Gajjar | Deep Gajjar | Xin Liu | 2025-12-10 Initial Site Survey - All Documents | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting and Hardware | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Jameson Fitzpatrick | James Bragg |  | CS_NG1
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Spare Parts List | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Fencing | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | IB - Load Plan Layout | Completed |  | 2026-01-01 | Alex Raff |  | Andrea Hosna |  | Amz_FTY3
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt Infeed Conveyor | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Chute - Carton | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis |  | Update xref | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Chute - Tote | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis |  | Update xref | CS_NG1
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-14 | Deep Gajjar | Xin Liu | Xin Liu | 2026-01-14 Initial Site Survey - All Documents | SSD_Fortna
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-15 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Wk 3 DGajjar - All Documents | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-16 | Deep Gajjar | Deep Gajjar | Xin Liu | 2026-01-15 Initial Site Survey - All Documents | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-18 | Deep Gajjar | Deep Gajjar | Xin Liu | 2026-01-16 Initial Site Survey - All Documents | SSD_DCS
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt - Lenze Motor | Completed |  | 2026-01-28 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt - Electrical Components | Completed |  | 2026-01-29 | Jameson Fitzpatrick | Jameson Fitzpatrick |  | BCH to confirm if provided | CS_NG1
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Mobile Chute - Left hand vs Right hand count | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Floor Guides | Completed |  | 2026-02-01 | Pierre Damis | Rasmus Sorensen | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Device Frame | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Floor Guides- Updated Assembly Drawing | Completed |  | 2026-02-01 | Pierre Damis | Rasmus Sorensen | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Operator Post | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Break Roller | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Mobile Chute - Break Roller Customer FAT | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis | Amazon Chute Force Tests - OneDrive | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Transition Slide Structure for single chute | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Transition Slide Structure Between banks | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Static Chute - Included In J&J Order | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Static Chute - Transition Slide Structure near recirculation line | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | End of Line Chute - Left hand vs Right hand count | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Rasmus Sorensen |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | N/A | SSDs | BGLS | Project Layouts | System Components | Destination - Blocks | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Andrea Hosna |  | SSD_GFCD
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Destination Layout - Hybrid Chute Locations | Completed |  | 2026-02-06 |  | Pierre Damis | Pierre Damis |  | LS_IND3
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Destination - IB MDR | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Destination - OB Break belt | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Induction Unit - Mounting Details | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Destination | On schedule |  | 2026-02-09 | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Svaraj Patel | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Safety Equipment | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Guarding small plate under induction | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Svaraj Patel | DCS/SNJ6/Daifuku to order | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Minor/Major IU Interface, generic drawing, Recirc line | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | James Bragg |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR: | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR: | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR: | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR: | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR: | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Scanner | Completed |  | 2026-02-10 |  | Pierre Damis | David Blanco |  | LS_IND3
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fence - Layout Update | Completed |  | 2026-02-10 |  | Pierre Damis | David Blanco |  | LS_IND3
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Sprial Chute mounting | Completed |  | 2026-02-10 |  | Pierre Damis | Pierre Damis |  | LS_IND3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Chute Design | Chute Interface |  |  | 2026-02-13 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-02-13 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Wk6_DGajjar - All Documents | SSD_DCS
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Detail Design | Sorter Netting |  |  | 2026-02-17 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | 2026-02-18 | Xin Liu | Xin Liu |  | 2026-02-18 SGA6 Initial Site Survey - All Documents | SSD_Daifuku
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Engineering | System Components | Hybrid FAT - Site Visit | Completed |  | 2026-02-19 |  | Rasmus Sorensen | Rasmus Sorensen | Hybrid destination test | LS_IND3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Safety Fencing |  |  | 2026-02-20 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Sorter Netting |  |  | 2026-02-20 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | End of Line Chute | Completed |  | 2026-02-23 | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | 2026-02-23 | Deep Gajjar | Deep Gajjar | Svaraj Patel | Do we need to provide transition plate? | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-23 | Deep Gajjar | Pierre Damis | Rasmus Sorensen |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-23 | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | Completed |  | 2026-03-02 | Deep Gajjar | Deep Gajjar |  | 6 weeks before install, Pending EE to provide a list of components | SSD_DCS
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | System Components | Destination | On schedule |  | 2026-03-02 | Pierre Damis | Pierre Damis | Andrea Hosna |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-03-02 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | System Components | Safety Fencing - Destination Area | On schedule |  | 2026-03-02 | Pierre Damis | Pierre Damis | Pierre Damis |  | SSD_GFCD
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-03-02 | Deep Gajjar | Pierre Damis | Pierre Damis | Template RA - SSF3 | SSD_DCS
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Detail Design | Transition Slide |  |  | 2026-03-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Cable Tray Path |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Electrical Components |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Risk Assessment |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Safety Labels |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Transition Slide |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Transition Slide |  |  | 2026-03-06 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | DST installation layout update | On schedule |  | 2026-03-06 |  | Alex Raff | David Blanco | Add dimension for caljen extendable conveyor. check note in teams labelled "IND_INST_UPDATE_1" | LS_IND3
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Chute Assembly Model | On schedule |  | 2026-03-06 | Pierre Damis | Pierre Damis | Rasmus Sorensen |  | SSD_GFCD
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Installation Drawings | Scanner | On schedule |  | 2026-03-09 | Xin Liu | Xin Liu | David Blanco | Xref update | Amz_RIC4
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Datum | Completed |  | 2026-03-09 | Deep Gajjar | Deep Gajjar | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-09 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-09 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-11 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-11 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-11 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-11 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-11 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-11 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-11 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-11 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-11 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Device frame floor mount | On schedule |  | 2026-03-11 | Pierre Damis | Pierre Damis | Rasmus Sorensen |  | SSD_GFCD
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Operator post floor mount | On schedule |  | 2026-03-11 | Pierre Damis | Pierre Damis | Rasmus Sorensen |  | SSD_GFCD
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Documentation | MRF | IOB Bracket Design | Completed |  | 2026-03-13 | Xin Liu | James Bragg |  | Site received, closed out JIRA. | Amz_RIC4
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-16 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-03-16 | Xin Liu | Xin Liu | Svaraj Patel | 2026-03-11 SWI2 Initial Site Survey - All Documents | SSD_Daifuku
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | 2026-03-16 | Deep Gajjar | Svaraj Patel |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-16 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-16 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-16 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-16 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-16 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-16 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-16 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-16 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | 2026-03-16 | Deep Gajjar | Xin Liu |  | 3 weeks before instal + 1 week buffer for MRF 4/13 | SSD_DCS
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Documentation | Installation Support | On schedule |  | 2026-03-18 | Xin Liu | James Bragg | James Bragg | Until end of ME Install | Amz_RIC4
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-24 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-24 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-24 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-24 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-24 | Deep Gajjar | James Bragg |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-24 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-24 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-25 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-25 | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Fortna
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Asbuild - Fencing Layout | On schedule |  | 2026-03-27 |  | Pierre Damis | David Blanco | [NG1WLM-134] Fencing redlines - Jira | LS_IND3
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Detail Design | Doubles Detection Bracket | On schedule |  | 2026-03-30 | Pierre Damis | Pierre Damis | Rasmus Sorensen | Doubles Detection Bracket - All Documents | SSD_GFCD
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | IB & OB - FAT | Pending Update |  | 2026-04-01 | Alex Raff |  |  | High Speed Diverts, Inspection Cart, Cognex Vision system, Induction Jam camera | Amz_FTY3
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-04-01 | Xin Liu | Xin Liu |  |  | Amz_RIC4
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Cabinet layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Cable tray layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Datum |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - Chutes |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - JAM PE |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - Transition Slide |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | ECO Layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Escape route layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | E-stop layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Fencing layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Maintenance layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Operator area layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Platform layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Safety signs layout |  |  | 2026-04-03 | Alex Raff |  |  | Pending Risk Assessment completion | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | SCADA layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Scanner layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Sorter Netting - SGS-SGN |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Sorter section layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Support layout |  |  | 2026-04-03 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-04-03 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-04-03 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-04-15 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-04-15 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-04-15 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-04-15 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Installation Binder |  |  | 2026-04-17 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Level 6 Checklist |  |  | 2026-04-17 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Safety Labels |  |  | 2026-04-17 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Sorter Mobile Component List |  |  | 2026-04-17 | Alex Raff |  |  |  | Amz_AVP3
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute - Locking Mechanism | On schedule |  | 2026-05-04 | Deep Gajjar | Pierre Damis | Rasmus Sorensen | SFL 9 Files - All Documents | SSD_DCS
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Design Engineering | Chute Design | Induction Reject Chute | On schedule |  | 2026-05-04 | Andrea Hosna | Andrea Hosna | Rasmus Sorensen | Reference Induction Install date to set deadline | YXX1
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Induction Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Mobile Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Static Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Induction Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Mobile Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Static Chute | On schedule |  | 2026-05-26 | Svaraj Patel |  |  | Final qtys for MRF | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Cabinet Location | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Destination | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | Guarding small plate under induction | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | System Interface | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | Minor/Major IU Interface, generic drawing, Recirc line | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Cabinet Location | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Destination | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | Guarding small plate under induction | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | 2026-07-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | System Interface | On schedule |  | 2026-07-24 | Svaraj Patel |  |  | Minor/Major IU Interface, generic drawing, Recirc line | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | 2026-07-27 | Svaraj Patel |  |  | 6 weeks before install, Pending EE to provide a list of components | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | 2026-07-27 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Detail Design | Sorter Supports | On schedule |  | 2026-07-27 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | 2026-07-27 | Svaraj Patel |  |  | 6 weeks before install, Pending EE to provide a list of components | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | 2026-07-27 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Detail Design | Sorter Supports | On schedule |  | 2026-07-27 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Design Engineering | Chute Design | Induction Unit Reverse Chute | On schedule |  | 2026-08-03 | Alex Raff | Alex Raff | Rasmus Sorensen | Amazon spec to include bead roller | Amz_FTY3
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | 2026-08-04 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | 2026-08-04 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | 2026-08-04 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Datum | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-08-24 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Datum | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-08-24 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-08-24 | Svaraj Patel |  |  |  | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | 2026-09-01 | Svaraj Patel |  |  | Site Start Date: 9/29/26 (4 weeks before install, 1 week buffer) | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Installation Drawing Prints | On schedule |  | 2026-09-01 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | 2026-09-01 | Svaraj Patel |  |  | Site Start Date: 9/29/26 (4 weeks before install, 1 week buffer) | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Installation Drawing Prints | On schedule |  | 2026-09-01 | Svaraj Patel |  |  | Pending Risk Assessment completion | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | 2026-11-23 | Svaraj Patel |  |  | End of ME Install. Confirm Date | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | 2026-11-23 | Svaraj Patel |  |  | End of ME Install. Confirm Date | SSD_Dematic
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute - Neoprene Addition | On schedule |  | 265291 | Deep Gajjar | Pierre Damis | Rasmus Sorensen | SFL 9 Files - All Documents | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_DCS
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Risk Assessment | Pending Update |  | TBD | Svaraj Patel |  |  | Template RA - SSF3 | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Fencing | Pending Update |  | TBD | Svaraj Patel |  |  | Confirm with Xin / Mary from PUR | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Site Survey | Pending Update |  | TBD | Svaraj Patel |  |  | Need to schedule | SSD_Dematic
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Spare Parts List | Pending Update |  | TBD | Svaraj Patel |  |  | Ref previous SSDs | SSD_Dematic
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_DCS
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Risk Assessment | Pending Update |  | TBD | Svaraj Patel |  |  | Template RA - SSF3 | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Fencing | Pending Update |  | TBD | Svaraj Patel |  |  | Confirm with Xin / Mary from PUR | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Site Survey | Pending Update |  | TBD | Svaraj Patel |  |  | Need to schedule | SSD_Dematic
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Spare Parts List | Pending Update |  | TBD | Svaraj Patel |  |  | Ref previous SSDs | SSD_Dematic
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel |  |  | SSD_DCS
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | EE Device Bracket - | Completed |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Equipment | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Fencing | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Sorter Support | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | ZMX Sensor Mount | Pending Update |  | TBD | Deep Gajjar | Pierre Damis | Rasmus Sorensen | Pending Change order apporval | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_DCS
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Xin Liu | Svaraj Patel | 2026-03-06 SNJ6 Initial Site Survey - All Documents | SSD_Fortna
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar |  |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete? | SSD_DCS
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar |  |  |  | SSD_DCS
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco | End of ME Install. Confirm Date | SSD_DCS
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | End of Line Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Recirculation Line | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Design Engineering | Chute Design | High Speed Divert | On schedule |  |  | Alex Raff | Alex Raff |  | BDK Scope | Amz_FTY3
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Safety Fencing | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Safety Labels | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - All ME Materials | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Cabinet layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Cable tray layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | IB - Consoladed EE Layouts | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Datum | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - Chutes | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - JAM PE | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - Transition Slide | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - ECO layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Escape route layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - E-stop layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Fencing layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | IB - Installation Binder | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Maintenance layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Operator area layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Platform layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | IB - Risk Assessment | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Safety signs layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - SCADA layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Scanner layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Sorter Netting - SGS-SGN | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_NGLite
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Installation Book | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Spare Parts List | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Sorter section layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Sorter Support | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Support layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - All ME Materials | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Cabinet layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Cable tray layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | OB - Consoladed EE Layouts | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Datum | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - Chutes | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - JAM PE | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - Transition Slide | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - ECO layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Escape route layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - E-stop layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Fencing layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | OB - Installation Binder | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | OB - Load Plan Layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Maintenance layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Operator area layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Platform layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | OB - Risk Assessment | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Safety Fencing | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Safety Labels | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Safety signs layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - SCADA layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Scanner layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | OB - Sorter Components | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | OB - Sorter Design Approval | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Sorter Netting - SGS-SGN | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Sorter section layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Sorter Support | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Support layout | Pending Update |  |  | Alex Raff |  |  |  | Amz_FTY3
Mechatronics | N/A | N/A | N/A | N/A | [10 empty] | MT_ME
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | On schedule |  |  | Jameson Fitzpatrick |  |  | 1/2" ordered last time, order 3/8" fully threaded | CS_NG2_3
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Jameson Fitzpatrick |  |  |  | CS_NG2_3
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing & Induction Unit Mounting | On schedule |  |  | Jameson Fitzpatrick |  |  |  | CS_NG2_3
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | On schedule |  |  | Jameson Fitzpatrick |  |  | 1/2" ordered last time, order 3/8" fully threaded | CS_NG2_3
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Jameson Fitzpatrick |  |  |  | CS_NG2_3
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing & Induction Unit Mounting | On schedule |  |  | Jameson Fitzpatrick |  |  |  | CS_NG2_3
Logistics | Target | N/A | RCSS | Loop Sorter | [10 empty] | Tar_RCSS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis |  |  | SSD_Fortna
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Safety Labels | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Sorter Support | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Layouts | Installation Drawings | Safety Fence | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_Digikey
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Project Layouts | Installation Drawings | Induction Unit - Mounitng Details | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_NGLite
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion | SSD_DCS
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_DCS
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | MRF | Safety Fencing | Completed |  |  | Jameson Fitzpatrick | Jameson Fitzpatrick |  |  | CS_NG1
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Destination | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Equipment | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | System Interface | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_DCS
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis |  | SSD_Fortna
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar |  |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco |  | SSD_Fortna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg |  | SSD_Fortna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg |  |  | SSD_Daifuku
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar |  | SSD_Fortna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann) |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel |  | SSD_Daifuku
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Safety Fence Panels | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_Digikey
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Induction Anchors | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_Digikey
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Safety Fence Anchors | Completed |  |  | Jameson Fitzpatrick |  |  |  | CS_Digikey
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Project Engineering | System Components | Safety Fencing | Completed |  |  | Jameson Fitzpatrick | Pierre Damis | Pierre Damis |  | CS_NGLite
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu |  |  |  | SSD_Daifuku
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar |  | SSD_Daifuku
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Engineering | System Components | Destinations | Pending Update |  |  | Andrea Hosna |  |  |  | YXX1
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing | Pending Update |  |  | Andrea Hosna |  |  |  | YXX1
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Netting | Pending Update |  |  | Andrea Hosna |  |  |  | YXX1

## Amazon SSDs
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | N/A | SSDs | BGLS | Project Layouts | System Components | Destination - Blocks | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Andrea Hosna
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | System Components | Safety Fencing - Destination Area | Completed |  | 2026-03-02 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | System Components | Destination | Completed |  | 2026-03-02 | Pierre Damis | Pierre Damis | Andrea Hosna
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-03-02 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Mobile Chute - Left hand vs Right hand count | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Mobile Chute - Break Roller Customer FAT | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis | Amazon Chute Force Tests - OneDrive
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Static Chute - Included In J&J Order | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | End of Line Chute - Left hand vs Right hand count | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Project Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Chute Assembly Model | Completed |  | 2026-03-06 | Pierre Damis | Pierre Damis | Rasmus Sorensen
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Operator post floor mount | Completed |  | 2026-03-11 | Pierre Damis | Pierre Damis | Rasmus Sorensen
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Device frame floor mount | Completed |  | 2026-03-11 | Pierre Damis | Pierre Damis | Rasmus Sorensen
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Floor Guides | Completed |  | 2026-02-01 | Pierre Damis | Rasmus Sorensen | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Device Frame | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Floor Guides- Updated Assembly Drawing | Completed |  | 2026-02-01 | Pierre Damis | Rasmus Sorensen | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Operator Post | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Break Roller | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Transition Slide Structure for single chute | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Mobile Chute - Transition Slide Structure Between banks | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Static Chute - Transition Slide Structure near recirculation line | Completed |  | 2026-02-01 | Pierre Damis | Pierre Damis | Pierre Damis
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Chute Design | Operator post floor mount - modified to attach to guides | On schedule |  | 2026-05-29 | Pierre Damis | Rasmus Sorensen | James Bragg
Logistics | Amazon | N/A | SSDs | BGLS | Design Engineering | Detail Design | Doubles Detection Bracket | Completed |  | 2026-03-30 | Pierre Damis | Pierre Damis | Rasmus Sorensen | Doubles Detection Bracket - All Documents

## SSD Dematic
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-04-03 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | End of Line Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-04-15 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-04-15 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Induction Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  | Final qtys for MRF
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Mobile Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Static Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Pierre Damis |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | End of Line Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Pierre Damis |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Induction Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Pierre Damis |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Mobile Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Pierre Damis |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | 2026-07-27 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | 2026-07-27 | Svaraj Patel | Deep Gajjar |  | 6 weeks before install, Pending EE to provide a list of components
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | 2026-09-01 | Svaraj Patel | David Blanco |  | Site Start Date: 9/29/26 (4 weeks before install, 1 week buffer)
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | 2026-06-25 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Spare Parts List | Pending Update |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel | Ref previous SSDs
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | Documentation | Risk Assessment | Pending Update |  | TBD | Svaraj Patel | Pierre Damis | Pierre Damis | Template RA - SSF3
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | 2026-11-23 | Svaraj Patel | David Blanco |  | End of ME Install. Confirm Date
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Static Chute | Behind Schedule |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  | Final qtys for MRF
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Datum | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | 2026-07-27 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-07-27 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | 2026-07-27 | Svaraj Patel | Deep Gajjar |  | 6 weeks before install, Pending EE to provide a list of components
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-04-15 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-04-15 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | 2026-09-01 | Svaraj Patel | David Blanco |  | Site Start Date: 9/29/26 (4 weeks before install, 1 week buffer)
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-07-27 | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Installation Drawing Prints | On schedule |  | 2026-09-01 | Svaraj Patel | Svaraj Patel | Svaraj Patel | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SAX9 | BGLS | Documentation | MRF | Safety Fencing | Pending Update |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel | Confirm with Xin / Mary from PUR
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Destination | Pending Update |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | Pending Chute Design Updates - Need to updat Blocks
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | Guarding small plate under induction
Logistics | Amazon | Dematic | SAX9 | BGLS | Project Engineering | System Components | System Interface | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | Minor/Major IU Interface, generic drawing, Recirc line
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | 2026-11-23 | Svaraj Patel | David Blanco |  | End of ME Install. Confirm Date
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Risk Assessment | Pending Update |  | TBD | Svaraj Patel | Pierre Damis | Pierre Damis | Template RA - SSF3
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | Documentation | Spare Parts List | Pending Update |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel | Ref previous SSDs
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Datum | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Installation Drawing Prints | On schedule |  | 2026-09-01 | Svaraj Patel | Svaraj Patel | Svaraj Patel | Pending Risk Assessment completion
Logistics | Amazon | Dematic | SCL3 | BGLS | Documentation | MRF | Safety Fencing | Pending Update |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel | Confirm with Xin / Mary from PUR
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | 2026-07-24 | Svaraj Patel |  |  | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  | 2026-07-24 | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | Guarding small plate under induction
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | System Interface | On schedule |  | 2026-07-24 | Svaraj Patel | Svaraj Patel |  | Minor/Major IU Interface, generic drawing, Recirc line
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Components | Destination | Pending Update |  | 2026-07-24 | Svaraj Patel | Svaraj Patel
Logistics | Amazon | Dematic | SCL3 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-04-03 | Svaraj Patel

## SSD DCS
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | End of Line Chute | Completed |  | 2026-02-23 | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | End of Line Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-23 | Deep Gajjar | Pierre Damis | Rasmus Sorensen
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-23 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Rasmus Sorensen
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | Completed |  | 2026-03-02 | Deep Gajjar | Deep Gajjar |  | 6 weeks before install, Pending EE to provide a list of components
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | 2026-03-16 | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | TBD | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | EE Device Bracket - | Completed |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Destination | On schedule |  | TBD | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute - Locking Mechanism | On schedule |  | 2026-05-04 | Deep Gajjar | Pierre Damis | Rasmus Sorensen | SFL 9 Files - All Documents
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-11 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-16 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Mobile Chute - Neoprene Addition | On schedule |  | 265291 | Deep Gajjar | Pierre Damis | Rasmus Sorensen | SFL 9 Files - All Documents
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Equipment | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-11 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-16 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Recirculation Line | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Fencing | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Fencing | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Sorter Support | Completed |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | EE Device Bracket - | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-11 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-16 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | BGLS Sorter Length | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-12-10 | Deep Gajjar | Deep Gajjar | Xin Liu | 2025-12-10 Initial Site Survey - All Documents
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Destination | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Spare Parts List | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-11 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-16 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | ECO Layout | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Svaraj Patel | (Doubles detection, centering frame). Completed 3 DCS, Fortna Daifuku WIP
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-01 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  |  | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Installation Book | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-11 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-16 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Point Load Layout | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-11 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-16 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Safety Equipment | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Guarding small plate under induction
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Svaraj Patel | DCS/SNJ6/Daifuku to order
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Equipment | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Minor/Major IU Interface, generic drawing, Recirc line
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Operator and Maintenace Area | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-06-16 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DGajjar WK 24 - All Documents
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Design done, Custom lengths needed per project
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | Sorter Support | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | TBD | Deep Gajjar | Pierre Damis
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Sorter Section | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Layouts | System Layout Submittal | Completed |  | 2026-01-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Datum | Completed |  | 2026-03-09 | Deep Gajjar | Deep Gajjar | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | Documentation | Spare Parts List | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Svaraj Patel
Logistics | Amazon | DCS | SSF3 | BGLS | Design Engineering | Chute Design | Recirculation Line | Completed |  | 2026-02-23 | Deep Gajjar | Deep Gajjar | Svaraj Patel | Do we need to provide transition plate?
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-11 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-16 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Engineering | System Components | System Interface | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Documentation | MRF | Safety Labels | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick | Pending Risk Assessment completion
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Installation Book | Completed |  | 2026-03-16 | Deep Gajjar | Xin Liu |  | 3 weeks before instal + 1 week buffer for MRF 4/13
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  | TBD | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | System Components | Destination | Completed |  | 2026-02-09 | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-11 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-16 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar | Pending Risk Assessment completion
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | Completed |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2025-11-20 | Deep Gajjar | Deep Gajjar | Deep Gajjar | ME 11-20-25 - All Documents
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-15 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Wk 3 DGajjar - All Documents
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-16 | Deep Gajjar | Deep Gajjar | Xin Liu | 2026-01-15 Initial Site Survey - All Documents
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-18 | Deep Gajjar | Deep Gajjar | Xin Liu | 2026-01-16 Initial Site Survey - All Documents
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-02-13 | Deep Gajjar | Deep Gajjar | Deep Gajjar | Wk6_DGajjar - All Documents
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | Completed |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | Completed |  | 2026-03-09 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  | TBD | Deep Gajjar | Xin Liu | James Bragg | Did we complete?
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  | 2026-03-09 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNC7 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-11 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SCA8 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-16 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SAX8 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | Completed |  | 2026-03-09 | Deep Gajjar | James Bragg |  | Confirm if completed by BDK
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete?
Logistics | Amazon | DCS | SAX8 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Documentation | MRF | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete?
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete?
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete?
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | Svaraj Patel | Did we complete?
Logistics | Amazon | DCS | SNC7 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | Completed |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Safety Labels | Completed |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann) | Pending Risk Assessment completion
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  | 2026-02-01 | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | Completed |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | DCS | SAX8 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SCA8 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SNJ5 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SOH7 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  | 2026-02-01 | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Installation Drawings | Sorter Support | Completed |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Safety Labels | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-03-02 | Deep Gajjar | Pierre Damis | Pierre Damis | Template RA - SSF3
Logistics | Amazon | DCS | SAX8 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR:
Logistics | Amazon | DCS | SCA8 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR:
Logistics | Amazon | DCS | SNJ5 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR:
Logistics | Amazon | DCS | SOH7 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR:
Logistics | Amazon | DCS | SNC7 | BGLS | Project Engineering | System Components | System Interface | Completed |  | 2026-02-09 | Deep Gajjar | Deep Gajjar | Deep Gajjar | DIR:
Logistics | Amazon | DCS | SFL9 | BGLS | Project Layouts | Installation Drawings | Sorter Support | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | DCS | SSF3 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar | Deep Gajjar | David Blanco | End of ME Install. Confirm Date
Logistics | Amazon | DCS | SNC7 | BGLS | Design Engineering | Chute Design | ZMX Sensor Mount | Pending Update |  | TBD | Deep Gajjar | Pierre Damis | Rasmus Sorensen | Pending Change order apporval

## SSD Daifuku
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Xin Liu | Xin Liu | Andrea Hosna
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  |  | Xin Liu | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Induction Unit | Completed |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Induction Unit | Completed |  |  | Xin Liu | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  |  | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Xin Liu | Pierre Damis
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Equipment | On schedule |  |  | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | David Blanco
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Fencing | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  |  | Xin Liu | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Safety Labels | On schedule |  |  | Xin Liu | Deep Gajjar | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  |  | Xin Liu | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | 2026-02-18 | Xin Liu | Xin Liu |  | 2026-02-18 SGA6 Initial Site Survey - All Documents
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-03-16 | Xin Liu | Xin Liu | Svaraj Patel | 2026-03-11 SWI2 Initial Site Survey - All Documents
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Xin Liu | Xin Liu | James Bragg
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SGA6 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Xin Liu | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Daifuku | SWI2 | BGLS | Documentation | MRF | Sorter Support | On schedule |  |  | Xin Liu | Xin Liu | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  |  | Xin Liu | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Xin Liu | Xin Liu | Deep Gajjar
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Xin Liu
Logistics | Amazon | Daifuku | SGA6 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SWI2 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Xin Liu | Pierre Damis | Pierre Damis
Logistics | Amazon | Daifuku | SGA6 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Daifuku | SSJ1 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Daifuku | SWI2 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Xin Liu | Deep Gajjar | Deep Gajjar

## SSD Fortna
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Documentation | As-Builds | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | BGLS Ordering Tool - ME | On schedule |  | TBD | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Cabinet Location | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | DES ECO Layout | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Destination | On schedule |  |  | Deep Gajjar | Xin Liu | Andrea Hosna
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-24 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Destination Chutes | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-25 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-24 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Destination Transitions | On schedule |  | 2026-03-09 | Deep Gajjar | Andrea Hosna | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | ECO Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Detail Design | EE Device Bracket - | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-24 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Egress, Maintenance Operator | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | End of Line Chute | On schedule |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Induction Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-24 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Induction Unit | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Induction Unit | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Installation Book | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | LNS ECO Layout | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-25 | Deep Gajjar | James Bragg
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-24 | Deep Gajjar | James Bragg
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | LNS Sorter Section | On schedule |  | 2026-03-09 | Deep Gajjar | James Bragg
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Mobile Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Point Load Layout | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Recirculation Line | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Risk Assessment | On schedule |  |  | Deep Gajjar | Pierre Damis
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Equipment | On schedule |  |  | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-25 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-25 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-24 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Deep Gajjar | Xin Liu | David Blanco
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Safety Fencing | On schedule |  | 2026-03-09 | Deep Gajjar | David Blanco | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-25 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-24 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Safety Labels | On schedule |  |  | Deep Gajjar | Deep Gajjar | Jameson Fitzpatrick
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Safety Labels | On schedule |  | 2026-03-09 | Deep Gajjar | Jameson Fitzpatrick | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Site Survey | Completed |  | 2026-01-14 | Deep Gajjar | Xin Liu | Xin Liu | 2026-01-14 Initial Site Survey - All Documents
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Site Survey | On schedule |  | TBD | Deep Gajjar | Xin Liu | Svaraj Patel | 2026-03-06 SNJ6 Initial Site Survey - All Documents
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Sorter Section | On schedule |  |  | Deep Gajjar | Xin Liu | James Bragg
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-25 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-24 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | Sorter Support | On schedule |  |  | Deep Gajjar | Deep Gajjar | Svaraj Patel
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Layouts | Installation Drawings | Sorter Support | On schedule |  | 2026-03-09 | Deep Gajjar | Svaraj Patel | Bert Ellard (Prolann)
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Detail Design | Sorter Supports | Completed |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | Documentation | Spare Parts List | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SAZ4 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SFW4 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SIL5 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SNJ6 | BGLS | Design Engineering | Chute Design | Static Chute | Completed |  |  | Deep Gajjar | Pierre Damis | Pierre Damis
Logistics | Amazon | Fortna | SAZ4 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SFW4 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SIL5 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar
Logistics | Amazon | Fortna | SNJ6 | BGLS | Project Engineering | System Components | System Interface | On schedule |  |  | Deep Gajjar | Deep Gajjar | Deep Gajjar

## RIC4
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Documentation | Risk Assessment | On schedule |  | 2026-04-01 | Xin Liu | Xin Liu
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Installation Drawings | Scanner | On schedule |  | 2026-03-09 | Xin Liu | Xin Liu | David Blanco | Xref update
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Documentation | MRF | IOB Bracket Design | Completed |  | 2026-03-13 | Xin Liu | James Bragg |  | Site received, closed out JIRA.
Logistics | Amazon | TREW | RIC4 | Loop Sorter | Project Engineering | Documentation | Installation Support | On schedule |  | 2026-03-18 | Xin Liu | James Bragg | James Bragg | Until end of ME Install

## YXX1
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Engineering | System Components | Destinations | Pending Update |  |  | Andrea Hosna
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Design Engineering | Chute Design | Induction Reject Chute | On schedule |  | 2026-05-04 | Andrea Hosna | Andrea Hosna | Rasmus Sorensen | Reference Induction Install date to set deadline
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing | Pending Update |  |  | Andrea Hosna
Logistics | Amazon | N/A | YXX1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Netting | Pending Update |  |  | Andrea Hosna

## AVP3
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Sorter Netting - SGS-SGN |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Datum |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Support layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Platform layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Sorter section layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Scanner layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Cabinet layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Cable tray layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | E-stop layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | ECO layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Escape route layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Maintenance layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Operator area layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Fencing layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Safety signs layout |  |  | 2026-04-03 | Alex Raff |  |  | Pending Risk assessment completion
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | SCADA layout |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - Chutes |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - Transition Slide |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Layouts | Installation Drawings | Destinaion Layout - JAM PE |  |  | 2026-04-03 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Safety Fencing | Completed |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Cable Tray Path |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Electrical Components |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Safety Labels |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Project Engineering | System Components | Transition Slide |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Risk Assessment |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Installation Binder |  |  | 2026-04-17 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Level 6 Checklist |  |  | 2026-04-17 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | Documentation | Sorter Mobile Component List |  |  | 2026-04-17 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Sorter Netting |  |  | 2026-02-20 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Safety Fencing |  |  | 2026-02-20 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Safety Labels |  |  | 2026-04-17 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Documentation | MRFs | Transition Slide |  |  | 2026-03-06 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Detail Design | Sorter Netting |  |  | 2026-02-17 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Chute Design | Chute Interface |  |  | 2026-02-13 | Alex Raff
Logistics | Amazon | N/A | AVP3 | Loop Sorter | Design Engineering | Detail Design | Transition Slide |  |  | 2026-03-03 | Alex Raff

## FTY3
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Design Engineering | Chute Design | Induction Unit Reverse Chute | On schedule |  | 2026-08-03 | Alex Raff | Alex Raff | Rasmus Sorensen | Amazon spec to include bead roller
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Design Engineering | Chute Design | High Speed Divert | On schedule |  |  | Alex Raff | Alex Raff |  | BDK Scope
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | IB - Risk Assessment | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | IB - Installation Binder | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | OB - Risk Assessment | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | Documentation | OB - Installation Binder | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Sorter Netting - SGS-SGN | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Datum | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Support layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Platform layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Sorter section layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Scanner layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Cabinet layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Cable tray layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - E-stop layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - ECO layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Escape route layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Maintenance layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Operator area layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Fencing layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Safety signs layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - SCADA layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - Chutes | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - Transition Slide | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | IB - Destinaion Layout - JAM PE | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Sorter Netting - SGS-SGN | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Datum | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Support layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Platform layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Sorter section layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Scanner layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Cabinet layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Cable tray layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - E-stop layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - ECO layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Escape route layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Maintenance layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Operator area layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Fencing layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Safety signs layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - SCADA layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - Chutes | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - Transition Slide | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Layouts | Installation Drawings | OB - Destinaion Layout - JAM PE | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Sorter Support | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Safety Fencing | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - Safety Labels | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | IB - All ME Materials | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Sorter Support | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Safety Fencing | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - Safety Labels | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Documentation | MRF | OB - All ME Materials | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | IB - Load Plan Layout | Completed |  | 2026-01-01 | Alex Raff |  | Andrea Hosna
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | OB - Sorter Components | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | OB - Load Plan Layout | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Components | IB & OB - FAT | Pending Update |  | 2026-04-01 | Alex Raff |  |  | High Speed Diverts, Inspection Cart, Cognex Vision system, Induction Jam camera
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | IB - Consoladed EE Layouts | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | OB - Sorter Design Approval | Pending Update |  |  | Alex Raff
Logistics | Amazon | N/A | FTY3 | Loop Sorter | Project Engineering | System Layouts | OB - Consoladed EE Layouts | Pending Update |  |  | Alex Raff

## Target RCSS
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Target | N/A | RCSS | Loop Sorter | Design Engineering

## Walmart IND3
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Destination Layout - Hybrid Chute Locations | Completed |  | 2026-02-06 |  | Pierre Damis | Pierre Damis
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Scanner | Completed |  | 2026-02-10 |  | Pierre Damis | David Blanco
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fence - Layout Update | Completed |  | 2026-02-10 |  | Pierre Damis | David Blanco
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Sprial Chute mounting | Completed |  | 2026-02-10 |  | Pierre Damis | Pierre Damis
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Engineering | System Components | Hybrid FAT - Site Visit | Completed |  | 2026-02-19 |  | Rasmus Sorensen | Rasmus Sorensen | Hybrid destination test
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | Asbuild - Fencing Layout | On schedule |  | 2026-03-27 |  | Pierre Damis | David Blanco | [NG1WLM-134] Fencing redlines - Jira
Logistics | Walmart | Knapp | IND3 | Loop Sorter | Project Layouts | Installation Drawings | DST installation layout update | On schedule |  | 2026-03-06 |  | Alex Raff | David Blanco | Add dimension for caljen extendable conveyor. check note in teams labelled "IND_INST_UPDATE_1"

## MT
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Mechatronics | N/A | N/A | N/A | N/A

## CS_NG 2&3
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | On schedule |  |  | Jameson Fitzpatrick |  |  | 1/2" ordered last time, order 3/8" fully threaded
Customer Support | Walmart | Knapp | NG2 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing & Induction Unit Mounting | On schedule |  |  | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Project Engineering | System Components | Safety Fencing | On schedule |  |  | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | On schedule |  |  | Jameson Fitzpatrick |  |  | 1/2" ordered last time, order 3/8" fully threaded
Customer Support | Walmart | Knapp | NG3 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing & Induction Unit Mounting | On schedule |  |  | Jameson Fitzpatrick

## CS_ NG1
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt - Electrical Components | Completed |  | 2026-01-29 | Jameson Fitzpatrick | Jameson Fitzpatrick |  | BCH to confirm if provided
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt - Lenze Motor | Completed |  | 2026-01-28 | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Break Belt Infeed Conveyor | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Jameson Fitzpatrick
| Walmart | Knapp | NG2 | Loop Sorter | Design Engineering | Chute Design | Chute - Carton | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Chute - Carton | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis |  | Update xref
| Walmart | Knapp | NG4 | Loop Sorter | Design Engineering | Chute Design | Chute - Tote | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Destination - IB MDR | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Destination - OB Break belt | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Induction Unit - Mounting Details | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting and Hardware | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Jameson Fitzpatrick | James Bragg
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | MRF | Safety Fencing | Completed |  |  | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | Installation Drawings | Safety Fencing | Completed |  | 2026-02-09 | Jameson Fitzpatrick | Jameson Fitzpatrick
| Walmart | Knapp | NG1 | Loop Sorter | Project Layouts | MRF | Induction Unit - Mounting Hardware | Completed |  | 2026-01-28 | Jameson Fitzpatrick | Jameson Fitzpatrick
Customer Support | Walmart | Knapp | NG1 | Loop Sorter | Project Engineering | System Components | Chute - Tote | Completed |  | 2026-01-01 | Jameson Fitzpatrick | Pierre Damis |  | Update xref

## CS_ Digikey
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Safety Fence Panels | Completed |  |  | Jameson Fitzpatrick
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Induction Anchors | Completed |  |  | Jameson Fitzpatrick
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Engineering | System Components | Safety Fence Anchors | Completed |  |  | Jameson Fitzpatrick
Customer Support | Digikey | N/A | DigiKey | Loop Sorter | Project Layouts | Installation Drawings | Safety Fence | Completed |  |  | Jameson Fitzpatrick

## CS_NG Lite
Division | Customer | Integ | Name | System | Task Category | Area | Deliverable | Status | Review Date | Due Date | Project Lead | Area Owner | Execution Owner | Comments
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Project Engineering | System Components | Safety Fencing | Completed |  |  | Jameson Fitzpatrick | Pierre Damis | Pierre Damis
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Design Engineering | Detail Design | Induction Unit - Mounting & Hardware | Completed |  |  | Jameson Fitzpatrick
Customer Support | Walmart | N/A | NG Lite | Loop Sorter | Project Layouts | Installation Drawings | Induction Unit - Mounitng Details | Completed |  |  | Jameson Fitzpatrick

## EE Workflow
Division | Customer | Integ | Project Schedule | Eng Scope | System (Draft) | Task Sequence (Draft) | Task Category | Area | Deliverable | Status | Review Date | Schedule | Estimated Duration | Project phase Duration | Project Lead | Area Owner | Execution Owner | Comments | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64 | Column65 | Column66 | Column67 | Column68 | Column69 | Column70 | Column71 | Column72 | Column73 | Column74 | Column75 | Column76 | Column77 | Column78 | Column79 | Column80 | Column81 | Column82 | Column83 | Column84 | Column85 | Column86 | Column87 | Column88 | Column89 | Column90 | Column91 | Column92 | Column93 | Column94 | Column95 | Column96 | Column97 | Column98 | Column99 | Column100 | Column101 | Column102 | Column103 | Column104 | Column105 | Column106 | Column107 | Column108 | Column109 | Column110 | Column111 | Column112 | Column113 | Column114 | Column115 | Column116 | Column117 | Column118 | Column119 | Column120 | Column121 | Column122 | Column123 | Column124 | Column125 | Column126 | Column127 | Column128 | Column129 | Column130 | Column131 | Column132 | Column133 | Column134 | Column135 | Column136 | Column137 | Column138 | Column139 | Column140 | Column141 | Column142 | Column143 | Column144 | Column145 | Column146 | Column147 | Column148 | Column149 | Column150 | Column151 | Column152 | Column153 | Column154 | Column155 | Column156 | Column157 | Column158 | Column159 | Column160 | Column161 | Column162 | Column163 | Column164 | Column165 | Column166 | Column167 | Column168 | Column169 | Column170 | Column171 | Column172 | Column173 | Column174 | Column175 | Column176 | Column177 | Column178 | Column179 | Column180 | Column181 | Column182 | Column183 | Column184 | Column185 | Column186 | Column187 | Column188 | Column189 | Column190 | Column191 | Column192 | Column193 | Column194 | Column195 | Column196 | Column197 | Column198 | Column199 | Column200 | Column201 | Column202 | Column203 | Column204 | Column205 | Column206 | Column207 | Column208 | Column209 | Column210 | Column211 | Column212 | Column213 | Column214 | Column215 | Column216 | Column217 | Column218 | Column219 | Column220 | Column221 | Column222 | Column223 | Column224 | Column225 | Column226 | Column227 | Column228 | Column229 | Column230 | Column231 | Column232 | Column233 | Column234 | Column235 | Column236 | Column237 | Column238 | Column239 | Column240 | Column241 | Column242 | Column243 | Column244 | Column245 | Column246 | Column247 | Column248 | Column249 | Column250 | Column251 | Column252 | Column253 | Column254 | Column255 | Column256 | Column257 | Column258 | Column259 | Column260 | Column261 | Column262 | Column263 | Column264 | Column265 | Column266 | Column267 | Column268 | Column269 | Column270 | Column271 | Column272 | Column273 | Column274 | Column275 | Column276 | Column277 | Column278 | Column279 | Column280 | Column281 | Column282 | Column283 | Column284 | Column285 | Column286 | Column287 | Column288 | Column289 | Column290 | Column291 | Column292 | Column293 | Column294 | Column295 | Column296 | Column297 | Column298 | Column299 | Column300 | Column301 | Column302 | Column303 | Column304 | Column305 | Column306 | Column307 | Column308 | Column309 | Column310 | Column311 | Column312 | Column313 | Column314 | Column315 | Column316 | Column317 | Column318 | Column319 | Column320 | Column321 | Column322 | Column323 | Column324 | Column325 | Column326 | Column327 | Column328 | Column329 | Column330 | Column331 | Column332 | Column333 | Column334 | Column335 | Column336 | Column337 | Column338 | Column339 | Column340 | Column341 | Column342 | Column343 | Column344 | Column345 | Column346 | Column347 | Column348 | Column349 | Column350 | Column351 | Column352 | Column353 | Column354 | Column355 | Column356 | Column357 | Column358 | Column359 | Column360 | Column361 | Column362 | Column363 | Column364 | Column365 | Column366 | Column367 | Column368 | Column369 | Column370 | Column371 | Column372 | Column373 | Column374 | Column375 | Column376 | Column377 | Column378 | Column379 | Column380 | Column381 | Column382 | Column383 | Column384 | Column385 | Column386 | Column387 | Column388 | Column389 | Column390 | Column391 | Column392 | Column393 | Column394 | Column395 | Column396 | Column397 | Column398 | Column399 | Column400 | Column401 | Column402 | Column403 | Column404 | Column405 | Column406 | Column407 | Column408 | Column409 | Column410 | Column411 | Column412 | Column413 | Column414 | Column415 | Column416 | Column417 | Column418 | Column419 | Column420 | Column421 | Column422 | Column423 | Column424 | Column425 | Column426 | Column427 | Column428 | Column429 | Column430 | Column431 | Column432 | Column433 | Column434 | Column435 | Column436 | Column437 | Column438 | Column439 | Column440 | Column441 | Column442 | Column443 | Column444 | Column445 | Column446 | Column447 | Column448 | Column449 | Column450 | Column451 | Column452 | Column453 | Column454 | Column455 | Column456 | Column457 | Column458 | Column459 | Column460 | Column461 | Column462 | Column463 | Column464 | Column465 | Column466 | Column467 | Column468 | Column469 | Column470 | Column471 | Column472 | Column473 | Column474 | Column475 | Column476 | Column477 | Column478 | Column479 | Column480 | Column481 | Column482 | Column483 | Column484 | Column485 | Column486 | Column487 | Column488 | Column489 | Column490 | Column491 | Column492 | Column493 | Column494 | Column495 | Column496 | Column497 | Column498 | Column499 | Column500 | Column501 | Column502 | Column503 | Column504 | Column505 | Column506 | Column507 | Column508 | Column509 | Column510 | Column511 | Column512 | Column513 | Column514 | Column515 | Column516 | Column517 | Column518 | Column519 | Column520 | Column521 | Column522 | Column523 | Column524 | Column525 | Column526 | Column527 | Column528 | Column529 | Column530 | Column531 | Column532 | Column533 | Column534 | Column535 | Column536 | Column537 | Column538 | Column539 | Column540 | Column541 | Column542 | Column543 | Column544 | Column545 | Column546 | Column547 | Column548 | Column549 | Column550 | Column551 | Column552 | Column553 | Column554 | Column555 | Column556 | Column557 | Column558 | Column559 | Column560 | Column561 | Column562 | Column563 | Column564 | Column565 | Column566 | Column567 | Column568 | Column569 | Column570 | Column571 | Column572 | Column573 | Column574 | Column575 | Column576 | Column577 | Column578 | Column579 | Column580 | Column581 | Column582 | Column583 | Column584 | Column585 | Column586 | Column587 | Column588 | Column589 | Column590 | Column591 | Column592 | Column593 | Column594 | Column595 | Column596 | Column597 | Column598 | Column599 | Column600 | Column601 | Column602 | Column603 | Column604 | Column605 | Column606 | Column607 | Column608 | Column609 | Column610 | Column611 | Column612 | Column613 | Column614 | Column615 | Column616 | Column617 | Column618 | Column619 | Column620 | Column621 | Column622 | Column623 | Column624 | Column625 | Column626 | Column627 | Column628 | Column629 | Column630 | Column631 | Column632 | Column633 | Column634 | Column635 | Column636 | Column637 | Column638 | Column639 | Column640 | Column641 | Column642 | Column643 | Column644 | Column645 | Column646 | Column647 | Column648 | Column649 | Column650 | Column651 | Column652 | Column653 | Column654 | Column655 | Column656 | Column657 | Column658 | Column659 | Column660 | Column661 | Column662 | Column663 | Column664 | Column665 | Column666 | Column667 | Column668 | Column669 | Column670 | Column671 | Column672 | Column673 | Column674 | Column675 | Column676 | Column677 | Column678 | Column679 | Column680 | Column681 | Column682 | Column683 | Column684 | Column685 | Column686 | Column687 | Column688 | Column689 | Column690 | Column691 | Column692 | Column693 | Column694 | Column695 | Column696 | Column697 | Column698 | Column699 | Column700 | Column701 | Column702 | Column703 | Column704 | Column705 | Column706 | Column707 | Column708 | Column709 | Column710 | Column711 | Column712 | Column713 | Column714 | Column715 | Column716 | Column717 | Column718 | Column719 | Column720 | Column721 | Column722 | Column723 | Column724 | Column725 | Column726 | Column727 | Column728 | Column729 | Column730 | Column731 | Column732 | Column733 | Column734 | Column735 | Column736 | Column737 | Column738 | Column739 | Column740 | Column741 | Column742 | Column743 | Column744 | Column745 | Column746 | Column747 | Column748 | Column749 | Column750 | Column751 | Column752 | Column753 | Column754 | Column755 | Column756 | Column757 | Column758 | Column759 | Column760 | Column761 | Column762 | Column763 | Column764 | Column765 | Column766 | Column767 | Column768 | Column769 | Column770 | Column771 | Column772 | Column773 | Column774 | Column775 | Column776 | Column777 | Column778 | Column779 | Column780 | Column781 | Column782 | Column783 | Column784 | Column785 | Column786 | Column787 | Column788 | Column789 | Column790 | Column791 | Column792 | Column793 | Column794 | Column795 | Column796 | Column797 | Column798 | Column799 | Column800 | Column801 | Column802 | Column803 | Column804 | Column805 | Column806 | Column807 | Column808 | Column809 | Column810 | Column811 | Column812 | Column813 | Column814 | Column815 | Column816 | Column817 | Column818 | Column819 | Column820 | Column821 | Column822 | Column823 | Column824 | Column825 | Column826 | Column827 | Column828 | Column829 | Column830 | Column831 | Column832 | Column833 | Column834 | Column835 | Column836 | Column837 | Column838 | Column839 | Column840 | Column841 | Column842 | Column843 | Column844 | Column845 | Column846 | Column847 | Column848 | Column849 | Column850 | Column851 | Column852 | Column853 | Column854 | Column855 | Column856 | Column857 | Column858 | Column859 | Column860 | Column861 | Column862 | Column863 | Column864 | Column865 | Column866 | Column867 | Column868 | Column869 | Column870 | Column871 | Column872 | Column873 | Column874 | Column875 | Column876 | Column877 | Column878 | Column879 | Column880 | Column881 | Column882 | Column883 | Column884 | Column885 | Column886 | Column887 | Column888 | Column889 | Column890 | Column891 | Column892 | Column893 | Column894 | Column895 | Column896 | Column897 | Column898 | Column899 | Column900 | Column901 | Column902 | Column903 | Column904 | Column905 | Column906 | Column907 | Column908 | Column909 | Column910 | Column911 | Column912 | Column913 | Column914 | Column915 | Column916 | Column917 | Column918 | Column919 | Column920 | Column921 | Column922 | Column923 | Column924 | Column925 | Column926 | Column927 | Column928 | Column929 | Column930 | Column931 | Column932 | Column933 | Column934 | Column935 | Column936 | Column937 | Column938 | Column939 | Column940 | Column941 | Column942 | Column943 | Column944 | Column945 | Column946 | Column947 | Column948 | Column949 | Column950 | Column951 | Column952 | Column953 | Column954 | Column955 | Column956 | Column957 | Column958 | Column959 | Column960 | Column961 | Column962 | Column963 | Column964 | Column965 | Column966 | Column967 | Column968 | Column969 | Column970 | Column971 | Column972 | Column973 | Column974 | Column975 | Column976 | Column977 | Column978 | Column979 | Column980 | Column981 | Column982 | Column983 | Column984 | Column985 | Column986 | Column987 | Column988 | Column989 | Column990 | Column991 | Column992 | Column993 | Column994 | Column995 | Column996 | Column997 | Column998 | Column999 | Column1000 | Column1001 | Column1002 | Column1003 | Column1004 | Column1005 | Column1006 | Column1007 | Column1008 | Column1009 | Column1010 | Column1011 | Column1012 | Column1013 | Column1014 | Column1015 | Column1016 | Column1017 | Column1018 | Column1019 | Column1020 | Column1021 | Column1022 | Column1023 | Column1024 | Column1025 | Column1026 | Column1027 | Column1028 | Column1029 | Column1030 | Column1031 | Column1032 | Column1033 | Column1034 | Column1035 | Column1036 | Column1037 | Column1038 | Column1039 | Column1040 | Column1041 | Column1042 | Column1043 | Column1044 | Column1045 | Column1046 | Column1047 | Column1048 | Column1049 | Column1050 | Column1051 | Column1052 | Column1053 | Column1054 | Column1055 | Column1056 | Column1057 | Column1058 | Column1059 | Column1060 | Column1061 | Column1062 | Column1063 | Column1064 | Column1065 | Column1066 | Column1067 | Column1068 | Column1069 | Column1070 | Column1071 | Column1072 | Column1073 | Column1074 | Column1075 | Column1076 | Column1077 | Column1078 | Column1079 | Column1080 | Column1081 | Column1082 | Column1083 | Column1084 | Column1085 | Column1086 | Column1087 | Column1088 | Column1089 | Column1090 | Column1091 | Column1092 | Column1093 | Column1094 | Column1095 | Column1096 | Column1097 | Column1098 | Column1099 | Column1100 | Column1101 | Column1102 | Column1103 | Column1104 | Column1105 | Column1106 | Column1107 | Column1108 | Column1109 | Column1110 | Column1111 | Column1112 | Column1113 | Column1114 | Column1115 | Column1116 | Column1117 | Column1118 | Column1119 | Column1120 | Column1121 | Column1122 | Column1123 | Column1124 | Column1125 | Column1126 | Column1127 | Column1128 | Column1129 | Column1130 | Column1131 | Column1132 | Column1133 | Column1134 | Column1135 | Column1136 | Column1137 | Column1138 | Column1139 | Column1140 | Column1141 | Column1142 | Column1143 | Column1144 | Column1145 | Column1146 | Column1147 | Column1148 | Column1149 | Column1150 | Column1151 | Column1152 | Column1153 | Column1154 | Column1155 | Column1156 | Column1157 | Column1158 | Column1159 | Column1160 | Column1161 | Column1162 | Column1163 | Column1164 | Column1165 | Column1166 | Column1167 | Column1168 | Column1169 | Column1170 | Column1171 | Column1172 | Column1173 | Column1174 | Column1175 | Column1176 | Column1177 | Column1178 | Column1179 | Column1180 | Column1181 | Column1182 | Column1183 | Column1184 | Column1185 | Column1186 | Column1187 | Column1188 | Column1189 | Column1190 | Column1191 | Column1192 | Column1193 | Column1194 | Column1195 | Column1196 | Column1197 | Column1198 | Column1199 | Column1200 | Column1201 | Column1202 | Column1203 | Column1204 | Column1205 | Column1206 | Column1207 | Column1208 | Column1209 | Column1210 | Column1211 | Column1212 | Column1213 | Column1214 | Column1215 | Column1216 | Column1217 | Column1218 | Column1219 | Column1220 | Column1221 | Column1222 | Column1223 | Column1224 | Column1225 | Column1226 | Column1227 | Column1228 | Column1229 | Column1230 | Column1231 | Column1232 | Column1233 | Column1234 | Column1235 | Column1236 | Column1237 | Column1238 | Column1239 | Column1240 | Column1241 | Column1242 | Column1243 | Column1244 | Column1245 | Column1246 | Column1247 | Column1248 | Column1249 | Column1250 | Column1251 | Column1252 | Column1253 | Column1254 | Column1255 | Column1256 | Column1257 | Column1258 | Column1259 | Column1260 | Column1261 | Column1262 | Column1263 | Column1264 | Column1265 | Column1266 | Column1267 | Column1268 | Column1269 | Column1270 | Column1271 | Column1272 | Column1273 | Column1274 | Column1275 | Column1276 | Column1277 | Column1278 | Column1279 | Column1280 | Column1281 | Column1282 | Column1283 | Column1284 | Column1285 | Column1286 | Column1287 | Column1288 | Column1289 | Column1290 | Column1291 | Column1292 | Column1293 | Column1294 | Column1295 | Column1296 | Column1297 | Column1298 | Column1299 | Column1300 | Column1301 | Column1302 | Column1303 | Column1304 | Column1305 | Column1306 | Column1307 | Column1308 | Column1309 | Column1310 | Column1311 | Column1312 | Column1313 | Column1314 | Column1315 | Column1316 | Column1317 | Column1318 | Column1319 | Column1320 | Column1321 | Column1322 | Column1323 | Column1324 | Column1325 | Column1326 | Column1327 | Column1328 | Column1329 | Column1330 | Column1331 | Column1332 | Column1333 | Column1334 | Column1335 | Column1336 | Column1337 | Column1338 | Column1339 | Column1340 | Column1341 | Column1342 | Column1343 | Column1344 | Column1345 | Column1346 | Column1347 | Column1348 | Column1349 | Column1350 | Column1351 | Column1352 | Column1353 | Column1354 | Column1355 | Column1356 | Column1357 | Column1358 | Column1359 | Column1360 | Column1361 | Column1362 | Column1363 | Column1364 | Column1365 | Column1366 | Column1367 | Column1368 | Column1369 | Column1370 | Column1371 | Column1372 | Column1373 | Column1374 | Column1375 | Column1376 | Column1377 | Column1378 | Column1379 | Column1380 | Column1381 | Column1382 | Column1383 | Column1384 | Column1385 | Column1386 | Column1387 | Column1388 | Column1389 | Column1390 | Column1391 | Column1392 | Column1393 | Column1394 | Column1395 | Column1396 | Column1397 | Column1398 | Column1399 | Column1400 | Column1401 | Column1402 | Column1403 | Column1404 | Column1405 | Column1406 | Column1407 | Column1408 | Column1409 | Column1410 | Column1411 | Column1412 | Column1413 | Column1414 | Column1415 | Column1416 | Column1417 | Column1418 | Column1419 | Column1420 | Column1421 | Column1422 | Column1423 | Column1424 | Column1425 | Column1426 | Column1427 | Column1428 | Column1429 | Column1430 | Column1431 | Column1432 | Column1433 | Column1434 | Column1435 | Column1436 | Column1437 | Column1438 | Column1439 | Column1440 | Column1441 | Column1442 | Column1443 | Column1444 | Column1445 | Column1446 | Column1447 | Column1448 | Column1449 | Column1450 | Column1451 | Column1452 | Column1453 | Column1454 | Column1455 | Column1456 | Column1457 | Column1458 | Column1459 | Column1460 | Column1461 | Column1462 | Column1463 | Column1464 | Column1465 | Column1466 | Column1467 | Column1468 | Column1469 | Column1470 | Column1471 | Column1472 | Column1473 | Column1474 | Column1475 | Column1476 | Column1477 | Column1478 | Column1479 | Column1480 | Column1481 | Column1482 | Column1483 | Column1484 | Column1485 | Column1486 | Column1487 | Column1488 | Column1489 | Column1490 | Column1491 | Column1492 | Column1493 | Column1494 | Column1495 | Column1496 | Column1497 | Column1498 | Column1499 | Column1500 | Column1501 | Column1502 | Column1503 | Column1504 | Column1505 | Column1506 | Column1507 | Column1508 | Column1509 | Column1510 | Column1511 | Column1512 | Column1513 | Column1514 | Column1515 | Column1516 | Column1517 | Column1518 | Column1519 | Column1520 | Column1521 | Column1522 | Column1523 | Column1524 | Column1525 | Column1526 | Column1527 | Column1528 | Column1529 | Column1530 | Column1531 | Column1532 | Column1533 | Column1534 | Column1535 | Column1536 | Column1537 | Column1538 | Column1539 | Column1540 | Column1541 | Column1542 | Column1543 | Column1544 | Column1545 | Column1546 | Column1547 | Column1548 | Column1549 | Column1550 | Column1551 | Column1552 | Column1553 | Column1554 | Column1555 | Column1556 | Column1557 | Column1558 | Column1559 | Column1560 | Column1561 | Column1562 | Column1563 | Column1564 | Column1565 | Column1566 | Column1567 | Column1568 | Column1569 | Column1570 | Column1571 | Column1572 | Column1573 | Column1574 | Column1575 | Column1576 | Column1577 | Column1578 | Column1579 | Column1580 | Column1581 | Column1582 | Column1583 | Column1584 | Column1585 | Column1586 | Column1587 | Column1588 | Column1589 | Column1590 | Column1591 | Column1592 | Column1593 | Column1594 | Column1595 | Column1596 | Column1597 | Column1598 | Column1599 | Column1600 | Column1601 | Column1602 | Column1603 | Column1604 | Column1605 | Column1606 | Column1607 | Column1608 | Column1609 | Column1610 | Column1611 | Column1612 | Column1613 | Column1614 | Column1615 | Column1616 | Column1617 | Column1618 | Column1619 | Column1620 | Column1621 | Column1622 | Column1623 | Column1624 | Column1625 | Column1626 | Column1627 | Column1628 | Column1629 | Column1630 | Column1631 | Column1632 | Column1633 | Column1634 | Column1635 | Column1636 | Column1637 | Column1638 | Column1639 | Column1640 | Column1641 | Column1642 | Column1643 | Column1644 | Column1645 | Column1646 | Column1647 | Column1648 | Column1649 | Column1650 | Column1651 | Column1652 | Column1653 | Column1654 | Column1655 | Column1656 | Column1657 | Column1658 | Column1659 | Column1660 | Column1661 | Column1662 | Column1663 | Column1664 | Column1665 | Column1666 | Column1667 | Column1668 | Column1669 | Column1670 | Column1671 | Column1672 | Column1673 | Column1674 | Column1675 | Column1676 | Column1677 | Column1678 | Column1679 | Column1680 | Column1681 | Column1682 | Column1683 | Column1684 | Column1685 | Column1686 | Column1687 | Column1688 | Column1689 | Column1690 | Column1691 | Column1692 | Column1693 | Column1694 | Column1695 | Column1696 | Column1697 | Column1698 | Column1699 | Column1700 | Column1701 | Column1702 | Column1703 | Column1704 | Column1705 | Column1706 | Column1707 | Column1708 | Column1709 | Column1710 | Column1711 | Column1712 | Column1713 | Column1714 | Column1715 | Column1716 | Column1717 | Column1718 | Column1719 | Column1720 | Column1721 | Column1722 | Column1723 | Column1724 | Column1725 | Column1726 | Column1727 | Column1728 | Column1729 | Column1730 | Column1731 | Column1732 | Column1733 | Column1734 | Column1735 | Column1736 | Column1737 | Column1738 | Column1739 | Column1740 | Column1741 | Column1742 | Column1743 | Column1744 | Column1745 | Column1746 | Column1747 | Column1748 | Column1749 | Column1750 | Column1751 | Column1752 | Column1753 | Column1754 | Column1755 | Column1756 | Column1757 | Column1758 | Column1759 | Column1760 | Column1761 | Column1762 | Column1763 | Column1764 | Column1765 | Column1766 | Column1767 | Column1768 | Column1769 | Column1770 | Column1771 | Column1772 | Column1773 | Column1774 | Column1775 | Column1776 | Column1777 | Column1778 | Column1779 | Column1780 | Column1781 | Column1782 | Column1783 | Column1784 | Column1785 | Column1786 | Column1787 | Column1788 | Column1789 | Column1790 | Column1791 | Column1792 | Column1793 | Column1794 | Column1795 | Column1796 | Column1797 | Column1798 | Column1799 | Column1800 | Column1801 | Column1802 | Column1803 | Column1804 | Column1805 | Column1806 | Column1807 | Column1808 | Column1809 | Column1810 | Column1811 | Column1812 | Column1813 | Column1814 | Column1815 | Column1816 | Column1817 | Column1818 | Column1819 | Column1820 | Column1821 | Column1822 | Column1823 | Column1824 | Column1825 | Column1826 | Column1827 | Column1828 | Column1829 | Column1830 | Column1831 | Column1832 | Column1833 | Column1834 | Column1835 | Column1836 | Column1837 | Column1838 | Column1839 | Column1840 | Column1841 | Column1842 | Column1843 | Column1844 | Column1845 | Column1846 | Column1847 | Column1848 | Column1849 | Column1850 | Column1851 | Column1852 | Column1853 | Column1854 | Column1855 | Column1856 | Column1857 | Column1858 | Column1859 | Column1860 | Column1861 | Column1862 | Column1863 | Column1864 | Column1865 | Column1866 | Column1867 | Column1868 | Column1869 | Column1870 | Column1871 | Column1872 | Column1873 | Column1874 | Column1875 | Column1876 | Column1877 | Column1878 | Column1879 | Column1880 | Column1881 | Column1882 | Column1883 | Column1884 | Column1885 | Column1886 | Column1887 | Column1888 | Column1889 | Column1890 | Column1891 | Column1892 | Column1893 | Column1894 | Column1895 | Column1896 | Column1897 | Column1898 | Column1899 | Column1900 | Column1901 | Column1902 | Column1903 | Column1904 | Column1905 | Column1906 | Column1907 | Column1908 | Column1909 | Column1910 | Column1911 | Column1912 | Column1913 | Column1914 | Column1915 | Column1916 | Column1917 | Column1918 | Column1919 | Column1920 | Column1921 | Column1922 | Column1923 | Column1924 | Column1925 | Column1926 | Column1927 | Column1928 | Column1929 | Column1930 | Column1931 | Column1932 | Column1933 | Column1934 | Column1935 | Column1936 | Column1937 | Column1938 | Column1939 | Column1940 | Column1941 | Column1942 | Column1943 | Column1944 | Column1945 | Column1946 | Column1947 | Column1948 | Column1949 | Column1950 | Column1951 | Column1952 | Column1953 | Column1954 | Column1955 | Column1956 | Column1957 | Column1958 | Column1959 | Column1960 | Column1961 | Column1962 | Column1963 | Column1964 | Column1965 | Column1966 | Column1967 | Column1968 | Column1969 | Column1970 | Column1971 | Column1972 | Column1973 | Column1974 | Column1975 | Column1976 | Column1977 | Column1978 | Column1979 | Column1980 | Column1981 | Column1982 | Column1983 | Column1984 | Column1985 | Column1986 | Column1987 | Column1988 | Column1989 | Column1990 | Column1991 | Column1992 | Column1993 | Column1994 | Column1995 | Column1996 | Column1997 | Column1998 | Column1999 | Column2000 | Column2001 | Column2002 | Column2003 | Column2004 | Column2005 | Column2006 | Column2007 | Column2008 | Column2009 | Column2010 | Column2011 | Column2012 | Column2013 | Column2014 | Column2015 | Column2016 | Column2017 | Column2018 | Column2019 | Column2020 | Column2021 | Column2022 | Column2023 | Column2024 | Column2025 | Column2026 | Column2027 | Column2028 | Column2029 | Column2030 | Column2031 | Column2032 | Column2033 | Column2034 | Column2035 | Column2036 | Column2037 | Column2038 | Column2039 | Column2040 | Column2041 | Column2042 | Column2043 | Column2044 | Column2045 | Column2046 | Column2047 | Column2048 | Column2049 | Column2050 | Column2051 | Column2052 | Column2053 | Column2054 | Column2055 | Column2056 | Column2057 | Column2058 | Column2059 | Column2060 | Column2061 | Column2062 | Column2063 | Column2064 | Column2065 | Column2066 | Column2067 | Column2068 | Column2069 | Column2070 | Column2071 | Column2072 | Column2073 | Column2074 | Column2075 | Column2076 | Column2077 | Column2078 | Column2079 | Column2080 | Column2081 | Column2082 | Column2083 | Column2084 | Column2085 | Column2086 | Column2087 | Column2088 | Column2089 | Column2090 | Column2091 | Column2092 | Column2093 | Column2094 | Column2095 | Column2096 | Column2097 | Column2098 | Column2099 | Column2100 | Column2101 | Column2102 | Column2103 | Column2104 | Column2105 | Column2106 | Column2107 | Column2108 | Column2109 | Column2110 | Column2111 | Column2112 | Column2113 | Column2114 | Column2115 | Column2116 | Column2117 | Column2118 | Column2119 | Column2120 | Column2121 | Column2122 | Column2123 | Column2124 | Column2125 | Column2126 | Column2127 | Column2128 | Column2129 | Column2130 | Column2131 | Column2132 | Column2133 | Column2134 | Column2135 | Column2136 | Column2137 | Column2138 | Column2139 | Column2140 | Column2141 | Column2142 | Column2143 | Column2144 | Column2145 | Column2146 | Column2147 | Column2148 | Column2149 | Column2150 | Column2151 | Column2152 | Column2153 | Column2154 | Column2155 | Column2156 | Column2157 | Column2158 | Column2159 | Column2160 | Column2161 | Column2162 | Column2163 | Column2164 | Column2165 | Column2166 | Column2167 | Column2168 | Column2169 | Column2170 | Column2171 | Column2172 | Column2173 | Column2174 | Column2175 | Column2176 | Column2177 | Column2178 | Column2179 | Column2180 | Column2181 | Column2182 | Column2183 | Column2184 | Column2185 | Column2186 | Column2187 | Column2188 | Column2189 | Column2190 | Column2191 | Column2192 | Column2193 | Column2194 | Column2195 | Column2196 | Column2197 | Column2198 | Column2199 | Column2200 | Column2201 | Column2202 | Column2203 | Column2204 | Column2205 | Column2206 | Column2207 | Column2208 | Column2209 | Column2210 | Column2211 | Column2212 | Column2213 | Column2214 | Column2215 | Column2216 | Column2217 | Column2218 | Column2219 | Column2220 | Column2221 | Column2222 | Column2223 | Column2224 | Column2225 | Column2226 | Column2227 | Column2228 | Column2229 | Column2230 | Column2231 | Column2232 | Column2233 | Column2234 | Column2235 | Column2236 | Column2237 | Column2238 | Column2239 | Column2240 | Column2241 | Column2242 | Column2243 | Column2244 | Column2245 | Column2246 | Column2247 | Column2248 | Column2249 | Column2250 | Column2251 | Column2252 | Column2253 | Column2254 | Column2255 | Column2256 | Column2257 | Column2258 | Column2259 | Column2260 | Column2261 | Column2262 | Column2263 | Column2264 | Column2265 | Column2266 | Column2267 | Column2268 | Column2269 | Column2270 | Column2271 | Column2272 | Column2273 | Column2274 | Column2275 | Column2276 | Column2277 | Column2278 | Column2279 | Column2280 | Column2281 | Column2282 | Column2283 | Column2284 | Column2285 | Column2286 | Column2287 | Column2288 | Column2289 | Column2290 | Column2291 | Column2292 | Column2293 | Column2294 | Column2295 | Column2296 | Column2297 | Column2298 | Column2299 | Column2300 | Column2301 | Column2302 | Column2303 | Column2304 | Column2305 | Column2306 | Column2307 | Column2308 | Column2309 | Column2310 | Column2311 | Column2312 | Column2313 | Column2314 | Column2315 | Column2316 | Column2317 | Column2318 | Column2319 | Column2320 | Column2321 | Column2322 | Column2323 | Column2324 | Column2325 | Column2326 | Column2327 | Column2328 | Column2329 | Column2330 | Column2331 | Column2332 | Column2333 | Column2334 | Column2335 | Column2336 | Column2337 | Column2338 | Column2339 | Column2340 | Column2341 | Column2342 | Column2343 | Column2344 | Column2345 | Column2346 | Column2347 | Column2348 | Column2349 | Column2350 | Column2351 | Column2352 | Column2353 | Column2354 | Column2355 | Column2356 | Column2357 | Column2358 | Column2359 | Column2360 | Column2361 | Column2362 | Column2363 | Column2364 | Column2365 | Column2366 | Column2367 | Column2368 | Column2369 | Column2370 | Column2371 | Column2372 | Column2373 | Column2374 | Column2375 | Column2376 | Column2377 | Column2378 | Column2379 | Column2380 | Column2381 | Column2382 | Column2383 | Column2384 | Column2385 | Column2386 | Column2387 | Column2388 | Column2389 | Column2390 | Column2391 | Column2392 | Column2393 | Column2394 | Column2395 | Column2396 | Column2397 | Column2398 | Column2399 | Column2400 | Column2401 | Column2402 | Column2403 | Column2404 | Column2405 | Column2406 | Column2407 | Column2408 | Column2409 | Column2410 | Column2411 | Column2412 | Column2413 | Column2414 | Column2415 | Column2416 | Column2417 | Column2418 | Column2419 | Column2420 | Column2421 | Column2422 | Column2423 | Column2424 | Column2425 | Column2426 | Column2427 | Column2428 | Column2429 | Column2430 | Column2431 | Column2432 | Column2433 | Column2434 | Column2435 | Column2436 | Column2437 | Column2438 | Column2439 | Column2440 | Column2441 | Column2442 | Column2443 | Column2444 | Column2445 | Column2446 | Column2447 | Column2448 | Column2449 | Column2450 | Column2451 | Column2452 | Column2453 | Column2454 | Column2455 | Column2456 | Column2457 | Column2458 | Column2459 | Column2460 | Column2461 | Column2462 | Column2463 | Column2464 | Column2465 | Column2466 | Column2467 | Column2468 | Column2469 | Column2470 | Column2471 | Column2472 | Column2473 | Column2474 | Column2475 | Column2476 | Column2477 | Column2478 | Column2479 | Column2480 | Column2481 | Column2482 | Column2483 | Column2484 | Column2485 | Column2486 | Column2487 | Column2488 | Column2489 | Column2490 | Column2491 | Column2492 | Column2493 | Column2494 | Column2495 | Column2496 | Column2497 | Column2498 | Column2499 | Column2500 | Column2501 | Column2502 | Column2503 | Column2504 | Column2505 | Column2506 | Column2507 | Column2508 | Column2509 | Column2510 | Column2511 | Column2512 | Column2513 | Column2514 | Column2515 | Column2516 | Column2517 | Column2518 | Column2519 | Column2520 | Column2521 | Column2522 | Column2523 | Column2524 | Column2525 | Column2526 | Column2527 | Column2528 | Column2529 | Column2530 | Column2531 | Column2532 | Column2533 | Column2534 | Column2535 | Column2536 | Column2537 | Column2538 | Column2539 | Column2540 | Column2541 | Column2542 | Column2543 | Column2544 | Column2545 | Column2546 | Column2547 | Column2548 | Column2549 | Column2550 | Column2551 | Column2552 | Column2553 | Column2554 | Column2555 | Column2556 | Column2557 | Column2558 | Column2559 | Column2560 | Column2561 | Column2562 | Column2563 | Column2564 | Column2565 | Column2566 | Column2567 | Column2568 | Column2569 | Column2570 | Column2571 | Column2572 | Column2573 | Column2574 | Column2575 | Column2576 | Column2577 | Column2578 | Column2579 | Column2580 | Column2581 | Column2582 | Column2583 | Column2584 | Column2585 | Column2586 | Column2587 | Column2588 | Column2589 | Column2590 | Column2591 | Column2592 | Column2593 | Column2594 | Column2595 | Column2596 | Column2597 | Column2598 | Column2599 | Column2600 | Column2601 | Column2602 | Column2603 | Column2604 | Column2605 | Column2606 | Column2607 | Column2608 | Column2609 | Column2610 | Column2611 | Column2612 | Column2613 | Column2614 | Column2615 | Column2616 | Column2617 | Column2618 | Column2619 | Column2620 | Column2621 | Column2622 | Column2623 | Column2624 | Column2625 | Column2626 | Column2627 | Column2628 | Column2629 | Column2630 | Column2631 | Column2632 | Column2633 | Column2634 | Column2635 | Column2636 | Column2637 | Column2638 | Column2639 | Column2640 | Column2641 | Column2642 | Column2643 | Column2644 | Column2645 | Column2646 | Column2647 | Column2648 | Column2649 | Column2650 | Column2651 | Column2652 | Column2653 | Column2654 | Column2655 | Column2656 | Column2657 | Column2658 | Column2659 | Column2660 | Column2661 | Column2662 | Column2663 | Column2664 | Column2665 | Column2666 | Column2667 | Column2668 | Column2669 | Column2670 | Column2671 | Column2672 | Column2673 | Column2674 | Column2675 | Column2676 | Column2677 | Column2678 | Column2679 | Column2680 | Column2681 | Column2682 | Column2683 | Column2684 | Column2685 | Column2686 | Column2687 | Column2688 | Column2689 | Column2690 | Column2691 | Column2692 | Column2693 | Column2694 | Column2695 | Column2696 | Column2697 | Column2698 | Column2699 | Column2700 | Column2701 | Column2702 | Column2703 | Column2704 | Column2705 | Column2706 | Column2707 | Column2708 | Column2709 | Column2710 | Column2711 | Column2712 | Column2713 | Column2714 | Column2715 | Column2716 | Column2717 | Column2718 | Column2719 | Column2720 | Column2721 | Column2722 | Column2723 | Column2724 | Column2725 | Column2726 | Column2727 | Column2728 | Column2729 | Column2730 | Column2731 | Column2732 | Column2733 | Column2734 | Column2735 | Column2736 | Column2737 | Column2738 | Column2739 | Column2740 | Column2741 | Column2742 | Column2743 | Column2744 | Column2745 | Column2746 | Column2747 | Column2748 | Column2749 | Column2750 | Column2751 | Column2752 | Column2753 | Column2754 | Column2755 | Column2756 | Column2757 | Column2758 | Column2759 | Column2760 | Column2761 | Column2762 | Column2763 | Column2764 | Column2765 | Column2766 | Column2767 | Column2768 | Column2769 | Column2770 | Column2771 | Column2772 | Column2773 | Column2774 | Column2775 | Column2776 | Column2777 | Column2778 | Column2779 | Column2780 | Column2781 | Column2782 | Column2783 | Column2784 | Column2785 | Column2786 | Column2787 | Column2788 | Column2789 | Column2790 | Column2791 | Column2792 | Column2793 | Column2794 | Column2795 | Column2796 | Column2797 | Column2798 | Column2799 | Column2800 | Column2801 | Column2802 | Column2803 | Column2804 | Column2805 | Column2806 | Column2807 | Column2808 | Column2809 | Column2810 | Column2811 | Column2812 | Column2813 | Column2814 | Column2815 | Column2816 | Column2817 | Column2818 | Column2819 | Column2820 | Column2821 | Column2822 | Column2823 | Column2824 | Column2825 | Column2826 | Column2827 | Column2828 | Column2829 | Column2830 | Column2831 | Column2832 | Column2833 | Column2834 | Column2835 | Column2836 | Column2837 | Column2838 | Column2839 | Column2840 | Column2841 | Column2842 | Column2843 | Column2844 | Column2845 | Column2846 | Column2847 | Column2848 | Column2849 | Column2850 | Column2851 | Column2852 | Column2853 | Column2854 | Column2855 | Column2856 | Column2857 | Column2858 | Column2859 | Column2860 | Column2861 | Column2862 | Column2863 | Column2864 | Column2865 | Column2866 | Column2867 | Column2868 | Column2869 | Column2870 | Column2871 | Column2872 | Column2873 | Column2874 | Column2875 | Column2876 | Column2877 | Column2878 | Column2879 | Column2880 | Column2881 | Column2882 | Column2883 | Column2884 | Column2885 | Column2886 | Column2887 | Column2888 | Column2889 | Column2890 | Column2891 | Column2892 | Column2893 | Column2894 | Column2895 | Column2896 | Column2897 | Column2898 | Column2899 | Column2900 | Column2901 | Column2902 | Column2903 | Column2904 | Column2905 | Column2906 | Column2907 | Column2908 | Column2909 | Column2910 | Column2911 | Column2912 | Column2913 | Column2914 | Column2915 | Column2916 | Column2917 | Column2918 | Column2919 | Column2920 | Column2921 | Column2922 | Column2923 | Column2924 | Column2925 | Column2926 | Column2927 | Column2928 | Column2929 | Column2930 | Column2931 | Column2932 | Column2933 | Column2934 | Column2935 | Column2936 | Column2937 | Column2938 | Column2939 | Column2940 | Column2941 | Column2942 | Column2943 | Column2944 | Column2945 | Column2946 | Column2947 | Column2948 | Column2949 | Column2950 | Column2951 | Column2952 | Column2953 | Column2954 | Column2955 | Column2956 | Column2957 | Column2958 | Column2959 | Column2960 | Column2961 | Column2962 | Column2963 | Column2964 | Column2965 | Column2966 | Column2967 | Column2968 | Column2969 | Column2970 | Column2971 | Column2972 | Column2973 | Column2974 | Column2975 | Column2976 | Column2977 | Column2978 | Column2979 | Column2980 | Column2981 | Column2982 | Column2983 | Column2984 | Column2985 | Column2986 | Column2987 | Column2988 | Column2989 | Column2990 | Column2991 | Column2992 | Column2993 | Column2994 | Column2995 | Column2996 | Column2997 | Column2998 | Column2999 | Column3000 | Column3001 | Column3002 | Column3003 | Column3004 | Column3005 | Column3006 | Column3007 | Column3008 | Column3009 | Column3010 | Column3011 | Column3012 | Column3013 | Column3014 | Column3015 | Column3016 | Column3017 | Column3018 | Column3019 | Column3020 | Column3021 | Column3022 | Column3023 | Column3024 | Column3025 | Column3026 | Column3027 | Column3028 | Column3029 | Column3030 | Column3031 | Column3032 | Column3033 | Column3034 | Column3035 | Column3036 | Column3037 | Column3038 | Column3039 | Column3040 | Column3041 | Column3042 | Column3043 | Column3044 | Column3045 | Column3046 | Column3047 | Column3048 | Column3049 | Column3050 | Column3051 | Column3052 | Column3053 | Column3054 | Column3055 | Column3056 | Column3057 | Column3058 | Column3059 | Column3060 | Column3061 | Column3062 | Column3063 | Column3064 | Column3065 | Column3066 | Column3067 | Column3068 | Column3069 | Column3070 | Column3071 | Column3072 | Column3073 | Column3074 | Column3075 | Column3076 | Column3077 | Column3078 | Column3079 | Column3080 | Column3081 | Column3082 | Column3083 | Column3084 | Column3085 | Column3086 | Column3087 | Column3088 | Column3089 | Column3090 | Column3091 | Column3092 | Column3093 | Column3094 | Column3095 | Column3096 | Column3097 | Column3098 | Column3099 | Column3100 | Column3101 | Column3102 | Column3103 | Column3104 | Column3105 | Column3106 | Column3107 | Column3108 | Column3109 | Column3110 | Column3111 | Column3112 | Column3113 | Column3114 | Column3115 | Column3116 | Column3117 | Column3118 | Column3119 | Column3120 | Column3121 | Column3122 | Column3123 | Column3124 | Column3125 | Column3126 | Column3127 | Column3128 | Column3129 | Column3130 | Column3131 | Column3132 | Column3133 | Column3134 | Column3135 | Column3136 | Column3137 | Column3138 | Column3139 | Column3140 | Column3141 | Column3142 | Column3143 | Column3144 | Column3145 | Column3146 | Column3147 | Column3148 | Column3149 | Column3150 | Column3151 | Column3152 | Column3153 | Column3154 | Column3155 | Column3156 | Column3157 | Column3158 | Column3159 | Column3160 | Column3161 | Column3162 | Column3163 | Column3164 | Column3165 | Column3166 | Column3167 | Column3168 | Column3169 | Column3170 | Column3171 | Column3172 | Column3173 | Column3174 | Column3175 | Column3176 | Column3177 | Column3178 | Column3179 | Column3180 | Column3181 | Column3182 | Column3183 | Column3184 | Column3185 | Column3186 | Column3187 | Column3188 | Column3189 | Column3190 | Column3191 | Column3192 | Column3193 | Column3194 | Column3195 | Column3196 | Column3197 | Column3198 | Column3199 | Column3200 | Column3201 | Column3202 | Column3203 | Column3204 | Column3205 | Column3206 | Column3207 | Column3208 | Column3209 | Column3210 | Column3211 | Column3212 | Column3213 | Column3214 | Column3215 | Column3216 | Column3217 | Column3218 | Column3219 | Column3220 | Column3221 | Column3222 | Column3223 | Column3224 | Column3225 | Column3226 | Column3227 | Column3228 | Column3229 | Column3230 | Column3231 | Column3232 | Column3233 | Column3234 | Column3235 | Column3236 | Column3237 | Column3238 | Column3239 | Column3240 | Column3241 | Column3242 | Column3243 | Column3244 | Column3245 | Column3246 | Column3247 | Column3248 | Column3249 | Column3250 | Column3251 | Column3252 | Column3253 | Column3254 | Column3255 | Column3256 | Column3257 | Column3258 | Column3259 | Column3260 | Column3261 | Column3262 | Column3263 | Column3264 | Column3265 | Column3266 | Column3267 | Column3268 | Column3269 | Column3270 | Column3271 | Column3272 | Column3273 | Column3274 | Column3275 | Column3276 | Column3277 | Column3278 | Column3279 | Column3280 | Column3281 | Column3282 | Column3283 | Column3284 | Column3285 | Column3286 | Column3287 | Column3288 | Column3289 | Column3290 | Column3291 | Column3292 | Column3293 | Column3294 | Column3295 | Column3296 | Column3297 | Column3298 | Column3299 | Column3300 | Column3301 | Column3302 | Column3303 | Column3304 | Column3305 | Column3306 | Column3307 | Column3308 | Column3309 | Column3310 | Column3311 | Column3312 | Column3313 | Column3314 | Column3315 | Column3316 | Column3317 | Column3318 | Column3319 | Column3320 | Column3321 | Column3322 | Column3323 | Column3324 | Column3325 | Column3326 | Column3327 | Column3328 | Column3329 | Column3330 | Column3331 | Column3332 | Column3333 | Column3334 | Column3335 | Column3336 | Column3337 | Column3338 | Column3339 | Column3340 | Column3341 | Column3342 | Column3343 | Column3344 | Column3345 | Column3346 | Column3347 | Column3348 | Column3349 | Column3350 | Column3351 | Column3352 | Column3353 | Column3354 | Column3355 | Column3356 | Column3357 | Column3358 | Column3359 | Column3360 | Column3361 | Column3362 | Column3363 | Column3364 | Column3365 | Column3366 | Column3367 | Column3368 | Column3369 | Column3370 | Column3371 | Column3372 | Column3373 | Column3374 | Column3375 | Column3376 | Column3377 | Column3378 | Column3379 | Column3380 | Column3381 | Column3382 | Column3383 | Column3384 | Column3385 | Column3386 | Column3387 | Column3388 | Column3389 | Column3390 | Column3391 | Column3392 | Column3393 | Column3394 | Column3395 | Column3396 | Column3397 | Column3398 | Column3399 | Column3400 | Column3401 | Column3402 | Column3403 | Column3404 | Column3405 | Column3406 | Column3407 | Column3408 | Column3409 | Column3410 | Column3411 | Column3412 | Column3413 | Column3414 | Column3415 | Column3416 | Column3417 | Column3418 | Column3419 | Column3420 | Column3421 | Column3422 | Column3423 | Column3424 | Column3425 | Column3426 | Column3427 | Column3428 | Column3429 | Column3430 | Column3431 | Column3432 | Column3433 | Column3434 | Column3435 | Column3436 | Column3437 | Column3438 | Column3439 | Column3440 | Column3441 | Column3442 | Column3443 | Column3444 | Column3445 | Column3446 | Column3447 | Column3448 | Column3449 | Column3450 | Column3451 | Column3452 | Column3453 | Column3454 | Column3455 | Column3456 | Column3457 | Column3458 | Column3459 | Column3460 | Column3461 | Column3462 | Column3463 | Column3464 | Column3465 | Column3466 | Column3467 | Column3468 | Column3469 | Column3470 | Column3471 | Column3472 | Column3473 | Column3474 | Column3475 | Column3476 | Column3477 | Column3478 | Column3479 | Column3480 | Column3481 | Column3482 | Column3483 | Column3484 | Column3485 | Column3486 | Column3487 | Column3488 | Column3489 | Column3490 | Column3491 | Column3492 | Column3493 | Column3494 | Column3495 | Column3496 | Column3497 | Column3498 | Column3499 | Column3500 | Column3501 | Column3502 | Column3503 | Column3504 | Column3505 | Column3506 | Column3507 | Column3508 | Column3509 | Column3510 | Column3511 | Column3512 | Column3513 | Column3514 | Column3515 | Column3516 | Column3517 | Column3518 | Column3519 | Column3520 | Column3521 | Column3522 | Column3523 | Column3524 | Column3525 | Column3526 | Column3527 | Column3528 | Column3529 | Column3530 | Column3531 | Column3532 | Column3533 | Column3534 | Column3535 | Column3536 | Column3537 | Column3538 | Column3539 | Column3540 | Column3541 | Column3542 | Column3543 | Column3544 | Column3545 | Column3546 | Column3547 | Column3548 | Column3549 | Column3550 | Column3551 | Column3552 | Column3553 | Column3554 | Column3555 | Column3556 | Column3557 | Column3558 | Column3559 | Column3560 | Column3561 | Column3562 | Column3563 | Column3564 | Column3565 | Column3566 | Column3567 | Column3568 | Column3569 | Column3570 | Column3571 | Column3572 | Column3573 | Column3574 | Column3575 | Column3576 | Column3577 | Column3578 | Column3579 | Column3580 | Column3581 | Column3582 | Column3583 | Column3584 | Column3585 | Column3586 | Column3587 | Column3588 | Column3589 | Column3590 | Column3591 | Column3592 | Column3593 | Column3594 | Column3595 | Column3596 | Column3597 | Column3598 | Column3599 | Column3600 | Column3601 | Column3602 | Column3603 | Column3604 | Column3605 | Column3606 | Column3607 | Column3608 | Column3609 | Column3610 | Column3611 | Column3612 | Column3613 | Column3614 | Column3615 | Column3616 | Column3617 | Column3618 | Column3619 | Column3620 | Column3621 | Column3622 | Column3623 | Column3624 | Column3625 | Column3626 | Column3627 | Column3628 | Column3629 | Column3630 | Column3631 | Column3632 | Column3633 | Column3634 | Column3635 | Column3636 | Column3637 | Column3638 | Column3639 | Column3640 | Column3641 | Column3642 | Column3643 | Column3644 | Column3645 | Column3646 | Column3647 | Column3648 | Column3649 | Column3650 | Column3651 | Column3652 | Column3653 | Column3654 | Column3655 | Column3656 | Column3657 | Column3658 | Column3659 | Column3660 | Column3661 | Column3662 | Column3663 | Column3664 | Column3665 | Column3666 | Column3667 | Column3668 | Column3669 | Column3670 | Column3671 | Column3672 | Column3673 | Column3674 | Column3675 | Column3676 | Column3677 | Column3678 | Column3679 | Column3680 | Column3681 | Column3682 | Column3683 | Column3684 | Column3685 | Column3686 | Column3687 | Column3688 | Column3689 | Column3690 | Column3691 | Column3692 | Column3693 | Column3694 | Column3695 | Column3696 | Column3697 | Column3698 | Column3699 | Column3700 | Column3701 | Column3702 | Column3703 | Column3704 | Column3705 | Column3706 | Column3707 | Column3708 | Column3709 | Column3710 | Column3711 | Column3712 | Column3713 | Column3714 | Column3715 | Column3716 | Column3717 | Column3718 | Column3719 | Column3720 | Column3721 | Column3722 | Column3723 | Column3724 | Column3725 | Column3726 | Column3727 | Column3728 | Column3729 | Column3730 | Column3731 | Column3732 | Column3733 | Column3734 | Column3735 | Column3736 | Column3737 | Column3738 | Column3739 | Column3740 | Column3741 | Column3742 | Column3743 | Column3744 | Column3745 | Column3746 | Column3747 | Column3748 | Column3749 | Column3750 | Column3751 | Column3752 | Column3753 | Column3754 | Column3755 | Column3756 | Column3757 | Column3758 | Column3759 | Column3760 | Column3761 | Column3762 | Column3763 | Column3764 | Column3765 | Column3766 | Column3767 | Column3768 | Column3769 | Column3770 | Column3771 | Column3772 | Column3773 | Column3774 | Column3775 | Column3776 | Column3777 | Column3778 | Column3779 | Column3780 | Column3781 | Column3782 | Column3783 | Column3784 | Column3785 | Column3786 | Column3787 | Column3788 | Column3789 | Column3790 | Column3791 | Column3792 | Column3793 | Column3794 | Column3795 | Column3796 | Column3797 | Column3798 | Column3799 | Column3800 | Column3801 | Column3802 | Column3803 | Column3804 | Column3805 | Column3806 | Column3807 | Column3808 | Column3809 | Column3810 | Column3811 | Column3812 | Column3813 | Column3814 | Column3815 | Column3816 | Column3817 | Column3818 | Column3819 | Column3820 | Column3821 | Column3822 | Column3823 | Column3824 | Column3825 | Column3826 | Column3827 | Column3828 | Column3829 | Column3830 | Column3831 | Column3832 | Column3833 | Column3834 | Column3835 | Column3836 | Column3837 | Column3838 | Column3839 | Column3840 | Column3841 | Column3842 | Column3843 | Column3844 | Column3845 | Column3846 | Column3847 | Column3848 | Column3849 | Column3850 | Column3851 | Column3852 | Column3853 | Column3854 | Column3855 | Column3856 | Column3857 | Column3858 | Column3859 | Column3860 | Column3861 | Column3862 | Column3863 | Column3864 | Column3865 | Column3866 | Column3867 | Column3868 | Column3869 | Column3870 | Column3871 | Column3872 | Column3873 | Column3874 | Column3875 | Column3876 | Column3877 | Column3878 | Column3879 | Column3880 | Column3881 | Column3882 | Column3883 | Column3884 | Column3885 | Column3886 | Column3887 | Column3888 | Column3889 | Column3890 | Column3891 | Column3892 | Column3893 | Column3894 | Column3895 | Column3896 | Column3897 | Column3898 | Column3899 | Column3900 | Column3901 | Column3902 | Column3903 | Column3904 | Column3905 | Column3906 | Column3907 | Column3908 | Column3909 | Column3910 | Column3911 | Column3912 | Column3913 | Column3914 | Column3915 | Column3916 | Column3917 | Column3918 | Column3919 | Column3920 | Column3921 | Column3922 | Column3923 | Column3924 | Column3925 | Column3926 | Column3927 | Column3928 | Column3929 | Column3930 | Column3931 | Column3932 | Column3933 | Column3934 | Column3935 | Column3936 | Column3937 | Column3938 | Column3939 | Column3940 | Column3941 | Column3942 | Column3943 | Column3944 | Column3945 | Column3946 | Column3947 | Column3948 | Column3949 | Column3950 | Column3951 | Column3952 | Column3953 | Column3954 | Column3955 | Column3956 | Column3957 | Column3958 | Column3959 | Column3960 | Column3961 | Column3962 | Column3963 | Column3964 | Column3965 | Column3966 | Column3967 | Column3968 | Column3969 | Column3970 | Column3971 | Column3972 | Column3973 | Column3974 | Column3975 | Column3976 | Column3977 | Column3978 | Column3979 | Column3980 | Column3981 | Column3982 | Column3983 | Column3984 | Column3985 | Column3986 | Column3987 | Column3988 | Column3989 | Column3990 | Column3991 | Column3992 | Column3993 | Column3994 | Column3995 | Column3996 | Column3997 | Column3998 | Column3999 | Column4000 | Column4001 | Column4002 | Column4003 | Column4004 | Column4005 | Column4006 | Column4007 | Column4008 | Column4009 | Column4010 | Column4011 | Column4012 | Column4013 | Column4014 | Column4015 | Column4016 | Column4017 | Column4018 | Column4019 | Column4020 | Column4021 | Column4022 | Column4023 | Column4024 | Column4025 | Column4026 | Column4027 | Column4028 | Column4029 | Column4030 | Column4031 | Column4032 | Column4033 | Column4034 | Column4035 | Column4036 | Column4037 | Column4038 | Column4039 | Column4040 | Column4041 | Column4042 | Column4043 | Column4044 | Column4045 | Column4046 | Column4047 | Column4048 | Column4049 | Column4050 | Column4051 | Column4052 | Column4053 | Column4054 | Column4055 | Column4056 | Column4057 | Column4058 | Column4059 | Column4060 | Column4061 | Column4062 | Column4063 | Column4064 | Column4065 | Column4066 | Column4067 | Column4068 | Column4069 | Column4070 | Column4071 | Column4072 | Column4073 | Column4074 | Column4075 | Column4076 | Column4077 | Column4078 | Column4079 | Column4080 | Column4081 | Column4082 | Column4083 | Column4084 | Column4085 | Column4086 | Column4087 | Column4088 | Column4089 | Column4090 | Column4091 | Column4092 | Column4093 | Column4094 | Column4095 | Column4096 | Column4097 | Column4098 | Column4099 | Column4100 | Column4101 | Column4102 | Column4103 | Column4104 | Column4105 | Column4106 | Column4107 | Column4108 | Column4109 | Column4110 | Column4111 | Column4112 | Column4113 | Column4114 | Column4115 | Column4116 | Column4117 | Column4118 | Column4119 | Column4120 | Column4121 | Column4122 | Column4123 | Column4124 | Column4125 | Column4126 | Column4127 | Column4128 | Column4129 | Column4130 | Column4131 | Column4132 | Column4133 | Column4134 | Column4135 | Column4136 | Column4137 | Column4138 | Column4139 | Column4140 | Column4141 | Column4142 | Column4143 | Column4144 | Column4145 | Column4146 | Column4147 | Column4148 | Column4149 | Column4150 | Column4151 | Column4152 | Column4153 | Column4154 | Column4155 | Column4156 | Column4157 | Column4158 | Column4159 | Column4160 | Column4161 | Column4162 | Column4163 | Column4164 | Column4165 | Column4166 | Column4167 | Column4168 | Column4169 | Column4170 | Column4171 | Column4172 | Column4173 | Column4174 | Column4175 | Column4176 | Column4177 | Column4178 | Column4179 | Column4180 | Column4181 | Column4182 | Column4183 | Column4184 | Column4185 | Column4186 | Column4187 | Column4188 | Column4189 | Column4190 | Column4191 | Column4192 | Column4193 | Column4194 | Column4195 | Column4196 | Column4197 | Column4198 | Column4199 | Column4200 | Column4201 | Column4202 | Column4203 | Column4204 | Column4205 | Column4206 | Column4207 | Column4208 | Column4209 | Column4210 | Column4211 | Column4212 | Column4213 | Column4214 | Column4215 | Column4216 | Column4217 | Column4218 | Column4219 | Column4220 | Column4221 | Column4222 | Column4223 | Column4224 | Column4225 | Column4226 | Column4227 | Column4228 | Column4229 | Column4230 | Column4231 | Column4232 | Column4233 | Column4234 | Column4235 | Column4236 | Column4237 | Column4238 | Column4239 | Column4240 | Column4241 | Column4242 | Column4243 | Column4244 | Column4245 | Column4246 | Column4247 | Column4248 | Column4249 | Column4250 | Column4251 | Column4252 | Column4253 | Column4254 | Column4255 | Column4256 | Column4257 | Column4258 | Column4259 | Column4260 | Column4261 | Column4262 | Column4263 | Column4264 | Column4265 | Column4266 | Column4267 | Column4268 | Column4269 | Column4270 | Column4271 | Column4272 | Column4273 | Column4274 | Column4275 | Column4276 | Column4277 | Column4278 | Column4279 | Column4280 | Column4281 | Column4282 | Column4283 | Column4284 | Column4285 | Column4286 | Column4287 | Column4288 | Column4289 | Column4290 | Column4291 | Column4292 | Column4293 | Column4294 | Column4295 | Column4296 | Column4297 | Column4298 | Column4299 | Column4300 | Column4301 | Column4302 | Column4303 | Column4304 | Column4305 | Column4306 | Column4307 | Column4308 | Column4309 | Column4310 | Column4311 | Column4312 | Column4313 | Column4314 | Column4315 | Column4316 | Column4317 | Column4318 | Column4319 | Column4320 | Column4321 | Column4322 | Column4323 | Column4324 | Column4325 | Column4326 | Column4327 | Column4328 | Column4329 | Column4330 | Column4331 | Column4332 | Column4333 | Column4334 | Column4335 | Column4336 | Column4337 | Column4338 | Column4339 | Column4340 | Column4341 | Column4342 | Column4343 | Column4344 | Column4345 | Column4346 | Column4347 | Column4348 | Column4349 | Column4350 | Column4351 | Column4352 | Column4353 | Column4354 | Column4355 | Column4356 | Column4357 | Column4358 | Column4359 | Column4360 | Column4361 | Column4362 | Column4363 | Column4364 | Column4365 | Column4366 | Column4367 | Column4368 | Column4369 | Column4370 | Column4371 | Column4372 | Column4373 | Column4374 | Column4375 | Column4376 | Column4377 | Column4378 | Column4379 | Column4380 | Column4381 | Column4382 | Column4383 | Column4384 | Column4385 | Column4386 | Column4387 | Column4388 | Column4389 | Column4390 | Column4391 | Column4392 | Column4393 | Column4394 | Column4395 | Column4396 | Column4397 | Column4398 | Column4399 | Column4400 | Column4401 | Column4402 | Column4403 | Column4404 | Column4405 | Column4406 | Column4407 | Column4408 | Column4409 | Column4410 | Column4411 | Column4412 | Column4413 | Column4414 | Column4415 | Column4416 | Column4417 | Column4418 | Column4419 | Column4420 | Column4421 | Column4422 | Column4423 | Column4424 | Column4425 | Column4426 | Column4427 | Column4428 | Column4429 | Column4430 | Column4431 | Column4432 | Column4433 | Column4434 | Column4435 | Column4436 | Column4437 | Column4438 | Column4439 | Column4440 | Column4441 | Column4442 | Column4443 | Column4444 | Column4445 | Column4446 | Column4447 | Column4448 | Column4449 | Column4450 | Column4451 | Column4452 | Column4453 | Column4454 | Column4455 | Column4456 | Column4457 | Column4458 | Column4459 | Column4460 | Column4461 | Column4462 | Column4463 | Column4464 | Column4465 | Column4466 | Column4467 | Column4468 | Column4469 | Column4470 | Column4471 | Column4472 | Column4473 | Column4474 | Column4475 | Column4476 | Column4477 | Column4478 | Column4479 | Column4480 | Column4481 | Column4482 | Column4483 | Column4484 | Column4485 | Column4486 | Column4487 | Column4488 | Column4489 | Column4490 | Column4491 | Column4492 | Column4493 | Column4494 | Column4495 | Column4496 | Column4497 | Column4498 | Column4499 | Column4500 | Column4501 | Column4502 | Column4503 | Column4504 | Column4505 | Column4506 | Column4507 | Column4508 | Column4509 | Column4510 | Column4511 | Column4512 | Column4513 | Column4514 | Column4515 | Column4516 | Column4517 | Column4518 | Column4519 | Column4520 | Column4521 | Column4522 | Column4523 | Column4524 | Column4525 | Column4526 | Column4527 | Column4528 | Column4529 | Column4530 | Column4531 | Column4532 | Column4533 | Column4534 | Column4535 | Column4536 | Column4537 | Column4538 | Column4539 | Column4540 | Column4541 | Column4542 | Column4543 | Column4544 | Column4545 | Column4546 | Column4547 | Column4548 | Column4549 | Column4550 | Column4551 | Column4552 | Column4553 | Column4554 | Column4555 | Column4556 | Column4557 | Column4558 | Column4559 | Column4560 | Column4561 | Column4562 | Column4563 | Column4564 | Column4565 | Column4566 | Column4567 | Column4568 | Column4569 | Column4570 | Column4571 | Column4572 | Column4573 | Column4574 | Column4575 | Column4576 | Column4577 | Column4578 | Column4579 | Column4580 | Column4581 | Column4582 | Column4583 | Column4584 | Column4585 | Column4586 | Column4587 | Column4588 | Column4589 | Column4590 | Column4591 | Column4592 | Column4593 | Column4594 | Column4595 | Column4596 | Column4597 | Column4598 | Column4599 | Column4600 | Column4601 | Column4602 | Column4603 | Column4604 | Column4605 | Column4606 | Column4607 | Column4608 | Column4609 | Column4610 | Column4611 | Column4612 | Column4613 | Column4614 | Column4615 | Column4616 | Column4617 | Column4618 | Column4619 | Column4620 | Column4621 | Column4622 | Column4623 | Column4624 | Column4625 | Column4626 | Column4627 | Column4628 | Column4629 | Column4630 | Column4631 | Column4632 | Column4633 | Column4634 | Column4635 | Column4636 | Column4637 | Column4638 | Column4639 | Column4640 | Column4641 | Column4642 | Column4643 | Column4644 | Column4645 | Column4646 | Column4647 | Column4648 | Column4649 | Column4650 | Column4651 | Column4652 | Column4653 | Column4654 | Column4655 | Column4656 | Column4657 | Column4658 | Column4659 | Column4660 | Column4661 | Column4662 | Column4663 | Column4664 | Column4665 | Column4666 | Column4667 | Column4668 | Column4669 | Column4670 | Column4671 | Column4672 | Column4673 | Column4674 | Column4675 | Column4676 | Column4677 | Column4678 | Column4679 | Column4680 | Column4681 | Column4682 | Column4683 | Column4684 | Column4685 | Column4686 | Column4687 | Column4688 | Column4689 | Column4690 | Column4691 | Column4692 | Column4693 | Column4694 | Column4695 | Column4696 | Column4697 | Column4698 | Column4699 | Column4700 | Column4701 | Column4702 | Column4703 | Column4704 | Column4705 | Column4706 | Column4707 | Column4708 | Column4709 | Column4710 | Column4711 | Column4712 | Column4713 | Column4714 | Column4715 | Column4716 | Column4717 | Column4718 | Column4719 | Column4720 | Column4721 | Column4722 | Column4723 | Column4724 | Column4725 | Column4726 | Column4727 | Column4728 | Column4729 | Column4730 | Column4731 | Column4732 | Column4733 | Column4734 | Column4735 | Column4736 | Column4737 | Column4738 | Column4739 | Column4740 | Column4741 | Column4742 | Column4743 | Column4744 | Column4745 | Column4746 | Column4747 | Column4748 | Column4749 | Column4750 | Column4751 | Column4752 | Column4753 | Column4754 | Column4755 | Column4756 | Column4757 | Column4758 | Column4759 | Column4760 | Column4761 | Column4762 | Column4763 | Column4764 | Column4765 | Column4766 | Column4767 | Column4768 | Column4769 | Column4770 | Column4771 | Column4772 | Column4773 | Column4774 | Column4775 | Column4776 | Column4777 | Column4778 | Column4779 | Column4780 | Column4781 | Column4782 | Column4783 | Column4784 | Column4785 | Column4786 | Column4787 | Column4788 | Column4789 | Column4790 | Column4791 | Column4792 | Column4793 | Column4794 | Column4795 | Column4796 | Column4797 | Column4798 | Column4799 | Column4800 | Column4801 | Column4802 | Column4803 | Column4804 | Column4805 | Column4806 | Column4807 | Column4808 | Column4809 | Column4810 | Column4811 | Column4812 | Column4813 | Column4814 | Column4815 | Column4816 | Column4817 | Column4818 | Column4819 | Column4820 | Column4821 | Column4822 | Column4823 | Column4824 | Column4825 | Column4826 | Column4827 | Column4828 | Column4829 | Column4830 | Column4831 | Column4832 | Column4833 | Column4834 | Column4835 | Column4836 | Column4837 | Column4838 | Column4839 | Column4840 | Column4841 | Column4842 | Column4843 | Column4844 | Column4845 | Column4846 | Column4847 | Column4848 | Column4849 | Column4850 | Column4851 | Column4852 | Column4853 | Column4854 | Column4855 | Column4856 | Column4857 | Column4858 | Column4859 | Column4860 | Column4861 | Column4862 | Column4863 | Column4864 | Column4865 | Column4866 | Column4867 | Column4868 | Column4869 | Column4870 | Column4871 | Column4872 | Column4873 | Column4874 | Column4875 | Column4876 | Column4877 | Column4878 | Column4879 | Column4880 | Column4881 | Column4882 | Column4883 | Column4884 | Column4885 | Column4886 | Column4887 | Column4888 | Column4889 | Column4890 | Column4891 | Column4892 | Column4893 | Column4894 | Column4895 | Column4896 | Column4897 | Column4898 | Column4899 | Column4900 | Column4901 | Column4902 | Column4903 | Column4904 | Column4905 | Column4906 | Column4907 | Column4908 | Column4909 | Column4910 | Column4911 | Column4912 | Column4913 | Column4914 | Column4915 | Column4916 | Column4917 | Column4918 | Column4919 | Column4920 | Column4921 | Column4922 | Column4923 | Column4924 | Column4925 | Column4926 | Column4927 | Column4928 | Column4929 | Column4930 | Column4931 | Column4932 | Column4933 | Column4934 | Column4935 | Column4936 | Column4937 | Column4938 | Column4939 | Column4940 | Column4941 | Column4942 | Column4943 | Column4944 | Column4945 | Column4946 | Column4947 | Column4948 | Column4949 | Column4950 | Column4951 | Column4952 | Column4953 | Column4954 | Column4955 | Column4956 | Column4957 | Column4958 | Column4959 | Column4960 | Column4961 | Column4962 | Column4963 | Column4964 | Column4965 | Column4966 | Column4967 | Column4968 | Column4969 | Column4970 | Column4971 | Column4972 | Column4973 | Column4974 | Column4975 | Column4976 | Column4977 | Column4978 | Column4979 | Column4980 | Column4981 | Column4982 | Column4983 | Column4984 | Column4985 | Column4986 | Column4987 | Column4988 | Column4989 | Column4990 | Column4991 | Column4992 | Column4993 | Column4994 | Column4995 | Column4996 | Column4997 | Column4998 | Column4999 | Column5000 | Column5001 | Column5002 | Column5003 | Column5004 | Column5005 | Column5006 | Column5007 | Column5008 | Column5009 | Column5010 | Column5011 | Column5012 | Column5013 | Column5014 | Column5015 | Column5016 | Column5017 | Column5018 | Column5019 | Column5020 | Column5021 | Column5022 | Column5023 | Column5024 | Column5025 | Column5026 | Column5027 | Column5028 | Column5029 | Column5030 | Column5031 | Column5032 | Column5033 | Column5034 | Column5035 | Column5036 | Column5037 | Column5038 | Column5039 | Column5040 | Column5041 | Column5042 | Column5043 | Column5044 | Column5045 | Column5046 | Column5047 | Column5048 | Column5049 | Column5050 | Column5051 | Column5052 | Column5053 | Column5054 | Column5055 | Column5056 | Column5057 | Column5058 | Column5059 | Column5060 | Column5061 | Column5062 | Column5063 | Column5064 | Column5065 | Column5066 | Column5067 | Column5068 | Column5069 | Column5070 | Column5071 | Column5072 | Column5073 | Column5074 | Column5075 | Column5076 | Column5077 | Column5078 | Column5079 | Column5080 | Column5081 | Column5082 | Column5083 | Column5084 | Column5085 | Column5086 | Column5087 | Column5088 | Column5089 | Column5090 | Column5091 | Column5092 | Column5093 | Column5094 | Column5095 | Column5096 | Column5097 | Column5098 | Column5099 | Column5100 | Column5101 | Column5102 | Column5103 | Column5104 | Column5105 | Column5106 | Column5107 | Column5108 | Column5109 | Column5110 | Column5111 | Column5112 | Column5113 | Column5114 | Column5115 | Column5116 | Column5117 | Column5118 | Column5119 | Column5120 | Column5121 | Column5122 | Column5123 | Column5124 | Column5125 | Column5126 | Column5127 | Column5128 | Column5129 | Column5130 | Column5131 | Column5132 | Column5133 | Column5134 | Column5135 | Column5136 | Column5137 | Column5138 | Column5139 | Column5140 | Column5141 | Column5142 | Column5143 | Column5144 | Column5145 | Column5146 | Column5147 | Column5148 | Column5149 | Column5150 | Column5151 | Column5152 | Column5153 | Column5154 | Column5155 | Column5156 | Column5157 | Column5158 | Column5159 | Column5160 | Column5161 | Column5162 | Column5163 | Column5164 | Column5165 | Column5166 | Column5167 | Column5168 | Column5169 | Column5170 | Column5171 | Column5172 | Column5173 | Column5174 | Column5175 | Column5176 | Column5177 | Column5178 | Column5179 | Column5180 | Column5181 | Column5182 | Column5183 | Column5184 | Column5185 | Column5186 | Column5187 | Column5188 | Column5189 | Column5190 | Column5191 | Column5192 | Column5193 | Column5194 | Column5195 | Column5196 | Column5197 | Column5198 | Column5199 | Column5200 | Column5201 | Column5202 | Column5203 | Column5204 | Column5205 | Column5206 | Column5207 | Column5208 | Column5209 | Column5210 | Column5211 | Column5212 | Column5213 | Column5214 | Column5215 | Column5216 | Column5217 | Column5218 | Column5219 | Column5220 | Column5221 | Column5222 | Column5223 | Column5224 | Column5225 | Column5226 | Column5227 | Column5228 | Column5229 | Column5230 | Column5231 | Column5232 | Column5233 | Column5234 | Column5235 | Column5236 | Column5237 | Column5238 | Column5239 | Column5240 | Column5241 | Column5242 | Column5243 | Column5244 | Column5245 | Column5246 | Column5247 | Column5248 | Column5249 | Column5250 | Column5251 | Column5252 | Column5253 | Column5254 | Column5255 | Column5256 | Column5257 | Column5258 | Column5259 | Column5260 | Column5261 | Column5262 | Column5263 | Column5264 | Column5265 | Column5266 | Column5267 | Column5268 | Column5269 | Column5270 | Column5271 | Column5272 | Column5273 | Column5274 | Column5275 | Column5276 | Column5277 | Column5278 | Column5279 | Column5280 | Column5281 | Column5282 | Column5283 | Column5284 | Column5285 | Column5286 | Column5287 | Column5288 | Column5289 | Column5290 | Column5291 | Column5292 | Column5293 | Column5294 | Column5295 | Column5296 | Column5297 | Column5298 | Column5299 | Column5300 | Column5301 | Column5302 | Column5303 | Column5304 | Column5305 | Column5306 | Column5307 | Column5308 | Column5309 | Column5310 | Column5311 | Column5312 | Column5313 | Column5314 | Column5315 | Column5316 | Column5317 | Column5318 | Column5319 | Column5320 | Column5321 | Column5322 | Column5323 | Column5324 | Column5325 | Column5326 | Column5327 | Column5328 | Column5329 | Column5330 | Column5331 | Column5332 | Column5333 | Column5334 | Column5335 | Column5336 | Column5337 | Column5338 | Column5339 | Column5340 | Column5341 | Column5342 | Column5343 | Column5344 | Column5345 | Column5346 | Column5347 | Column5348 | Column5349 | Column5350 | Column5351 | Column5352 | Column5353 | Column5354 | Column5355 | Column5356 | Column5357 | Column5358 | Column5359 | Column5360 | Column5361 | Column5362 | Column5363 | Column5364 | Column5365 | Column5366 | Column5367 | Column5368 | Column5369 | Column5370 | Column5371 | Column5372 | Column5373 | Column5374 | Column5375 | Column5376 | Column5377 | Column5378 | Column5379 | Column5380 | Column5381 | Column5382 | Column5383 | Column5384 | Column5385 | Column5386 | Column5387 | Column5388 | Column5389 | Column5390 | Column5391 | Column5392 | Column5393 | Column5394 | Column5395 | Column5396 | Column5397 | Column5398 | Column5399 | Column5400 | Column5401 | Column5402 | Column5403 | Column5404 | Column5405 | Column5406 | Column5407 | Column5408 | Column5409 | Column5410 | Column5411 | Column5412 | Column5413 | Column5414 | Column5415 | Column5416 | Column5417 | Column5418 | Column5419 | Column5420 | Column5421 | Column5422 | Column5423 | Column5424 | Column5425 | Column5426 | Column5427 | Column5428 | Column5429 | Column5430 | Column5431 | Column5432 | Column5433 | Column5434 | Column5435 | Column5436 | Column5437 | Column5438 | Column5439 | Column5440 | Column5441 | Column5442 | Column5443 | Column5444 | Column5445 | Column5446 | Column5447 | Column5448 | Column5449 | Column5450 | Column5451 | Column5452 | Column5453 | Column5454 | Column5455 | Column5456 | Column5457 | Column5458 | Column5459 | Column5460 | Column5461 | Column5462 | Column5463 | Column5464 | Column5465 | Column5466 | Column5467 | Column5468 | Column5469 | Column5470 | Column5471 | Column5472 | Column5473 | Column5474 | Column5475 | Column5476 | Column5477 | Column5478 | Column5479 | Column5480 | Column5481 | Column5482 | Column5483 | Column5484 | Column5485 | Column5486 | Column5487 | Column5488 | Column5489 | Column5490 | Column5491 | Column5492 | Column5493 | Column5494 | Column5495 | Column5496 | Column5497 | Column5498 | Column5499 | Column5500 | Column5501 | Column5502 | Column5503 | Column5504 | Column5505 | Column5506 | Column5507 | Column5508 | Column5509 | Column5510 | Column5511 | Column5512 | Column5513 | Column5514 | Column5515 | Column5516 | Column5517 | Column5518 | Column5519 | Column5520 | Column5521 | Column5522 | Column5523 | Column5524 | Column5525 | Column5526 | Column5527 | Column5528 | Column5529 | Column5530 | Column5531 | Column5532 | Column5533 | Column5534 | Column5535 | Column5536 | Column5537 | Column5538 | Column5539 | Column5540 | Column5541 | Column5542 | Column5543 | Column5544 | Column5545 | Column5546 | Column5547 | Column5548 | Column5549 | Column5550 | Column5551 | Column5552 | Column5553 | Column5554 | Column5555 | Column5556 | Column5557 | Column5558 | Column5559 | Column5560 | Column5561 | Column5562 | Column5563 | Column5564 | Column5565 | Column5566 | Column5567 | Column5568 | Column5569 | Column5570 | Column5571 | Column5572 | Column5573 | Column5574 | Column5575 | Column5576 | Column5577 | Column5578 | Column5579 | Column5580 | Column5581 | Column5582 | Column5583 | Column5584 | Column5585 | Column5586 | Column5587 | Column5588 | Column5589 | Column5590 | Column5591 | Column5592 | Column5593 | Column5594 | Column5595 | Column5596 | Column5597 | Column5598 | Column5599 | Column5600 | Column5601 | Column5602 | Column5603 | Column5604 | Column5605 | Column5606 | Column5607 | Column5608 | Column5609 | Column5610 | Column5611 | Column5612 | Column5613 | Column5614 | Column5615 | Column5616 | Column5617 | Column5618 | Column5619 | Column5620 | Column5621 | Column5622 | Column5623 | Column5624 | Column5625 | Column5626 | Column5627 | Column5628 | Column5629 | Column5630 | Column5631 | Column5632 | Column5633 | Column5634 | Column5635 | Column5636 | Column5637 | Column5638 | Column5639 | Column5640 | Column5641 | Column5642 | Column5643 | Column5644 | Column5645 | Column5646 | Column5647 | Column5648 | Column5649 | Column5650 | Column5651 | Column5652 | Column5653 | Column5654 | Column5655 | Column5656 | Column5657 | Column5658 | Column5659 | Column5660 | Column5661 | Column5662 | Column5663 | Column5664 | Column5665 | Column5666 | Column5667 | Column5668 | Column5669 | Column5670 | Column5671 | Column5672 | Column5673 | Column5674 | Column5675 | Column5676 | Column5677 | Column5678 | Column5679 | Column5680 | Column5681 | Column5682 | Column5683 | Column5684 | Column5685 | Column5686 | Column5687 | Column5688 | Column5689 | Column5690 | Column5691 | Column5692 | Column5693 | Column5694 | Column5695 | Column5696 | Column5697 | Column5698 | Column5699 | Column5700 | Column5701 | Column5702 | Column5703 | Column5704 | Column5705 | Column5706 | Column5707 | Column5708 | Column5709 | Column5710 | Column5711 | Column5712 | Column5713 | Column5714 | Column5715 | Column5716 | Column5717 | Column5718 | Column5719 | Column5720 | Column5721 | Column5722 | Column5723 | Column5724 | Column5725 | Column5726 | Column5727 | Column5728 | Column5729 | Column5730 | Column5731 | Column5732 | Column5733 | Column5734 | Column5735 | Column5736 | Column5737 | Column5738 | Column5739 | Column5740 | Column5741 | Column5742 | Column5743 | Column5744 | Column5745 | Column5746 | Column5747 | Column5748 | Column5749 | Column5750 | Column5751 | Column5752 | Column5753 | Column5754 | Column5755 | Column5756 | Column5757 | Column5758 | Column5759 | Column5760 | Column5761 | Column5762 | Column5763 | Column5764 | Column5765 | Column5766 | Column5767 | Column5768 | Column5769 | Column5770 | Column5771 | Column5772 | Column5773 | Column5774 | Column5775 | Column5776 | Column5777 | Column5778 | Column5779 | Column5780 | Column5781 | Column5782 | Column5783 | Column5784 | Column5785 | Column5786 | Column5787 | Column5788 | Column5789 | Column5790 | Column5791 | Column5792 | Column5793 | Column5794 | Column5795 | Column5796 | Column5797 | Column5798 | Column5799 | Column5800 | Column5801 | Column5802 | Column5803 | Column5804 | Column5805 | Column5806 | Column5807 | Column5808 | Column5809 | Column5810 | Column5811 | Column5812 | Column5813 | Column5814 | Column5815 | Column5816 | Column5817 | Column5818 | Column5819 | Column5820 | Column5821 | Column5822 | Column5823 | Column5824 | Column5825 | Column5826 | Column5827 | Column5828 | Column5829 | Column5830 | Column5831 | Column5832 | Column5833 | Column5834 | Column5835 | Column5836 | Column5837 | Column5838 | Column5839 | Column5840 | Column5841 | Column5842 | Column5843 | Column5844 | Column5845 | Column5846 | Column5847 | Column5848 | Column5849 | Column5850 | Column5851 | Column5852 | Column5853 | Column5854 | Column5855 | Column5856 | Column5857 | Column5858 | Column5859 | Column5860 | Column5861 | Column5862 | Column5863 | Column5864 | Column5865 | Column5866 | Column5867 | Column5868 | Column5869 | Column5870 | Column5871 | Column5872 | Column5873 | Column5874 | Column5875 | Column5876 | Column5877 | Column5878 | Column5879 | Column5880 | Column5881 | Column5882 | Column5883 | Column5884 | Column5885 | Column5886 | Column5887 | Column5888 | Column5889 | Column5890 | Column5891 | Column5892 | Column5893 | Column5894 | Column5895 | Column5896 | Column5897 | Column5898 | Column5899 | Column5900 | Column5901 | Column5902 | Column5903 | Column5904 | Column5905 | Column5906 | Column5907 | Column5908 | Column5909 | Column5910 | Column5911 | Column5912 | Column5913 | Column5914 | Column5915 | Column5916 | Column5917 | Column5918 | Column5919 | Column5920 | Column5921 | Column5922 | Column5923 | Column5924 | Column5925 | Column5926 | Column5927 | Column5928 | Column5929 | Column5930 | Column5931 | Column5932 | Column5933 | Column5934 | Column5935 | Column5936 | Column5937 | Column5938 | Column5939 | Column5940 | Column5941 | Column5942 | Column5943 | Column5944 | Column5945 | Column5946 | Column5947 | Column5948 | Column5949 | Column5950 | Column5951 | Column5952 | Column5953 | Column5954 | Column5955 | Column5956 | Column5957 | Column5958 | Column5959 | Column5960 | Column5961 | Column5962 | Column5963 | Column5964 | Column5965 | Column5966 | Column5967 | Column5968 | Column5969 | Column5970 | Column5971 | Column5972 | Column5973 | Column5974 | Column5975 | Column5976 | Column5977 | Column5978 | Column5979 | Column5980 | Column5981 | Column5982 | Column5983 | Column5984 | Column5985 | Column5986 | Column5987 | Column5988 | Column5989 | Column5990 | Column5991 | Column5992 | Column5993 | Column5994 | Column5995 | Column5996 | Column5997 | Column5998 | Column5999 | Column6000 | Column6001 | Column6002 | Column6003 | Column6004 | Column6005 | Column6006 | Column6007 | Column6008 | Column6009 | Column6010 | Column6011 | Column6012 | Column6013 | Column6014 | Column6015 | Column6016 | Column6017 | Column6018 | Column6019 | Column6020 | Column6021 | Column6022 | Column6023 | Column6024 | Column6025 | Column6026 | Column6027 | Column6028 | Column6029 | Column6030 | Column6031 | Column6032 | Column6033 | Column6034 | Column6035 | Column6036 | Column6037 | Column6038 | Column6039 | Column6040 | Column6041 | Column6042 | Column6043 | Column6044 | Column6045 | Column6046 | Column6047 | Column6048 | Column6049 | Column6050 | Column6051 | Column6052 | Column6053 | Column6054 | Column6055 | Column6056 | Column6057 | Column6058 | Column6059 | Column6060 | Column6061 | Column6062 | Column6063 | Column6064 | Column6065 | Column6066 | Column6067 | Column6068 | Column6069 | Column6070 | Column6071 | Column6072 | Column6073 | Column6074 | Column6075 | Column6076 | Column6077 | Column6078 | Column6079 | Column6080 | Column6081 | Column6082 | Column6083 | Column6084 | Column6085 | Column6086 | Column6087 | Column6088 | Column6089 | Column6090 | Column6091 | Column6092 | Column6093 | Column6094 | Column6095 | Column6096 | Column6097 | Column6098 | Column6099 | Column6100 | Column6101 | Column6102 | Column6103 | Column6104 | Column6105 | Column6106 | Column6107 | Column6108 | Column6109 | Column6110 | Column6111 | Column6112 | Column6113 | Column6114 | Column6115 | Column6116 | Column6117 | Column6118 | Column6119 | Column6120 | Column6121 | Column6122 | Column6123 | Column6124 | Column6125 | Column6126 | Column6127 | Column6128 | Column6129 | Column6130 | Column6131 | Column6132 | Column6133 | Column6134 | Column6135 | Column6136 | Column6137 | Column6138 | Column6139 | Column6140 | Column6141 | Column6142 | Column6143 | Column6144 | Column6145 | Column6146 | Column6147 | Column6148 | Column6149 | Column6150 | Column6151 | Column6152 | Column6153 | Column6154 | Column6155 | Column6156 | Column6157 | Column6158 | Column6159 | Column6160 | Column6161 | Column6162 | Column6163 | Column6164 | Column6165 | Column6166 | Column6167 | Column6168 | Column6169 | Column6170 | Column6171 | Column6172 | Column6173 | Column6174 | Column6175 | Column6176 | Column6177 | Column6178 | Column6179 | Column6180 | Column6181 | Column6182 | Column6183 | Column6184 | Column6185 | Column6186 | Column6187 | Column6188 | Column6189 | Column6190 | Column6191 | Column6192 | Column6193 | Column6194 | Column6195 | Column6196 | Column6197 | Column6198 | Column6199 | Column6200 | Column6201 | Column6202 | Column6203 | Column6204 | Column6205 | Column6206 | Column6207 | Column6208 | Column6209 | Column6210 | Column6211 | Column6212 | Column6213 | Column6214 | Column6215 | Column6216 | Column6217 | Column6218 | Column6219 | Column6220 | Column6221 | Column6222 | Column6223 | Column6224 | Column6225 | Column6226 | Column6227 | Column6228 | Column6229 | Column6230 | Column6231 | Column6232 | Column6233 | Column6234 | Column6235 | Column6236 | Column6237 | Column6238 | Column6239 | Column6240 | Column6241 | Column6242 | Column6243 | Column6244 | Column6245 | Column6246 | Column6247 | Column6248 | Column6249 | Column6250 | Column6251 | Column6252 | Column6253 | Column6254 | Column6255 | Column6256 | Column6257 | Column6258 | Column6259 | Column6260 | Column6261 | Column6262 | Column6263 | Column6264 | Column6265 | Column6266 | Column6267 | Column6268 | Column6269 | Column6270 | Column6271 | Column6272 | Column6273 | Column6274 | Column6275 | Column6276 | Column6277 | Column6278 | Column6279 | Column6280 | Column6281 | Column6282 | Column6283 | Column6284 | Column6285 | Column6286 | Column6287 | Column6288 | Column6289 | Column6290 | Column6291 | Column6292 | Column6293 | Column6294 | Column6295 | Column6296 | Column6297 | Column6298 | Column6299 | Column6300 | Column6301 | Column6302 | Column6303 | Column6304 | Column6305 | Column6306 | Column6307 | Column6308 | Column6309 | Column6310 | Column6311 | Column6312 | Column6313 | Column6314 | Column6315 | Column6316 | Column6317 | Column6318 | Column6319 | Column6320 | Column6321 | Column6322 | Column6323 | Column6324 | Column6325 | Column6326 | Column6327 | Column6328 | Column6329 | Column6330 | Column6331 | Column6332 | Column6333 | Column6334 | Column6335 | Column6336 | Column6337 | Column6338 | Column6339 | Column6340 | Column6341 | Column6342 | Column6343 | Column6344 | Column6345 | Column6346 | Column6347 | Column6348 | Column6349 | Column6350 | Column6351 | Column6352 | Column6353 | Column6354 | Column6355 | Column6356 | Column6357 | Column6358 | Column6359 | Column6360 | Column6361 | Column6362 | Column6363 | Column6364 | Column6365 | Column6366 | Column6367 | Column6368 | Column6369 | Column6370 | Column6371 | Column6372 | Column6373 | Column6374 | Column6375 | Column6376 | Column6377 | Column6378 | Column6379 | Column6380 | Column6381 | Column6382 | Column6383 | Column6384 | Column6385 | Column6386 | Column6387 | Column6388 | Column6389 | Column6390 | Column6391 | Column6392 | Column6393 | Column6394 | Column6395 | Column6396 | Column6397 | Column6398 | Column6399 | Column6400 | Column6401 | Column6402 | Column6403 | Column6404 | Column6405 | Column6406 | Column6407 | Column6408 | Column6409 | Column6410 | Column6411 | Column6412 | Column6413 | Column6414 | Column6415 | Column6416 | Column6417 | Column6418 | Column6419 | Column6420 | Column6421 | Column6422 | Column6423 | Column6424 | Column6425 | Column6426 | Column6427 | Column6428 | Column6429 | Column6430 | Column6431 | Column6432 | Column6433 | Column6434 | Column6435 | Column6436 | Column6437 | Column6438 | Column6439 | Column6440 | Column6441 | Column6442 | Column6443 | Column6444 | Column6445 | Column6446 | Column6447 | Column6448 | Column6449 | Column6450 | Column6451 | Column6452 | Column6453 | Column6454 | Column6455 | Column6456 | Column6457 | Column6458 | Column6459 | Column6460 | Column6461 | Column6462 | Column6463 | Column6464 | Column6465 | Column6466 | Column6467 | Column6468 | Column6469 | Column6470 | Column6471 | Column6472 | Column6473 | Column6474 | Column6475 | Column6476 | Column6477 | Column6478 | Column6479 | Column6480 | Column6481 | Column6482 | Column6483 | Column6484 | Column6485 | Column6486 | Column6487 | Column6488 | Column6489 | Column6490 | Column6491 | Column6492 | Column6493 | Column6494 | Column6495 | Column6496 | Column6497 | Column6498 | Column6499 | Column6500 | Column6501 | Column6502 | Column6503 | Column6504 | Column6505 | Column6506 | Column6507 | Column6508 | Column6509 | Column6510 | Column6511 | Column6512 | Column6513 | Column6514 | Column6515 | Column6516 | Column6517 | Column6518 | Column6519 | Column6520 | Column6521 | Column6522 | Column6523 | Column6524 | Column6525 | Column6526 | Column6527 | Column6528 | Column6529 | Column6530 | Column6531 | Column6532 | Column6533 | Column6534 | Column6535 | Column6536 | Column6537 | Column6538 | Column6539 | Column6540 | Column6541 | Column6542 | Column6543 | Column6544 | Column6545 | Column6546 | Column6547 | Column6548 | Column6549 | Column6550 | Column6551 | Column6552 | Column6553 | Column6554 | Column6555 | Column6556 | Column6557 | Column6558 | Column6559 | Column6560 | Column6561 | Column6562 | Column6563 | Column6564 | Column6565 | Column6566 | Column6567 | Column6568 | Column6569 | Column6570 | Column6571 | Column6572 | Column6573 | Column6574 | Column6575 | Column6576 | Column6577 | Column6578 | Column6579 | Column6580 | Column6581 | Column6582 | Column6583 | Column6584 | Column6585 | Column6586 | Column6587 | Column6588 | Column6589 | Column6590 | Column6591 | Column6592 | Column6593 | Column6594 | Column6595 | Column6596 | Column6597 | Column6598 | Column6599 | Column6600 | Column6601 | Column6602 | Column6603 | Column6604 | Column6605 | Column6606 | Column6607 | Column6608 | Column6609 | Column6610 | Column6611 | Column6612 | Column6613 | Column6614 | Column6615 | Column6616 | Column6617 | Column6618 | Column6619 | Column6620 | Column6621 | Column6622 | Column6623 | Column6624 | Column6625 | Column6626 | Column6627 | Column6628 | Column6629 | Column6630 | Column6631 | Column6632 | Column6633 | Column6634 | Column6635 | Column6636 | Column6637 | Column6638 | Column6639 | Column6640 | Column6641 | Column6642 | Column6643 | Column6644 | Column6645 | Column6646 | Column6647 | Column6648 | Column6649 | Column6650 | Column6651 | Column6652 | Column6653 | Column6654 | Column6655 | Column6656 | Column6657 | Column6658 | Column6659 | Column6660 | Column6661 | Column6662 | Column6663 | Column6664 | Column6665 | Column6666 | Column6667 | Column6668 | Column6669 | Column6670 | Column6671 | Column6672 | Column6673 | Column6674 | Column6675 | Column6676 | Column6677 | Column6678 | Column6679 | Column6680 | Column6681 | Column6682 | Column6683 | Column6684 | Column6685 | Column6686 | Column6687 | Column6688 | Column6689 | Column6690 | Column6691 | Column6692 | Column6693 | Column6694 | Column6695 | Column6696 | Column6697 | Column6698 | Column6699 | Column6700 | Column6701 | Column6702 | Column6703 | Column6704 | Column6705 | Column6706 | Column6707 | Column6708 | Column6709 | Column6710 | Column6711 | Column6712 | Column6713 | Column6714 | Column6715 | Column6716 | Column6717 | Column6718 | Column6719 | Column6720 | Column6721 | Column6722 | Column6723 | Column6724 | Column6725 | Column6726 | Column6727 | Column6728 | Column6729 | Column6730 | Column6731 | Column6732 | Column6733 | Column6734 | Column6735 | Column6736 | Column6737 | Column6738 | Column6739 | Column6740 | Column6741 | Column6742 | Column6743 | Column6744 | Column6745 | Column6746 | Column6747 | Column6748 | Column6749 | Column6750 | Column6751 | Column6752 | Column6753 | Column6754 | Column6755 | Column6756 | Column6757 | Column6758 | Column6759 | Column6760 | Column6761 | Column6762 | Column6763 | Column6764 | Column6765 | Column6766 | Column6767 | Column6768 | Column6769 | Column6770 | Column6771 | Column6772 | Column6773 | Column6774 | Column6775 | Column6776 | Column6777 | Column6778 | Column6779 | Column6780 | Column6781 | Column6782 | Column6783 | Column6784 | Column6785 | Column6786 | Column6787 | Column6788 | Column6789 | Column6790 | Column6791 | Column6792 | Column6793 | Column6794 | Column6795 | Column6796 | Column6797 | Column6798 | Column6799 | Column6800 | Column6801 | Column6802 | Column6803 | Column6804 | Column6805 | Column6806 | Column6807 | Column6808 | Column6809 | Column6810 | Column6811 | Column6812 | Column6813 | Column6814 | Column6815 | Column6816 | Column6817 | Column6818 | Column6819 | Column6820 | Column6821 | Column6822 | Column6823 | Column6824 | Column6825 | Column6826 | Column6827 | Column6828 | Column6829 | Column6830 | Column6831 | Column6832 | Column6833 | Column6834 | Column6835 | Column6836 | Column6837 | Column6838 | Column6839 | Column6840 | Column6841 | Column6842 | Column6843 | Column6844 | Column6845 | Column6846 | Column6847 | Column6848 | Column6849 | Column6850 | Column6851 | Column6852 | Column6853 | Column6854 | Column6855 | Column6856 | Column6857 | Column6858 | Column6859 | Column6860 | Column6861 | Column6862 | Column6863 | Column6864 | Column6865 | Column6866 | Column6867 | Column6868 | Column6869 | Column6870 | Column6871 | Column6872 | Column6873 | Column6874 | Column6875 | Column6876 | Column6877 | Column6878 | Column6879 | Column6880 | Column6881 | Column6882 | Column6883 | Column6884 | Column6885 | Column6886 | Column6887 | Column6888 | Column6889 | Column6890 | Column6891 | Column6892 | Column6893 | Column6894 | Column6895 | Column6896 | Column6897 | Column6898 | Column6899 | Column6900 | Column6901 | Column6902 | Column6903 | Column6904 | Column6905 | Column6906 | Column6907 | Column6908 | Column6909 | Column6910 | Column6911 | Column6912 | Column6913 | Column6914 | Column6915 | Column6916 | Column6917 | Column6918 | Column6919 | Column6920 | Column6921 | Column6922 | Column6923 | Column6924 | Column6925 | Column6926 | Column6927 | Column6928 | Column6929 | Column6930 | Column6931 | Column6932 | Column6933 | Column6934 | Column6935 | Column6936 | Column6937 | Column6938 | Column6939 | Column6940 | Column6941 | Column6942 | Column6943 | Column6944 | Column6945 | Column6946 | Column6947 | Column6948 | Column6949 | Column6950 | Column6951 | Column6952 | Column6953 | Column6954 | Column6955 | Column6956 | Column6957 | Column6958 | Column6959 | Column6960 | Column6961 | Column6962 | Column6963 | Column6964 | Column6965 | Column6966 | Column6967 | Column6968 | Column6969 | Column6970 | Column6971 | Column6972 | Column6973 | Column6974 | Column6975 | Column6976 | Column6977 | Column6978 | Column6979 | Column6980 | Column6981 | Column6982 | Column6983 | Column6984 | Column6985 | Column6986 | Column6987 | Column6988 | Column6989 | Column6990 | Column6991 | Column6992 | Column6993 | Column6994 | Column6995 | Column6996 | Column6997 | Column6998 | Column6999 | Column7000 | Column7001 | Column7002 | Column7003 | Column7004 | Column7005 | Column7006 | Column7007 | Column7008 | Column7009 | Column7010 | Column7011 | Column7012 | Column7013 | Column7014 | Column7015 | Column7016 | Column7017 | Column7018 | Column7019 | Column7020 | Column7021 | Column7022 | Column7023 | Column7024 | Column7025 | Column7026 | Column7027 | Column7028 | Column7029 | Column7030 | Column7031 | Column7032 | Column7033 | Column7034 | Column7035 | Column7036 | Column7037 | Column7038 | Column7039 | Column7040 | Column7041 | Column7042 | Column7043 | Column7044 | Column7045 | Column7046 | Column7047 | Column7048 | Column7049 | Column7050 | Column7051 | Column7052 | Column7053 | Column7054 | Column7055 | Column7056 | Column7057 | Column7058 | Column7059 | Column7060 | Column7061 | Column7062 | Column7063 | Column7064 | Column7065 | Column7066 | Column7067 | Column7068 | Column7069 | Column7070 | Column7071 | Column7072 | Column7073 | Column7074 | Column7075 | Column7076 | Column7077 | Column7078 | Column7079 | Column7080 | Column7081 | Column7082 | Column7083 | Column7084 | Column7085 | Column7086 | Column7087 | Column7088 | Column7089 | Column7090 | Column7091 | Column7092 | Column7093 | Column7094 | Column7095 | Column7096 | Column7097 | Column7098 | Column7099 | Column7100 | Column7101 | Column7102 | Column7103 | Column7104 | Column7105 | Column7106 | Column7107 | Column7108 | Column7109 | Column7110 | Column7111 | Column7112 | Column7113 | Column7114 | Column7115 | Column7116 | Column7117 | Column7118 | Column7119 | Column7120 | Column7121 | Column7122 | Column7123 | Column7124 | Column7125 | Column7126 | Column7127 | Column7128 | Column7129 | Column7130 | Column7131 | Column7132 | Column7133 | Column7134 | Column7135 | Column7136 | Column7137 | Column7138 | Column7139 | Column7140 | Column7141 | Column7142 | Column7143 | Column7144 | Column7145 | Column7146 | Column7147 | Column7148 | Column7149 | Column7150 | Column7151 | Column7152 | Column7153 | Column7154 | Column7155 | Column7156 | Column7157 | Column7158 | Column7159 | Column7160 | Column7161 | Column7162 | Column7163 | Column7164 | Column7165 | Column7166 | Column7167 | Column7168 | Column7169 | Column7170 | Column7171 | Column7172 | Column7173 | Column7174 | Column7175 | Column7176 | Column7177 | Column7178 | Column7179 | Column7180 | Column7181 | Column7182 | Column7183 | Column7184 | Column7185 | Column7186 | Column7187 | Column7188 | Column7189 | Column7190 | Column7191 | Column7192 | Column7193 | Column7194 | Column7195 | Column7196 | Column7197 | Column7198 | Column7199 | Column7200 | Column7201 | Column7202 | Column7203 | Column7204 | Column7205 | Column7206 | Column7207 | Column7208 | Column7209 | Column7210 | Column7211 | Column7212 | Column7213 | Column7214 | Column7215 | Column7216 | Column7217 | Column7218 | Column7219 | Column7220 | Column7221 | Column7222 | Column7223 | Column7224 | Column7225 | Column7226 | Column7227 | Column7228 | Column7229 | Column7230 | Column7231 | Column7232 | Column7233 | Column7234 | Column7235 | Column7236 | Column7237 | Column7238 | Column7239 | Column7240 | Column7241 | Column7242 | Column7243 | Column7244 | Column7245 | Column7246 | Column7247 | Column7248 | Column7249 | Column7250 | Column7251 | Column7252 | Column7253 | Column7254 | Column7255 | Column7256 | Column7257 | Column7258 | Column7259 | Column7260 | Column7261 | Column7262 | Column7263 | Column7264 | Column7265 | Column7266 | Column7267 | Column7268 | Column7269 | Column7270 | Column7271 | Column7272 | Column7273 | Column7274 | Column7275 | Column7276 | Column7277 | Column7278 | Column7279 | Column7280 | Column7281 | Column7282 | Column7283 | Column7284 | Column7285 | Column7286 | Column7287 | Column7288 | Column7289 | Column7290 | Column7291 | Column7292 | Column7293 | Column7294 | Column7295 | Column7296 | Column7297 | Column7298 | Column7299 | Column7300 | Column7301 | Column7302 | Column7303 | Column7304 | Column7305 | Column7306 | Column7307 | Column7308 | Column7309 | Column7310 | Column7311 | Column7312 | Column7313 | Column7314 | Column7315 | Column7316 | Column7317 | Column7318 | Column7319 | Column7320 | Column7321 | Column7322 | Column7323 | Column7324 | Column7325 | Column7326 | Column7327 | Column7328 | Column7329 | Column7330 | Column7331 | Column7332 | Column7333 | Column7334 | Column7335 | Column7336 | Column7337 | Column7338 | Column7339 | Column7340 | Column7341 | Column7342 | Column7343 | Column7344 | Column7345 | Column7346 | Column7347 | Column7348 | Column7349 | Column7350 | Column7351 | Column7352 | Column7353 | Column7354 | Column7355 | Column7356 | Column7357 | Column7358 | Column7359 | Column7360 | Column7361 | Column7362 | Column7363 | Column7364 | Column7365 | Column7366 | Column7367 | Column7368 | Column7369 | Column7370 | Column7371 | Column7372 | Column7373 | Column7374 | Column7375 | Column7376 | Column7377 | Column7378 | Column7379 | Column7380 | Column7381 | Column7382 | Column7383 | Column7384 | Column7385 | Column7386 | Column7387 | Column7388 | Column7389 | Column7390 | Column7391 | Column7392 | Column7393 | Column7394 | Column7395 | Column7396 | Column7397 | Column7398 | Column7399 | Column7400 | Column7401 | Column7402 | Column7403 | Column7404 | Column7405 | Column7406 | Column7407 | Column7408 | Column7409 | Column7410 | Column7411 | Column7412 | Column7413 | Column7414 | Column7415 | Column7416 | Column7417 | Column7418 | Column7419 | Column7420 | Column7421 | Column7422 | Column7423 | Column7424 | Column7425 | Column7426 | Column7427 | Column7428 | Column7429 | Column7430 | Column7431 | Column7432 | Column7433 | Column7434 | Column7435 | Column7436 | Column7437 | Column7438 | Column7439 | Column7440 | Column7441 | Column7442 | Column7443 | Column7444 | Column7445 | Column7446 | Column7447 | Column7448 | Column7449 | Column7450 | Column7451 | Column7452 | Column7453 | Column7454 | Column7455 | Column7456 | Column7457 | Column7458 | Column7459 | Column7460 | Column7461 | Column7462 | Column7463 | Column7464 | Column7465 | Column7466 | Column7467 | Column7468 | Column7469 | Column7470 | Column7471 | Column7472 | Column7473 | Column7474 | Column7475 | Column7476 | Column7477 | Column7478 | Column7479 | Column7480 | Column7481 | Column7482 | Column7483 | Column7484 | Column7485 | Column7486 | Column7487 | Column7488 | Column7489 | Column7490 | Column7491 | Column7492 | Column7493 | Column7494 | Column7495 | Column7496 | Column7497 | Column7498 | Column7499 | Column7500 | Column7501 | Column7502 | Column7503 | Column7504 | Column7505 | Column7506 | Column7507 | Column7508 | Column7509 | Column7510 | Column7511 | Column7512 | Column7513 | Column7514 | Column7515 | Column7516 | Column7517 | Column7518 | Column7519 | Column7520 | Column7521 | Column7522 | Column7523 | Column7524 | Column7525 | Column7526 | Column7527 | Column7528 | Column7529 | Column7530 | Column7531 | Column7532 | Column7533 | Column7534 | Column7535 | Column7536 | Column7537 | Column7538 | Column7539 | Column7540 | Column7541 | Column7542 | Column7543 | Column7544 | Column7545 | Column7546 | Column7547 | Column7548 | Column7549 | Column7550 | Column7551 | Column7552 | Column7553 | Column7554 | Column7555 | Column7556 | Column7557 | Column7558 | Column7559 | Column7560 | Column7561 | Column7562 | Column7563 | Column7564 | Column7565 | Column7566 | Column7567 | Column7568 | Column7569 | Column7570 | Column7571 | Column7572 | Column7573 | Column7574 | Column7575 | Column7576 | Column7577 | Column7578 | Column7579 | Column7580 | Column7581 | Column7582 | Column7583 | Column7584 | Column7585 | Column7586 | Column7587 | Column7588 | Column7589 | Column7590 | Column7591 | Column7592 | Column7593 | Column7594 | Column7595 | Column7596 | Column7597 | Column7598 | Column7599 | Column7600 | Column7601 | Column7602 | Column7603 | Column7604 | Column7605 | Column7606 | Column7607 | Column7608 | Column7609 | Column7610 | Column7611 | Column7612 | Column7613 | Column7614 | Column7615 | Column7616 | Column7617 | Column7618 | Column7619 | Column7620 | Column7621 | Column7622 | Column7623 | Column7624 | Column7625 | Column7626 | Column7627 | Column7628 | Column7629 | Column7630 | Column7631 | Column7632 | Column7633 | Column7634 | Column7635 | Column7636 | Column7637 | Column7638 | Column7639 | Column7640 | Column7641 | Column7642 | Column7643 | Column7644 | Column7645 | Column7646 | Column7647 | Column7648 | Column7649 | Column7650 | Column7651 | Column7652 | Column7653 | Column7654 | Column7655 | Column7656 | Column7657 | Column7658 | Column7659 | Column7660 | Column7661 | Column7662 | Column7663 | Column7664 | Column7665 | Column7666 | Column7667 | Column7668 | Column7669 | Column7670 | Column7671 | Column7672 | Column7673 | Column7674 | Column7675 | Column7676 | Column7677 | Column7678 | Column7679 | Column7680 | Column7681 | Column7682 | Column7683 | Column7684 | Column7685 | Column7686 | Column7687 | Column7688 | Column7689 | Column7690 | Column7691 | Column7692 | Column7693 | Column7694 | Column7695 | Column7696 | Column7697 | Column7698 | Column7699 | Column7700 | Column7701 | Column7702 | Column7703 | Column7704 | Column7705 | Column7706 | Column7707 | Column7708 | Column7709 | Column7710 | Column7711 | Column7712 | Column7713 | Column7714 | Column7715 | Column7716 | Column7717 | Column7718 | Column7719 | Column7720 | Column7721 | Column7722 | Column7723 | Column7724 | Column7725 | Column7726 | Column7727 | Column7728 | Column7729 | Column7730 | Column7731 | Column7732 | Column7733 | Column7734 | Column7735 | Column7736 | Column7737 | Column7738 | Column7739 | Column7740 | Column7741 | Column7742 | Column7743 | Column7744 | Column7745 | Column7746 | Column7747 | Column7748 | Column7749 | Column7750 | Column7751 | Column7752 | Column7753 | Column7754 | Column7755 | Column7756 | Column7757 | Column7758 | Column7759 | Column7760 | Column7761 | Column7762 | Column7763 | Column7764 | Column7765 | Column7766 | Column7767 | Column7768 | Column7769 | Column7770 | Column7771 | Column7772 | Column7773 | Column7774 | Column7775 | Column7776 | Column7777 | Column7778 | Column7779 | Column7780 | Column7781 | Column7782 | Column7783 | Column7784 | Column7785 | Column7786 | Column7787 | Column7788 | Column7789 | Column7790 | Column7791 | Column7792 | Column7793 | Column7794 | Column7795 | Column7796 | Column7797 | Column7798 | Column7799 | Column7800 | Column7801 | Column7802 | Column7803 | Column7804 | Column7805 | Column7806 | Column7807 | Column7808 | Column7809 | Column7810 | Column7811 | Column7812 | Column7813 | Column7814 | Column7815 | Column7816 | Column7817 | Column7818 | Column7819 | Column7820 | Column7821 | Column7822 | Column7823 | Column7824 | Column7825 | Column7826 | Column7827 | Column7828 | Column7829 | Column7830 | Column7831 | Column7832 | Column7833 | Column7834 | Column7835 | Column7836 | Column7837 | Column7838 | Column7839 | Column7840 | Column7841 | Column7842 | Column7843 | Column7844 | Column7845 | Column7846 | Column7847 | Column7848 | Column7849 | Column7850 | Column7851 | Column7852 | Column7853 | Column7854 | Column7855 | Column7856 | Column7857 | Column7858 | Column7859 | Column7860 | Column7861 | Column7862 | Column7863 | Column7864 | Column7865 | Column7866 | Column7867 | Column7868 | Column7869 | Column7870 | Column7871 | Column7872 | Column7873 | Column7874 | Column7875 | Column7876 | Column7877 | Column7878 | Column7879 | Column7880 | Column7881 | Column7882 | Column7883 | Column7884 | Column7885 | Column7886 | Column7887 | Column7888 | Column7889 | Column7890 | Column7891 | Column7892 | Column7893 | Column7894 | Column7895 | Column7896 | Column7897 | Column7898 | Column7899 | Column7900 | Column7901 | Column7902 | Column7903 | Column7904 | Column7905 | Column7906 | Column7907 | Column7908 | Column7909 | Column7910 | Column7911 | Column7912 | Column7913 | Column7914 | Column7915 | Column7916 | Column7917 | Column7918 | Column7919 | Column7920 | Column7921 | Column7922 | Column7923 | Column7924 | Column7925 | Column7926 | Column7927 | Column7928 | Column7929 | Column7930 | Column7931 | Column7932 | Column7933 | Column7934 | Column7935 | Column7936 | Column7937 | Column7938 | Column7939 | Column7940 | Column7941 | Column7942 | Column7943 | Column7944 | Column7945 | Column7946 | Column7947 | Column7948 | Column7949 | Column7950 | Column7951 | Column7952 | Column7953 | Column7954 | Column7955 | Column7956 | Column7957 | Column7958 | Column7959 | Column7960 | Column7961 | Column7962 | Column7963 | Column7964 | Column7965 | Column7966 | Column7967 | Column7968 | Column7969 | Column7970 | Column7971 | Column7972 | Column7973 | Column7974 | Column7975 | Column7976 | Column7977 | Column7978 | Column7979 | Column7980 | Column7981 | Column7982 | Column7983 | Column7984 | Column7985 | Column7986 | Column7987 | Column7988 | Column7989 | Column7990 | Column7991 | Column7992 | Column7993 | Column7994 | Column7995 | Column7996 | Column7997 | Column7998 | Column7999 | Column8000 | Column8001 | Column8002 | Column8003 | Column8004 | Column8005 | Column8006 | Column8007 | Column8008 | Column8009 | Column8010 | Column8011 | Column8012 | Column8013 | Column8014 | Column8015 | Column8016 | Column8017 | Column8018 | Column8019 | Column8020 | Column8021 | Column8022 | Column8023 | Column8024 | Column8025 | Column8026 | Column8027 | Column8028 | Column8029 | Column8030 | Column8031 | Column8032 | Column8033 | Column8034 | Column8035 | Column8036 | Column8037 | Column8038 | Column8039 | Column8040 | Column8041 | Column8042 | Column8043 | Column8044 | Column8045 | Column8046 | Column8047 | Column8048 | Column8049 | Column8050 | Column8051 | Column8052 | Column8053 | Column8054 | Column8055 | Column8056 | Column8057 | Column8058 | Column8059 | Column8060 | Column8061 | Column8062 | Column8063 | Column8064 | Column8065 | Column8066 | Column8067 | Column8068 | Column8069 | Column8070 | Column8071 | Column8072 | Column8073 | Column8074 | Column8075 | Column8076 | Column8077 | Column8078 | Column8079 | Column8080 | Column8081 | Column8082 | Column8083 | Column8084 | Column8085 | Column8086 | Column8087 | Column8088 | Column8089 | Column8090 | Column8091 | Column8092 | Column8093 | Column8094 | Column8095 | Column8096 | Column8097 | Column8098 | Column8099 | Column8100 | Column8101 | Column8102 | Column8103 | Column8104 | Column8105 | Column8106 | Column8107 | Column8108 | Column8109 | Column8110 | Column8111 | Column8112 | Column8113 | Column8114 | Column8115 | Column8116 | Column8117 | Column8118 | Column8119 | Column8120 | Column8121 | Column8122 | Column8123 | Column8124 | Column8125 | Column8126 | Column8127 | Column8128 | Column8129 | Column8130 | Column8131 | Column8132 | Column8133 | Column8134 | Column8135 | Column8136 | Column8137 | Column8138 | Column8139 | Column8140 | Column8141 | Column8142 | Column8143 | Column8144 | Column8145 | Column8146 | Column8147 | Column8148 | Column8149 | Column8150 | Column8151 | Column8152 | Column8153 | Column8154 | Column8155 | Column8156 | Column8157 | Column8158 | Column8159 | Column8160 | Column8161 | Column8162 | Column8163 | Column8164 | Column8165 | Column8166 | Column8167 | Column8168 | Column8169 | Column8170 | Column8171 | Column8172 | Column8173 | Column8174 | Column8175 | Column8176 | Column8177 | Column8178 | Column8179 | Column8180 | Column8181 | Column8182 | Column8183 | Column8184 | Column8185 | Column8186 | Column8187 | Column8188 | Column8189 | Column8190 | Column8191 | Column8192 | Column8193 | Column8194 | Column8195 | Column8196 | Column8197 | Column8198 | Column8199 | Column8200 | Column8201 | Column8202 | Column8203 | Column8204 | Column8205 | Column8206 | Column8207 | Column8208 | Column8209 | Column8210 | Column8211 | Column8212 | Column8213 | Column8214 | Column8215 | Column8216 | Column8217 | Column8218 | Column8219 | Column8220 | Column8221 | Column8222 | Column8223 | Column8224 | Column8225 | Column8226 | Column8227 | Column8228 | Column8229 | Column8230 | Column8231 | Column8232 | Column8233 | Column8234 | Column8235 | Column8236 | Column8237 | Column8238 | Column8239 | Column8240 | Column8241 | Column8242 | Column8243 | Column8244 | Column8245 | Column8246 | Column8247 | Column8248 | Column8249 | Column8250 | Column8251 | Column8252 | Column8253 | Column8254 | Column8255 | Column8256 | Column8257 | Column8258 | Column8259 | Column8260 | Column8261 | Column8262 | Column8263 | Column8264 | Column8265 | Column8266 | Column8267 | Column8268 | Column8269 | Column8270 | Column8271 | Column8272 | Column8273 | Column8274 | Column8275 | Column8276 | Column8277 | Column8278 | Column8279 | Column8280 | Column8281 | Column8282 | Column8283 | Column8284 | Column8285 | Column8286 | Column8287 | Column8288 | Column8289 | Column8290 | Column8291 | Column8292 | Column8293 | Column8294 | Column8295 | Column8296 | Column8297 | Column8298 | Column8299 | Column8300 | Column8301 | Column8302 | Column8303 | Column8304 | Column8305 | Column8306 | Column8307 | Column8308 | Column8309 | Column8310 | Column8311 | Column8312 | Column8313 | Column8314 | Column8315 | Column8316 | Column8317 | Column8318 | Column8319 | Column8320 | Column8321 | Column8322 | Column8323 | Column8324 | Column8325 | Column8326 | Column8327 | Column8328 | Column8329 | Column8330 | Column8331 | Column8332 | Column8333 | Column8334 | Column8335 | Column8336 | Column8337 | Column8338 | Column8339 | Column8340 | Column8341 | Column8342 | Column8343 | Column8344 | Column8345 | Column8346 | Column8347 | Column8348 | Column8349 | Column8350 | Column8351 | Column8352 | Column8353 | Column8354 | Column8355 | Column8356 | Column8357 | Column8358 | Column8359 | Column8360 | Column8361 | Column8362 | Column8363 | Column8364 | Column8365 | Column8366 | Column8367 | Column8368 | Column8369 | Column8370 | Column8371 | Column8372 | Column8373 | Column8374 | Column8375 | Column8376 | Column8377 | Column8378 | Column8379 | Column8380 | Column8381 | Column8382 | Column8383 | Column8384 | Column8385 | Column8386 | Column8387 | Column8388 | Column8389 | Column8390 | Column8391 | Column8392 | Column8393 | Column8394 | Column8395 | Column8396 | Column8397 | Column8398 | Column8399 | Column8400 | Column8401 | Column8402 | Column8403 | Column8404 | Column8405 | Column8406 | Column8407 | Column8408 | Column8409 | Column8410 | Column8411 | Column8412 | Column8413 | Column8414 | Column8415 | Column8416 | Column8417 | Column8418 | Column8419 | Column8420 | Column8421 | Column8422 | Column8423 | Column8424 | Column8425 | Column8426 | Column8427 | Column8428 | Column8429 | Column8430 | Column8431 | Column8432 | Column8433 | Column8434 | Column8435 | Column8436 | Column8437 | Column8438 | Column8439 | Column8440 | Column8441 | Column8442 | Column8443 | Column8444 | Column8445 | Column8446 | Column8447 | Column8448 | Column8449 | Column8450 | Column8451 | Column8452 | Column8453 | Column8454 | Column8455 | Column8456 | Column8457 | Column8458 | Column8459 | Column8460 | Column8461 | Column8462 | Column8463 | Column8464 | Column8465 | Column8466 | Column8467 | Column8468 | Column8469 | Column8470 | Column8471 | Column8472 | Column8473 | Column8474 | Column8475 | Column8476 | Column8477 | Column8478 | Column8479 | Column8480 | Column8481 | Column8482 | Column8483 | Column8484 | Column8485 | Column8486 | Column8487 | Column8488 | Column8489 | Column8490 | Column8491 | Column8492 | Column8493 | Column8494 | Column8495 | Column8496 | Column8497 | Column8498 | Column8499 | Column8500 | Column8501 | Column8502 | Column8503 | Column8504 | Column8505 | Column8506 | Column8507 | Column8508 | Column8509 | Column8510 | Column8511 | Column8512 | Column8513 | Column8514 | Column8515 | Column8516 | Column8517 | Column8518 | Column8519 | Column8520 | Column8521 | Column8522 | Column8523 | Column8524 | Column8525 | Column8526 | Column8527 | Column8528 | Column8529 | Column8530 | Column8531 | Column8532 | Column8533 | Column8534 | Column8535 | Column8536 | Column8537 | Column8538 | Column8539 | Column8540 | Column8541 | Column8542 | Column8543 | Column8544 | Column8545 | Column8546 | Column8547 | Column8548 | Column8549 | Column8550 | Column8551 | Column8552 | Column8553 | Column8554 | Column8555 | Column8556 | Column8557 | Column8558 | Column8559 | Column8560 | Column8561 | Column8562 | Column8563 | Column8564 | Column8565 | Column8566 | Column8567 | Column8568 | Column8569 | Column8570 | Column8571 | Column8572 | Column8573 | Column8574 | Column8575 | Column8576 | Column8577 | Column8578 | Column8579 | Column8580 | Column8581 | Column8582 | Column8583 | Column8584 | Column8585 | Column8586 | Column8587 | Column8588 | Column8589 | Column8590 | Column8591 | Column8592 | Column8593 | Column8594 | Column8595 | Column8596 | Column8597 | Column8598 | Column8599 | Column8600 | Column8601 | Column8602 | Column8603 | Column8604 | Column8605 | Column8606 | Column8607 | Column8608 | Column8609 | Column8610 | Column8611 | Column8612 | Column8613 | Column8614 | Column8615 | Column8616 | Column8617 | Column8618 | Column8619 | Column8620 | Column8621 | Column8622 | Column8623 | Column8624 | Column8625 | Column8626 | Column8627 | Column8628 | Column8629 | Column8630 | Column8631 | Column8632 | Column8633 | Column8634 | Column8635 | Column8636 | Column8637 | Column8638 | Column8639 | Column8640 | Column8641 | Column8642 | Column8643 | Column8644 | Column8645 | Column8646 | Column8647 | Column8648 | Column8649 | Column8650 | Column8651 | Column8652 | Column8653 | Column8654 | Column8655 | Column8656 | Column8657 | Column8658 | Column8659 | Column8660 | Column8661 | Column8662 | Column8663 | Column8664 | Column8665 | Column8666 | Column8667 | Column8668 | Column8669 | Column8670 | Column8671 | Column8672 | Column8673 | Column8674 | Column8675 | Column8676 | Column8677 | Column8678 | Column8679 | Column8680 | Column8681 | Column8682 | Column8683 | Column8684 | Column8685 | Column8686 | Column8687 | Column8688 | Column8689 | Column8690 | Column8691 | Column8692 | Column8693 | Column8694 | Column8695 | Column8696 | Column8697 | Column8698 | Column8699 | Column8700 | Column8701 | Column8702 | Column8703 | Column8704 | Column8705 | Column8706 | Column8707 | Column8708 | Column8709 | Column8710 | Column8711 | Column8712 | Column8713 | Column8714 | Column8715 | Column8716 | Column8717 | Column8718 | Column8719 | Column8720 | Column8721 | Column8722 | Column8723 | Column8724 | Column8725 | Column8726 | Column8727 | Column8728 | Column8729 | Column8730 | Column8731 | Column8732 | Column8733 | Column8734 | Column8735 | Column8736 | Column8737 | Column8738 | Column8739 | Column8740 | Column8741 | Column8742 | Column8743 | Column8744 | Column8745 | Column8746 | Column8747 | Column8748 | Column8749 | Column8750 | Column8751 | Column8752 | Column8753 | Column8754 | Column8755 | Column8756 | Column8757 | Column8758 | Column8759 | Column8760 | Column8761 | Column8762 | Column8763 | Column8764 | Column8765 | Column8766 | Column8767 | Column8768 | Column8769 | Column8770 | Column8771 | Column8772 | Column8773 | Column8774 | Column8775 | Column8776 | Column8777 | Column8778 | Column8779 | Column8780 | Column8781 | Column8782 | Column8783 | Column8784 | Column8785 | Column8786 | Column8787 | Column8788 | Column8789 | Column8790 | Column8791 | Column8792 | Column8793 | Column8794 | Column8795 | Column8796 | Column8797 | Column8798 | Column8799 | Column8800 | Column8801 | Column8802 | Column8803 | Column8804 | Column8805 | Column8806 | Column8807 | Column8808 | Column8809 | Column8810 | Column8811 | Column8812 | Column8813 | Column8814 | Column8815 | Column8816 | Column8817 | Column8818 | Column8819 | Column8820 | Column8821 | Column8822 | Column8823 | Column8824 | Column8825 | Column8826 | Column8827 | Column8828 | Column8829 | Column8830 | Column8831 | Column8832 | Column8833 | Column8834 | Column8835 | Column8836 | Column8837 | Column8838 | Column8839 | Column8840 | Column8841 | Column8842 | Column8843 | Column8844 | Column8845 | Column8846 | Column8847 | Column8848 | Column8849 | Column8850 | Column8851 | Column8852 | Column8853 | Column8854 | Column8855 | Column8856 | Column8857 | Column8858 | Column8859 | Column8860 | Column8861 | Column8862 | Column8863 | Column8864 | Column8865 | Column8866 | Column8867 | Column8868 | Column8869 | Column8870 | Column8871 | Column8872 | Column8873 | Column8874 | Column8875 | Column8876 | Column8877 | Column8878 | Column8879 | Column8880 | Column8881 | Column8882 | Column8883 | Column8884 | Column8885 | Column8886 | Column8887 | Column8888 | Column8889 | Column8890 | Column8891 | Column8892 | Column8893 | Column8894 | Column8895 | Column8896 | Column8897 | Column8898 | Column8899 | Column8900 | Column8901 | Column8902 | Column8903 | Column8904 | Column8905 | Column8906 | Column8907 | Column8908 | Column8909 | Column8910 | Column8911 | Column8912 | Column8913 | Column8914 | Column8915 | Column8916 | Column8917 | Column8918 | Column8919 | Column8920 | Column8921 | Column8922 | Column8923 | Column8924 | Column8925 | Column8926 | Column8927 | Column8928 | Column8929 | Column8930 | Column8931 | Column8932 | Column8933 | Column8934 | Column8935 | Column8936 | Column8937 | Column8938 | Column8939 | Column8940 | Column8941 | Column8942 | Column8943 | Column8944 | Column8945 | Column8946 | Column8947 | Column8948 | Column8949 | Column8950 | Column8951 | Column8952 | Column8953 | Column8954 | Column8955 | Column8956 | Column8957 | Column8958 | Column8959 | Column8960 | Column8961 | Column8962 | Column8963 | Column8964 | Column8965 | Column8966 | Column8967 | Column8968 | Column8969 | Column8970 | Column8971 | Column8972 | Column8973 | Column8974 | Column8975 | Column8976 | Column8977 | Column8978 | Column8979 | Column8980 | Column8981 | Column8982 | Column8983 | Column8984 | Column8985 | Column8986 | Column8987 | Column8988 | Column8989 | Column8990 | Column8991 | Column8992 | Column8993 | Column8994 | Column8995 | Column8996 | Column8997 | Column8998 | Column8999 | Column9000 | Column9001 | Column9002 | Column9003 | Column9004 | Column9005 | Column9006 | Column9007 | Column9008 | Column9009 | Column9010 | Column9011 | Column9012 | Column9013 | Column9014 | Column9015 | Column9016 | Column9017 | Column9018 | Column9019 | Column9020 | Column9021 | Column9022 | Column9023 | Column9024 | Column9025 | Column9026 | Column9027 | Column9028 | Column9029 | Column9030 | Column9031 | Column9032 | Column9033 | Column9034 | Column9035 | Column9036 | Column9037 | Column9038 | Column9039 | Column9040 | Column9041 | Column9042 | Column9043 | Column9044 | Column9045 | Column9046 | Column9047 | Column9048 | Column9049 | Column9050 | Column9051 | Column9052 | Column9053 | Column9054 | Column9055 | Column9056 | Column9057 | Column9058 | Column9059 | Column9060 | Column9061 | Column9062 | Column9063 | Column9064 | Column9065 | Column9066 | Column9067 | Column9068 | Column9069 | Column9070 | Column9071 | Column9072 | Column9073 | Column9074 | Column9075 | Column9076 | Column9077 | Column9078 | Column9079 | Column9080 | Column9081 | Column9082 | Column9083 | Column9084 | Column9085 | Column9086 | Column9087 | Column9088 | Column9089 | Column9090 | Column9091 | Column9092 | Column9093 | Column9094 | Column9095 | Column9096 | Column9097 | Column9098 | Column9099 | Column9100 | Column9101 | Column9102 | Column9103 | Column9104 | Column9105 | Column9106 | Column9107 | Column9108 | Column9109 | Column9110 | Column9111 | Column9112 | Column9113 | Column9114 | Column9115 | Column9116 | Column9117 | Column9118 | Column9119 | Column9120 | Column9121 | Column9122 | Column9123 | Column9124 | Column9125 | Column9126 | Column9127 | Column9128 | Column9129 | Column9130 | Column9131 | Column9132 | Column9133 | Column9134 | Column9135 | Column9136 | Column9137 | Column9138 | Column9139 | Column9140 | Column9141 | Column9142 | Column9143 | Column9144 | Column9145 | Column9146 | Column9147 | Column9148 | Column9149 | Column9150 | Column9151 | Column9152 | Column9153 | Column9154 | Column9155 | Column9156 | Column9157 | Column9158 | Column9159 | Column9160 | Column9161 | Column9162 | Column9163 | Column9164 | Column9165 | Column9166 | Column9167 | Column9168 | Column9169 | Column9170 | Column9171 | Column9172 | Column9173 | Column9174 | Column9175 | Column9176 | Column9177 | Column9178 | Column9179 | Column9180 | Column9181 | Column9182 | Column9183 | Column9184 | Column9185 | Column9186 | Column9187 | Column9188 | Column9189 | Column9190 | Column9191 | Column9192 | Column9193 | Column9194 | Column9195 | Column9196 | Column9197 | Column9198 | Column9199 | Column9200 | Column9201 | Column9202 | Column9203 | Column9204 | Column9205 | Column9206 | Column9207 | Column9208 | Column9209 | Column9210 | Column9211 | Column9212 | Column9213 | Column9214 | Column9215 | Column9216 | Column9217 | Column9218 | Column9219 | Column9220 | Column9221 | Column9222 | Column9223 | Column9224 | Column9225 | Column9226 | Column9227 | Column9228 | Column9229 | Column9230 | Column9231 | Column9232 | Column9233 | Column9234 | Column9235 | Column9236 | Column9237 | Column9238 | Column9239 | Column9240 | Column9241 | Column9242 | Column9243 | Column9244 | Column9245 | Column9246 | Column9247 | Column9248 | Column9249 | Column9250 | Column9251 | Column9252 | Column9253 | Column9254 | Column9255 | Column9256 | Column9257 | Column9258 | Column9259 | Column9260 | Column9261 | Column9262 | Column9263 | Column9264 | Column9265 | Column9266 | Column9267 | Column9268 | Column9269 | Column9270 | Column9271 | Column9272 | Column9273 | Column9274 | Column9275 | Column9276 | Column9277 | Column9278 | Column9279 | Column9280 | Column9281 | Column9282 | Column9283 | Column9284 | Column9285 | Column9286 | Column9287 | Column9288 | Column9289 | Column9290 | Column9291 | Column9292 | Column9293 | Column9294 | Column9295 | Column9296 | Column9297 | Column9298 | Column9299 | Column9300 | Column9301 | Column9302 | Column9303 | Column9304 | Column9305 | Column9306 | Column9307 | Column9308 | Column9309 | Column9310 | Column9311 | Column9312 | Column9313 | Column9314 | Column9315 | Column9316 | Column9317 | Column9318 | Column9319 | Column9320 | Column9321 | Column9322 | Column9323 | Column9324 | Column9325 | Column9326 | Column9327 | Column9328 | Column9329 | Column9330 | Column9331 | Column9332 | Column9333 | Column9334 | Column9335 | Column9336 | Column9337 | Column9338 | Column9339 | Column9340 | Column9341 | Column9342 | Column9343 | Column9344 | Column9345 | Column9346 | Column9347 | Column9348 | Column9349 | Column9350 | Column9351 | Column9352 | Column9353 | Column9354 | Column9355 | Column9356 | Column9357 | Column9358 | Column9359 | Column9360 | Column9361 | Column9362 | Column9363 | Column9364 | Column9365 | Column9366 | Column9367 | Column9368 | Column9369 | Column9370 | Column9371 | Column9372 | Column9373 | Column9374 | Column9375 | Column9376 | Column9377 | Column9378 | Column9379 | Column9380 | Column9381 | Column9382 | Column9383 | Column9384 | Column9385 | Column9386 | Column9387 | Column9388 | Column9389 | Column9390 | Column9391 | Column9392 | Column9393 | Column9394 | Column9395 | Column9396 | Column9397 | Column9398 | Column9399 | Column9400 | Column9401 | Column9402 | Column9403 | Column9404 | Column9405 | Column9406 | Column9407 | Column9408 | Column9409 | Column9410 | Column9411 | Column9412 | Column9413 | Column9414 | Column9415 | Column9416 | Column9417 | Column9418 | Column9419 | Column9420 | Column9421 | Column9422 | Column9423 | Column9424 | Column9425 | Column9426 | Column9427 | Column9428 | Column9429 | Column9430 | Column9431 | Column9432 | Column9433 | Column9434 | Column9435 | Column9436 | Column9437 | Column9438 | Column9439 | Column9440 | Column9441 | Column9442 | Column9443 | Column9444 | Column9445 | Column9446 | Column9447 | Column9448 | Column9449 | Column9450 | Column9451 | Column9452 | Column9453 | Column9454 | Column9455 | Column9456 | Column9457 | Column9458 | Column9459 | Column9460 | Column9461 | Column9462 | Column9463 | Column9464 | Column9465 | Column9466 | Column9467 | Column9468 | Column9469 | Column9470 | Column9471 | Column9472 | Column9473 | Column9474 | Column9475 | Column9476 | Column9477 | Column9478 | Column9479 | Column9480 | Column9481 | Column9482 | Column9483 | Column9484 | Column9485 | Column9486 | Column9487 | Column9488 | Column9489 | Column9490 | Column9491 | Column9492 | Column9493 | Column9494 | Column9495 | Column9496 | Column9497 | Column9498 | Column9499 | Column9500 | Column9501 | Column9502 | Column9503 | Column9504 | Column9505 | Column9506 | Column9507 | Column9508 | Column9509 | Column9510 | Column9511 | Column9512 | Column9513 | Column9514 | Column9515 | Column9516 | Column9517 | Column9518 | Column9519 | Column9520 | Column9521 | Column9522 | Column9523 | Column9524 | Column9525 | Column9526 | Column9527 | Column9528 | Column9529 | Column9530 | Column9531 | Column9532 | Column9533 | Column9534 | Column9535 | Column9536 | Column9537 | Column9538 | Column9539 | Column9540 | Column9541 | Column9542 | Column9543 | Column9544 | Column9545 | Column9546 | Column9547 | Column9548 | Column9549 | Column9550 | Column9551 | Column9552 | Column9553 | Column9554 | Column9555 | Column9556 | Column9557 | Column9558 | Column9559 | Column9560 | Column9561 | Column9562 | Column9563 | Column9564 | Column9565 | Column9566 | Column9567 | Column9568 | Column9569 | Column9570 | Column9571 | Column9572 | Column9573 | Column9574 | Column9575 | Column9576 | Column9577 | Column9578 | Column9579 | Column9580 | Column9581 | Column9582 | Column9583 | Column9584 | Column9585 | Column9586 | Column9587 | Column9588 | Column9589 | Column9590 | Column9591 | Column9592 | Column9593 | Column9594 | Column9595 | Column9596 | Column9597 | Column9598 | Column9599 | Column9600 | Column9601 | Column9602 | Column9603 | Column9604 | Column9605 | Column9606 | Column9607 | Column9608 | Column9609 | Column9610 | Column9611 | Column9612 | Column9613 | Column9614 | Column9615 | Column9616 | Column9617 | Column9618 | Column9619 | Column9620 | Column9621 | Column9622 | Column9623 | Column9624 | Column9625 | Column9626 | Column9627 | Column9628 | Column9629 | Column9630 | Column9631 | Column9632 | Column9633 | Column9634 | Column9635 | Column9636 | Column9637 | Column9638 | Column9639 | Column9640 | Column9641 | Column9642 | Column9643 | Column9644 | Column9645 | Column9646 | Column9647 | Column9648 | Column9649 | Column9650 | Column9651 | Column9652 | Column9653 | Column9654 | Column9655 | Column9656 | Column9657 | Column9658 | Column9659 | Column9660 | Column9661 | Column9662 | Column9663 | Column9664 | Column9665 | Column9666 | Column9667 | Column9668 | Column9669 | Column9670 | Column9671 | Column9672 | Column9673 | Column9674 | Column9675 | Column9676 | Column9677 | Column9678 | Column9679 | Column9680 | Column9681 | Column9682 | Column9683 | Column9684 | Column9685 | Column9686 | Column9687 | Column9688 | Column9689 | Column9690 | Column9691 | Column9692 | Column9693 | Column9694 | Column9695 | Column9696 | Column9697 | Column9698 | Column9699 | Column9700 | Column9701 | Column9702 | Column9703 | Column9704 | Column9705 | Column9706 | Column9707 | Column9708 | Column9709 | Column9710 | Column9711 | Column9712 | Column9713 | Column9714 | Column9715 | Column9716 | Column9717 | Column9718 | Column9719 | Column9720 | Column9721 | Column9722 | Column9723 | Column9724 | Column9725 | Column9726 | Column9727 | Column9728 | Column9729 | Column9730 | Column9731 | Column9732 | Column9733 | Column9734 | Column9735 | Column9736 | Column9737 | Column9738 | Column9739 | Column9740 | Column9741 | Column9742 | Column9743 | Column9744 | Column9745 | Column9746 | Column9747 | Column9748 | Column9749 | Column9750 | Column9751 | Column9752 | Column9753 | Column9754 | Column9755 | Column9756 | Column9757 | Column9758 | Column9759 | Column9760 | Column9761 | Column9762 | Column9763 | Column9764 | Column9765 | Column9766 | Column9767 | Column9768 | Column9769 | Column9770 | Column9771 | Column9772 | Column9773 | Column9774 | Column9775 | Column9776 | Column9777 | Column9778 | Column9779 | Column9780 | Column9781 | Column9782 | Column9783 | Column9784 | Column9785 | Column9786 | Column9787 | Column9788 | Column9789 | Column9790 | Column9791 | Column9792 | Column9793 | Column9794 | Column9795 | Column9796 | Column9797 | Column9798 | Column9799 | Column9800 | Column9801 | Column9802 | Column9803 | Column9804 | Column9805 | Column9806 | Column9807 | Column9808 | Column9809 | Column9810 | Column9811 | Column9812 | Column9813 | Column9814 | Column9815 | Column9816 | Column9817 | Column9818 | Column9819 | Column9820 | Column9821 | Column9822 | Column9823 | Column9824 | Column9825 | Column9826 | Column9827 | Column9828 | Column9829 | Column9830 | Column9831 | Column9832 | Column9833 | Column9834 | Column9835 | Column9836 | Column9837 | Column9838 | Column9839 | Column9840 | Column9841 | Column9842 | Column9843 | Column9844 | Column9845 | Column9846 | Column9847 | Column9848 | Column9849 | Column9850 | Column9851 | Column9852 | Column9853 | Column9854 | Column9855 | Column9856 | Column9857 | Column9858 | Column9859 | Column9860 | Column9861 | Column9862 | Column9863 | Column9864 | Column9865 | Column9866 | Column9867 | Column9868 | Column9869 | Column9870 | Column9871 | Column9872 | Column9873 | Column9874 | Column9875 | Column9876 | Column9877 | Column9878 | Column9879 | Column9880 | Column9881 | Column9882 | Column9883 | Column9884 | Column9885 | Column9886 | Column9887 | Column9888 | Column9889 | Column9890 | Column9891 | Column9892 | Column9893 | Column9894 | Column9895 | Column9896 | Column9897 | Column9898 | Column9899 | Column9900 | Column9901 | Column9902 | Column9903 | Column9904 | Column9905 | Column9906 | Column9907 | Column9908 | Column9909 | Column9910 | Column9911 | Column9912 | Column9913 | Column9914 | Column9915 | Column9916 | Column9917 | Column9918 | Column9919 | Column9920 | Column9921 | Column9922 | Column9923 | Column9924 | Column9925 | Column9926 | Column9927 | Column9928 | Column9929 | Column9930 | Column9931 | Column9932 | Column9933 | Column9934 | Column9935 | Column9936 | Column9937 | Column9938 | Column9939 | Column9940 | Column9941 | Column9942 | Column9943 | Column9944 | Column9945 | Column9946 | Column9947 | Column9948 | Column9949 | Column9950 | Column9951 | Column9952 | Column9953 | Column9954 | Column9955 | Column9956 | Column9957 | Column9958 | Column9959 | Column9960 | Column9961 | Column9962 | Column9963 | Column9964 | Column9965 | Column9966 | Column9967 | Column9968 | Column9969 | Column9970 | Column9971 | Column9972 | Column9973 | Column9974 | Column9975 | Column9976 | Column9977 | Column9978 | Column9979 | Column9980 | Column9981 | Column9982 | Column9983 | Column9984 | Column9985 | Column9986 | Column9987 | Column9988 | Column9989 | Column9990 | Column9991 | Column9992 | Column9993 | Column9994 | Column9995 | Column9996 | Column9997 | Column9998 | Column9999 | Column10000 | Column10001 | Column10002 | Column10003 | Column10004 | Column10005 | Column10006 | Column10007 | Column10008 | Column10009 | Column10010 | Column10011 | Column10012 | Column10013 | Column10014 | Column10015 | Column10016 | Column10017 | Column10018 | Column10019 | Column10020 | Column10021 | Column10022 | Column10023 | Column10024 | Column10025 | Column10026 | Column10027 | Column10028 | Column10029 | Column10030 | Column10031 | Column10032 | Column10033 | Column10034 | Column10035 | Column10036 | Column10037 | Column10038 | Column10039 | Column10040 | Column10041 | Column10042 | Column10043 | Column10044 | Column10045 | Column10046 | Column10047 | Column10048 | Column10049 | Column10050 | Column10051 | Column10052 | Column10053 | Column10054 | Column10055 | Column10056 | Column10057 | Column10058 | Column10059 | Column10060 | Column10061 | Column10062 | Column10063 | Column10064 | Column10065 | Column10066 | Column10067 | Column10068 | Column10069 | Column10070 | Column10071 | Column10072 | Column10073 | Column10074 | Column10075 | Column10076 | Column10077 | Column10078 | Column10079 | Column10080 | Column10081 | Column10082 | Column10083 | Column10084 | Column10085 | Column10086 | Column10087 | Column10088 | Column10089 | Column10090 | Column10091 | Column10092 | Column10093 | Column10094 | Column10095 | Column10096 | Column10097 | Column10098 | Column10099 | Column10100 | Column10101 | Column10102 | Column10103 | Column10104 | Column10105 | Column10106 | Column10107 | Column10108 | Column10109 | Column10110 | Column10111 | Column10112 | Column10113 | Column10114 | Column10115 | Column10116 | Column10117 | Column10118 | Column10119 | Column10120 | Column10121 | Column10122 | Column10123 | Column10124 | Column10125 | Column10126 | Column10127 | Column10128 | Column10129 | Column10130 | Column10131 | Column10132 | Column10133 | Column10134 | Column10135 | Column10136 | Column10137 | Column10138 | Column10139 | Column10140 | Column10141 | Column10142 | Column10143 | Column10144 | Column10145 | Column10146 | Column10147 | Column10148 | Column10149 | Column10150 | Column10151 | Column10152 | Column10153 | Column10154 | Column10155 | Column10156 | Column10157 | Column10158 | Column10159 | Column10160 | Column10161 | Column10162 | Column10163 | Column10164 | Column10165 | Column10166 | Column10167 | Column10168 | Column10169 | Column10170 | Column10171 | Column10172 | Column10173 | Column10174 | Column10175 | Column10176 | Column10177 | Column10178 | Column10179 | Column10180 | Column10181 | Column10182 | Column10183 | Column10184 | Column10185 | Column10186 | Column10187 | Column10188 | Column10189 | Column10190 | Column10191 | Column10192 | Column10193 | Column10194 | Column10195 | Column10196 | Column10197 | Column10198 | Column10199 | Column10200 | Column10201 | Column10202 | Column10203 | Column10204 | Column10205 | Column10206 | Column10207 | Column10208 | Column10209 | Column10210 | Column10211 | Column10212 | Column10213 | Column10214 | Column10215 | Column10216 | Column10217 | Column10218 | Column10219 | Column10220 | Column10221 | Column10222 | Column10223 | Column10224 | Column10225 | Column10226 | Column10227 | Column10228 | Column10229 | Column10230 | Column10231 | Column10232 | Column10233 | Column10234 | Column10235 | Column10236 | Column10237 | Column10238 | Column10239 | Column10240 | Column10241 | Column10242 | Column10243 | Column10244 | Column10245 | Column10246 | Column10247 | Column10248 | Column10249 | Column10250 | Column10251 | Column10252 | Column10253 | Column10254 | Column10255 | Column10256 | Column10257 | Column10258 | Column10259 | Column10260 | Column10261 | Column10262 | Column10263 | Column10264 | Column10265 | Column10266 | Column10267 | Column10268 | Column10269 | Column10270 | Column10271 | Column10272 | Column10273 | Column10274 | Column10275 | Column10276 | Column10277 | Column10278 | Column10279 | Column10280 | Column10281 | Column10282 | Column10283 | Column10284 | Column10285 | Column10286 | Column10287 | Column10288 | Column10289 | Column10290 | Column10291 | Column10292 | Column10293 | Column10294 | Column10295 | Column10296 | Column10297 | Column10298 | Column10299 | Column10300 | Column10301 | Column10302 | Column10303 | Column10304 | Column10305 | Column10306 | Column10307 | Column10308 | Column10309 | Column10310 | Column10311 | Column10312 | Column10313 | Column10314 | Column10315 | Column10316 | Column10317 | Column10318 | Column10319 | Column10320 | Column10321 | Column10322 | Column10323 | Column10324 | Column10325 | Column10326 | Column10327 | Column10328 | Column10329 | Column10330 | Column10331 | Column10332 | Column10333 | Column10334 | Column10335 | Column10336 | Column10337 | Column10338 | Column10339 | Column10340 | Column10341 | Column10342 | Column10343 | Column10344 | Column10345 | Column10346 | Column10347 | Column10348 | Column10349 | Column10350 | Column10351 | Column10352 | Column10353 | Column10354 | Column10355 | Column10356 | Column10357 | Column10358 | Column10359 | Column10360 | Column10361 | Column10362 | Column10363 | Column10364 | Column10365 | Column10366 | Column10367 | Column10368 | Column10369 | Column10370 | Column10371 | Column10372 | Column10373 | Column10374 | Column10375 | Column10376 | Column10377 | Column10378 | Column10379 | Column10380 | Column10381 | Column10382 | Column10383 | Column10384 | Column10385 | Column10386 | Column10387 | Column10388 | Column10389 | Column10390 | Column10391 | Column10392 | Column10393 | Column10394 | Column10395 | Column10396 | Column10397 | Column10398 | Column10399 | Column10400 | Column10401 | Column10402 | Column10403 | Column10404 | Column10405 | Column10406 | Column10407 | Column10408 | Column10409 | Column10410 | Column10411 | Column10412 | Column10413 | Column10414 | Column10415 | Column10416 | Column10417 | Column10418 | Column10419 | Column10420 | Column10421 | Column10422 | Column10423 | Column10424 | Column10425 | Column10426 | Column10427 | Column10428 | Column10429 | Column10430 | Column10431 | Column10432 | Column10433 | Column10434 | Column10435 | Column10436 | Column10437 | Column10438 | Column10439 | Column10440 | Column10441 | Column10442 | Column10443 | Column10444 | Column10445 | Column10446 | Column10447 | Column10448 | Column10449 | Column10450 | Column10451 | Column10452 | Column10453 | Column10454 | Column10455 | Column10456 | Column10457 | Column10458 | Column10459 | Column10460 | Column10461 | Column10462 | Column10463 | Column10464 | Column10465 | Column10466 | Column10467 | Column10468 | Column10469 | Column10470 | Column10471 | Column10472 | Column10473 | Column10474 | Column10475 | Column10476 | Column10477 | Column10478 | Column10479 | Column10480 | Column10481 | Column10482 | Column10483 | Column10484 | Column10485 | Column10486 | Column10487 | Column10488 | Column10489 | Column10490 | Column10491 | Column10492 | Column10493 | Column10494 | Column10495 | Column10496 | Column10497 | Column10498 | Column10499 | Column10500 | Column10501 | Column10502 | Column10503 | Column10504 | Column10505 | Column10506 | Column10507 | Column10508 | Column10509 | Column10510 | Column10511 | Column10512 | Column10513 | Column10514 | Column10515 | Column10516 | Column10517 | Column10518 | Column10519 | Column10520 | Column10521 | Column10522 | Column10523 | Column10524 | Column10525 | Column10526 | Column10527 | Column10528 | Column10529 | Column10530 | Column10531 | Column10532 | Column10533 | Column10534 | Column10535 | Column10536 | Column10537 | Column10538 | Column10539 | Column10540 | Column10541 | Column10542 | Column10543 | Column10544 | Column10545 | Column10546 | Column10547 | Column10548 | Column10549 | Column10550 | Column10551 | Column10552 | Column10553 | Column10554 | Column10555 | Column10556 | Column10557 | Column10558 | Column10559 | Column10560 | Column10561 | Column10562 | Column10563 | Column10564 | Column10565 | Column10566 | Column10567 | Column10568 | Column10569 | Column10570 | Column10571 | Column10572 | Column10573 | Column10574 | Column10575 | Column10576 | Column10577 | Column10578 | Column10579 | Column10580 | Column10581 | Column10582 | Column10583 | Column10584 | Column10585 | Column10586 | Column10587 | Column10588 | Column10589 | Column10590 | Column10591 | Column10592 | Column10593 | Column10594 | Column10595 | Column10596 | Column10597 | Column10598 | Column10599 | Column10600 | Column10601 | Column10602 | Column10603 | Column10604 | Column10605 | Column10606 | Column10607 | Column10608 | Column10609 | Column10610 | Column10611 | Column10612 | Column10613 | Column10614 | Column10615 | Column10616 | Column10617 | Column10618 | Column10619 | Column10620 | Column10621 | Column10622 | Column10623 | Column10624 | Column10625 | Column10626 | Column10627 | Column10628 | Column10629 | Column10630 | Column10631 | Column10632 | Column10633 | Column10634 | Column10635 | Column10636 | Column10637 | Column10638 | Column10639 | Column10640 | Column10641 | Column10642 | Column10643 | Column10644 | Column10645 | Column10646 | Column10647 | Column10648 | Column10649 | Column10650 | Column10651 | Column10652 | Column10653 | Column10654 | Column10655 | Column10656 | Column10657 | Column10658 | Column10659 | Column10660 | Column10661 | Column10662 | Column10663 | Column10664 | Column10665 | Column10666 | Column10667 | Column10668 | Column10669 | Column10670 | Column10671 | Column10672 | Column10673 | Column10674 | Column10675 | Column10676 | Column10677 | Column10678 | Column10679 | Column10680 | Column10681 | Column10682 | Column10683 | Column10684 | Column10685 | Column10686 | Column10687 | Column10688 | Column10689 | Column10690 | Column10691 | Column10692 | Column10693 | Column10694 | Column10695 | Column10696 | Column10697 | Column10698 | Column10699 | Column10700 | Column10701 | Column10702 | Column10703 | Column10704 | Column10705 | Column10706 | Column10707 | Column10708 | Column10709 | Column10710 | Column10711 | Column10712 | Column10713 | Column10714 | Column10715 | Column10716 | Column10717 | Column10718 | Column10719 | Column10720 | Column10721 | Column10722 | Column10723 | Column10724 | Column10725 | Column10726 | Column10727 | Column10728 | Column10729 | Column10730 | Column10731 | Column10732 | Column10733 | Column10734 | Column10735 | Column10736 | Column10737 | Column10738 | Column10739 | Column10740 | Column10741 | Column10742 | Column10743 | Column10744 | Column10745 | Column10746 | Column10747 | Column10748 | Column10749 | Column10750 | Column10751 | Column10752 | Column10753 | Column10754 | Column10755 | Column10756 | Column10757 | Column10758 | Column10759 | Column10760 | Column10761 | Column10762 | Column10763 | Column10764 | Column10765 | Column10766 | Column10767 | Column10768 | Column10769 | Column10770 | Column10771 | Column10772 | Column10773 | Column10774 | Column10775 | Column10776 | Column10777 | Column10778 | Column10779 | Column10780 | Column10781 | Column10782 | Column10783 | Column10784 | Column10785 | Column10786 | Column10787 | Column10788 | Column10789 | Column10790 | Column10791 | Column10792 | Column10793 | Column10794 | Column10795 | Column10796 | Column10797 | Column10798 | Column10799 | Column10800 | Column10801 | Column10802 | Column10803 | Column10804 | Column10805 | Column10806 | Column10807 | Column10808 | Column10809 | Column10810 | Column10811 | Column10812 | Column10813 | Column10814 | Column10815 | Column10816 | Column10817 | Column10818 | Column10819 | Column10820 | Column10821 | Column10822 | Column10823 | Column10824 | Column10825 | Column10826 | Column10827 | Column10828 | Column10829 | Column10830 | Column10831 | Column10832 | Column10833 | Column10834 | Column10835 | Column10836 | Column10837 | Column10838 | Column10839 | Column10840 | Column10841 | Column10842 | Column10843 | Column10844 | Column10845 | Column10846 | Column10847 | Column10848 | Column10849 | Column10850 | Column10851 | Column10852 | Column10853 | Column10854 | Column10855 | Column10856 | Column10857 | Column10858 | Column10859 | Column10860 | Column10861 | Column10862 | Column10863 | Column10864 | Column10865 | Column10866 | Column10867 | Column10868 | Column10869 | Column10870 | Column10871 | Column10872 | Column10873 | Column10874 | Column10875 | Column10876 | Column10877 | Column10878 | Column10879 | Column10880 | Column10881 | Column10882 | Column10883 | Column10884 | Column10885 | Column10886 | Column10887 | Column10888 | Column10889 | Column10890 | Column10891 | Column10892 | Column10893 | Column10894 | Column10895 | Column10896 | Column10897 | Column10898 | Column10899 | Column10900 | Column10901 | Column10902 | Column10903 | Column10904 | Column10905 | Column10906 | Column10907 | Column10908 | Column10909 | Column10910 | Column10911 | Column10912 | Column10913 | Column10914 | Column10915 | Column10916 | Column10917 | Column10918 | Column10919 | Column10920 | Column10921 | Column10922 | Column10923 | Column10924 | Column10925 | Column10926 | Column10927 | Column10928 | Column10929 | Column10930 | Column10931 | Column10932 | Column10933 | Column10934 | Column10935 | Column10936 | Column10937 | Column10938 | Column10939 | Column10940 | Column10941 | Column10942 | Column10943 | Column10944 | Column10945 | Column10946 | Column10947 | Column10948 | Column10949 | Column10950 | Column10951 | Column10952 | Column10953 | Column10954 | Column10955 | Column10956 | Column10957 | Column10958 | Column10959 | Column10960 | Column10961 | Column10962 | Column10963 | Column10964 | Column10965 | Column10966 | Column10967 | Column10968 | Column10969 | Column10970 | Column10971 | Column10972 | Column10973 | Column10974 | Column10975 | Column10976 | Column10977 | Column10978 | Column10979 | Column10980 | Column10981 | Column10982 | Column10983 | Column10984 | Column10985 | Column10986 | Column10987 | Column10988 | Column10989 | Column10990 | Column10991 | Column10992 | Column10993 | Column10994 | Column10995 | Column10996 | Column10997 | Column10998 | Column10999 | Column11000 | Column11001 | Column11002 | Column11003 | Column11004 | Column11005 | Column11006 | Column11007 | Column11008 | Column11009 | Column11010 | Column11011 | Column11012 | Column11013 | Column11014 | Column11015 | Column11016 | Column11017 | Column11018 | Column11019 | Column11020 | Column11021 | Column11022 | Column11023 | Column11024 | Column11025 | Column11026 | Column11027 | Column11028 | Column11029 | Column11030 | Column11031 | Column11032 | Column11033 | Column11034 | Column11035 | Column11036 | Column11037 | Column11038 | Column11039 | Column11040 | Column11041 | Column11042 | Column11043 | Column11044 | Column11045 | Column11046 | Column11047 | Column11048 | Column11049 | Column11050 | Column11051 | Column11052 | Column11053 | Column11054 | Column11055 | Column11056 | Column11057 | Column11058 | Column11059 | Column11060 | Column11061 | Column11062 | Column11063 | Column11064 | Column11065 | Column11066 | Column11067 | Column11068 | Column11069 | Column11070 | Column11071 | Column11072 | Column11073 | Column11074 | Column11075 | Column11076 | Column11077 | Column11078 | Column11079 | Column11080 | Column11081 | Column11082 | Column11083 | Column11084 | Column11085 | Column11086 | Column11087 | Column11088 | Column11089 | Column11090 | Column11091 | Column11092 | Column11093 | Column11094 | Column11095 | Column11096 | Column11097 | Column11098 | Column11099 | Column11100 | Column11101 | Column11102 | Column11103 | Column11104 | Column11105 | Column11106 | Column11107 | Column11108 | Column11109 | Column11110 | Column11111 | Column11112 | Column11113 | Column11114 | Column11115 | Column11116 | Column11117 | Column11118 | Column11119 | Column11120 | Column11121 | Column11122 | Column11123 | Column11124 | Column11125 | Column11126 | Column11127 | Column11128 | Column11129 | Column11130 | Column11131 | Column11132 | Column11133 | Column11134 | Column11135 | Column11136 | Column11137 | Column11138 | Column11139 | Column11140 | Column11141 | Column11142 | Column11143 | Column11144 | Column11145 | Column11146 | Column11147 | Column11148 | Column11149 | Column11150 | Column11151 | Column11152 | Column11153 | Column11154 | Column11155 | Column11156 | Column11157 | Column11158 | Column11159 | Column11160 | Column11161 | Column11162 | Column11163 | Column11164 | Column11165 | Column11166 | Column11167 | Column11168 | Column11169 | Column11170 | Column11171 | Column11172 | Column11173 | Column11174 | Column11175 | Column11176 | Column11177 | Column11178 | Column11179 | Column11180 | Column11181 | Column11182 | Column11183 | Column11184 | Column11185 | Column11186 | Column11187 | Column11188 | Column11189 | Column11190 | Column11191 | Column11192 | Column11193 | Column11194 | Column11195 | Column11196 | Column11197 | Column11198 | Column11199 | Column11200 | Column11201 | Column11202 | Column11203 | Column11204 | Column11205 | Column11206 | Column11207 | Column11208 | Column11209 | Column11210 | Column11211 | Column11212 | Column11213 | Column11214 | Column11215 | Column11216 | Column11217 | Column11218 | Column11219 | Column11220 | Column11221 | Column11222 | Column11223 | Column11224 | Column11225 | Column11226 | Column11227 | Column11228 | Column11229 | Column11230 | Column11231 | Column11232 | Column11233 | Column11234 | Column11235 | Column11236 | Column11237 | Column11238 | Column11239 | Column11240 | Column11241 | Column11242 | Column11243 | Column11244 | Column11245 | Column11246 | Column11247 | Column11248 | Column11249 | Column11250 | Column11251 | Column11252 | Column11253 | Column11254 | Column11255 | Column11256 | Column11257 | Column11258 | Column11259 | Column11260 | Column11261 | Column11262 | Column11263 | Column11264 | Column11265 | Column11266 | Column11267 | Column11268 | Column11269 | Column11270 | Column11271 | Column11272 | Column11273 | Column11274 | Column11275 | Column11276 | Column11277 | Column11278 | Column11279 | Column11280 | Column11281 | Column11282 | Column11283 | Column11284 | Column11285 | Column11286 | Column11287 | Column11288 | Column11289 | Column11290 | Column11291 | Column11292 | Column11293 | Column11294 | Column11295 | Column11296 | Column11297 | Column11298 | Column11299 | Column11300 | Column11301 | Column11302 | Column11303 | Column11304 | Column11305 | Column11306 | Column11307 | Column11308 | Column11309 | Column11310 | Column11311 | Column11312 | Column11313 | Column11314 | Column11315 | Column11316 | Column11317 | Column11318 | Column11319 | Column11320 | Column11321 | Column11322 | Column11323 | Column11324 | Column11325 | Column11326 | Column11327 | Column11328 | Column11329 | Column11330 | Column11331 | Column11332 | Column11333 | Column11334 | Column11335 | Column11336 | Column11337 | Column11338 | Column11339 | Column11340 | Column11341 | Column11342 | Column11343 | Column11344 | Column11345 | Column11346 | Column11347 | Column11348 | Column11349 | Column11350 | Column11351 | Column11352 | Column11353 | Column11354 | Column11355 | Column11356 | Column11357 | Column11358 | Column11359 | Column11360 | Column11361 | Column11362 | Column11363 | Column11364 | Column11365 | Column11366 | Column11367 | Column11368 | Column11369 | Column11370 | Column11371 | Column11372 | Column11373 | Column11374 | Column11375 | Column11376 | Column11377 | Column11378 | Column11379 | Column11380 | Column11381 | Column11382 | Column11383 | Column11384 | Column11385 | Column11386 | Column11387 | Column11388 | Column11389 | Column11390 | Column11391 | Column11392 | Column11393 | Column11394 | Column11395 | Column11396 | Column11397 | Column11398 | Column11399 | Column11400 | Column11401 | Column11402 | Column11403 | Column11404 | Column11405 | Column11406 | Column11407 | Column11408 | Column11409 | Column11410 | Column11411 | Column11412 | Column11413 | Column11414 | Column11415 | Column11416 | Column11417 | Column11418 | Column11419 | Column11420 | Column11421 | Column11422 | Column11423 | Column11424 | Column11425 | Column11426 | Column11427 | Column11428 | Column11429 | Column11430 | Column11431 | Column11432 | Column11433 | Column11434 | Column11435 | Column11436 | Column11437 | Column11438 | Column11439 | Column11440 | Column11441 | Column11442 | Column11443 | Column11444 | Column11445 | Column11446 | Column11447 | Column11448 | Column11449 | Column11450 | Column11451 | Column11452 | Column11453 | Column11454 | Column11455 | Column11456 | Column11457 | Column11458 | Column11459 | Column11460 | Column11461 | Column11462 | Column11463 | Column11464 | Column11465 | Column11466 | Column11467 | Column11468 | Column11469 | Column11470 | Column11471 | Column11472 | Column11473 | Column11474 | Column11475 | Column11476 | Column11477 | Column11478 | Column11479 | Column11480 | Column11481 | Column11482 | Column11483 | Column11484 | Column11485 | Column11486 | Column11487 | Column11488 | Column11489 | Column11490 | Column11491 | Column11492 | Column11493 | Column11494 | Column11495 | Column11496 | Column11497 | Column11498 | Column11499 | Column11500 | Column11501 | Column11502 | Column11503 | Column11504 | Column11505 | Column11506 | Column11507 | Column11508 | Column11509 | Column11510 | Column11511 | Column11512 | Column11513 | Column11514 | Column11515 | Column11516 | Column11517 | Column11518 | Column11519 | Column11520 | Column11521 | Column11522 | Column11523 | Column11524 | Column11525 | Column11526 | Column11527 | Column11528 | Column11529 | Column11530 | Column11531 | Column11532 | Column11533 | Column11534 | Column11535 | Column11536 | Column11537 | Column11538 | Column11539 | Column11540 | Column11541 | Column11542 | Column11543 | Column11544 | Column11545 | Column11546 | Column11547 | Column11548 | Column11549 | Column11550 | Column11551 | Column11552 | Column11553 | Column11554 | Column11555 | Column11556 | Column11557 | Column11558 | Column11559 | Column11560 | Column11561 | Column11562 | Column11563 | Column11564 | Column11565 | Column11566 | Column11567 | Column11568 | Column11569 | Column11570 | Column11571 | Column11572 | Column11573 | Column11574 | Column11575 | Column11576 | Column11577 | Column11578 | Column11579 | Column11580 | Column11581 | Column11582 | Column11583 | Column11584 | Column11585 | Column11586 | Column11587 | Column11588 | Column11589 | Column11590 | Column11591 | Column11592 | Column11593 | Column11594 | Column11595 | Column11596 | Column11597 | Column11598 | Column11599 | Column11600 | Column11601 | Column11602 | Column11603 | Column11604 | Column11605 | Column11606 | Column11607 | Column11608 | Column11609 | Column11610 | Column11611 | Column11612 | Column11613 | Column11614 | Column11615 | Column11616 | Column11617 | Column11618 | Column11619 | Column11620 | Column11621 | Column11622 | Column11623 | Column11624 | Column11625 | Column11626 | Column11627 | Column11628 | Column11629 | Column11630 | Column11631 | Column11632 | Column11633 | Column11634 | Column11635 | Column11636 | Column11637 | Column11638 | Column11639 | Column11640 | Column11641 | Column11642 | Column11643 | Column11644 | Column11645 | Column11646 | Column11647 | Column11648 | Column11649 | Column11650 | Column11651 | Column11652 | Column11653 | Column11654 | Column11655 | Column11656 | Column11657 | Column11658 | Column11659 | Column11660 | Column11661 | Column11662 | Column11663 | Column11664 | Column11665 | Column11666 | Column11667 | Column11668 | Column11669 | Column11670 | Column11671 | Column11672 | Column11673 | Column11674 | Column11675 | Column11676 | Column11677 | Column11678 | Column11679 | Column11680 | Column11681 | Column11682 | Column11683 | Column11684 | Column11685 | Column11686 | Column11687 | Column11688 | Column11689 | Column11690 | Column11691 | Column11692 | Column11693 | Column11694 | Column11695 | Column11696 | Column11697 | Column11698 | Column11699 | Column11700 | Column11701 | Column11702 | Column11703 | Column11704 | Column11705 | Column11706 | Column11707 | Column11708 | Column11709 | Column11710 | Column11711 | Column11712 | Column11713 | Column11714 | Column11715 | Column11716 | Column11717 | Column11718 | Column11719 | Column11720 | Column11721 | Column11722 | Column11723 | Column11724 | Column11725 | Column11726 | Column11727 | Column11728 | Column11729 | Column11730 | Column11731 | Column11732 | Column11733 | Column11734 | Column11735 | Column11736 | Column11737 | Column11738 | Column11739 | Column11740 | Column11741 | Column11742 | Column11743 | Column11744 | Column11745 | Column11746 | Column11747 | Column11748 | Column11749 | Column11750 | Column11751 | Column11752 | Column11753 | Column11754 | Column11755 | Column11756 | Column11757 | Column11758 | Column11759 | Column11760 | Column11761 | Column11762 | Column11763 | Column11764 | Column11765 | Column11766 | Column11767 | Column11768 | Column11769 | Column11770 | Column11771 | Column11772 | Column11773 | Column11774 | Column11775 | Column11776 | Column11777 | Column11778 | Column11779 | Column11780 | Column11781 | Column11782 | Column11783 | Column11784 | Column11785 | Column11786 | Column11787 | Column11788 | Column11789 | Column11790 | Column11791 | Column11792 | Column11793 | Column11794 | Column11795 | Column11796 | Column11797 | Column11798 | Column11799 | Column11800 | Column11801 | Column11802 | Column11803 | Column11804 | Column11805 | Column11806 | Column11807 | Column11808 | Column11809 | Column11810 | Column11811 | Column11812 | Column11813 | Column11814 | Column11815 | Column11816 | Column11817 | Column11818 | Column11819 | Column11820 | Column11821 | Column11822 | Column11823 | Column11824 | Column11825 | Column11826 | Column11827 | Column11828 | Column11829 | Column11830 | Column11831 | Column11832 | Column11833 | Column11834 | Column11835 | Column11836 | Column11837 | Column11838 | Column11839 | Column11840 | Column11841 | Column11842 | Column11843 | Column11844 | Column11845 | Column11846 | Column11847 | Column11848 | Column11849 | Column11850 | Column11851 | Column11852 | Column11853 | Column11854 | Column11855 | Column11856 | Column11857 | Column11858 | Column11859 | Column11860 | Column11861 | Column11862 | Column11863 | Column11864 | Column11865 | Column11866 | Column11867 | Column11868 | Column11869 | Column11870 | Column11871 | Column11872 | Column11873 | Column11874 | Column11875 | Column11876 | Column11877 | Column11878 | Column11879 | Column11880 | Column11881 | Column11882 | Column11883 | Column11884 | Column11885 | Column11886 | Column11887 | Column11888 | Column11889 | Column11890 | Column11891 | Column11892 | Column11893 | Column11894 | Column11895 | Column11896 | Column11897 | Column11898 | Column11899 | Column11900 | Column11901 | Column11902 | Column11903 | Column11904 | Column11905 | Column11906 | Column11907 | Column11908 | Column11909 | Column11910 | Column11911 | Column11912 | Column11913 | Column11914 | Column11915 | Column11916 | Column11917 | Column11918 | Column11919 | Column11920 | Column11921 | Column11922 | Column11923 | Column11924 | Column11925 | Column11926 | Column11927 | Column11928 | Column11929 | Column11930 | Column11931 | Column11932 | Column11933 | Column11934 | Column11935 | Column11936 | Column11937 | Column11938 | Column11939 | Column11940 | Column11941 | Column11942 | Column11943 | Column11944 | Column11945 | Column11946 | Column11947 | Column11948 | Column11949 | Column11950 | Column11951 | Column11952 | Column11953 | Column11954 | Column11955 | Column11956 | Column11957 | Column11958 | Column11959 | Column11960 | Column11961 | Column11962 | Column11963 | Column11964 | Column11965 | Column11966 | Column11967 | Column11968 | Column11969 | Column11970 | Column11971 | Column11972 | Column11973 | Column11974 | Column11975 | Column11976 | Column11977 | Column11978 | Column11979 | Column11980 | Column11981 | Column11982 | Column11983 | Column11984 | Column11985 | Column11986 | Column11987 | Column11988 | Column11989 | Column11990 | Column11991 | Column11992 | Column11993 | Column11994 | Column11995 | Column11996 | Column11997 | Column11998 | Column11999 | Column12000 | Column12001 | Column12002 | Column12003 | Column12004 | Column12005 | Column12006 | Column12007 | Column12008 | Column12009 | Column12010 | Column12011 | Column12012 | Column12013 | Column12014 | Column12015 | Column12016 | Column12017 | Column12018 | Column12019 | Column12020 | Column12021 | Column12022 | Column12023 | Column12024 | Column12025 | Column12026 | Column12027 | Column12028 | Column12029 | Column12030 | Column12031 | Column12032 | Column12033 | Column12034 | Column12035 | Column12036 | Column12037 | Column12038 | Column12039 | Column12040 | Column12041 | Column12042 | Column12043 | Column12044 | Column12045 | Column12046 | Column12047 | Column12048 | Column12049 | Column12050 | Column12051 | Column12052 | Column12053 | Column12054 | Column12055 | Column12056 | Column12057 | Column12058 | Column12059 | Column12060 | Column12061 | Column12062 | Column12063 | Column12064 | Column12065 | Column12066 | Column12067 | Column12068 | Column12069 | Column12070 | Column12071 | Column12072 | Column12073 | Column12074 | Column12075 | Column12076 | Column12077 | Column12078 | Column12079 | Column12080 | Column12081 | Column12082 | Column12083 | Column12084 | Column12085 | Column12086 | Column12087 | Column12088 | Column12089 | Column12090 | Column12091 | Column12092 | Column12093 | Column12094 | Column12095 | Column12096 | Column12097 | Column12098 | Column12099 | Column12100 | Column12101 | Column12102 | Column12103 | Column12104 | Column12105 | Column12106 | Column12107 | Column12108 | Column12109 | Column12110 | Column12111 | Column12112 | Column12113 | Column12114 | Column12115 | Column12116 | Column12117 | Column12118 | Column12119 | Column12120 | Column12121 | Column12122 | Column12123 | Column12124 | Column12125 | Column12126 | Column12127 | Column12128 | Column12129 | Column12130 | Column12131 | Column12132 | Column12133 | Column12134 | Column12135 | Column12136 | Column12137 | Column12138 | Column12139 | Column12140 | Column12141 | Column12142 | Column12143 | Column12144 | Column12145 | Column12146 | Column12147 | Column12148 | Column12149 | Column12150 | Column12151 | Column12152 | Column12153 | Column12154 | Column12155 | Column12156 | Column12157 | Column12158 | Column12159 | Column12160 | Column12161 | Column12162 | Column12163 | Column12164 | Column12165 | Column12166 | Column12167 | Column12168 | Column12169 | Column12170 | Column12171 | Column12172 | Column12173 | Column12174 | Column12175 | Column12176 | Column12177 | Column12178 | Column12179 | Column12180 | Column12181 | Column12182 | Column12183 | Column12184 | Column12185 | Column12186 | Column12187 | Column12188 | Column12189 | Column12190 | Column12191 | Column12192 | Column12193 | Column12194 | Column12195 | Column12196 | Column12197 | Column12198 | Column12199 | Column12200 | Column12201 | Column12202 | Column12203 | Column12204 | Column12205 | Column12206 | Column12207 | Column12208 | Column12209 | Column12210 | Column12211 | Column12212 | Column12213 | Column12214 | Column12215 | Column12216 | Column12217 | Column12218 | Column12219 | Column12220 | Column12221 | Column12222 | Column12223 | Column12224 | Column12225 | Column12226 | Column12227 | Column12228 | Column12229 | Column12230 | Column12231 | Column12232 | Column12233 | Column12234 | Column12235 | Column12236 | Column12237 | Column12238 | Column12239 | Column12240 | Column12241 | Column12242 | Column12243 | Column12244 | Column12245 | Column12246 | Column12247 | Column12248 | Column12249 | Column12250 | Column12251 | Column12252 | Column12253 | Column12254 | Column12255 | Column12256 | Column12257 | Column12258 | Column12259 | Column12260 | Column12261 | Column12262 | Column12263 | Column12264 | Column12265 | Column12266 | Column12267 | Column12268 | Column12269 | Column12270 | Column12271 | Column12272 | Column12273 | Column12274 | Column12275 | Column12276 | Column12277 | Column12278 | Column12279 | Column12280 | Column12281 | Column12282 | Column12283 | Column12284 | Column12285 | Column12286 | Column12287 | Column12288 | Column12289 | Column12290 | Column12291 | Column12292 | Column12293 | Column12294 | Column12295 | Column12296 | Column12297 | Column12298 | Column12299 | Column12300 | Column12301 | Column12302 | Column12303 | Column12304 | Column12305 | Column12306 | Column12307 | Column12308 | Column12309 | Column12310 | Column12311 | Column12312 | Column12313 | Column12314 | Column12315 | Column12316 | Column12317 | Column12318 | Column12319 | Column12320 | Column12321 | Column12322 | Column12323 | Column12324 | Column12325 | Column12326 | Column12327 | Column12328 | Column12329 | Column12330 | Column12331 | Column12332 | Column12333 | Column12334 | Column12335 | Column12336 | Column12337 | Column12338 | Column12339 | Column12340 | Column12341 | Column12342 | Column12343 | Column12344 | Column12345 | Column12346 | Column12347 | Column12348 | Column12349 | Column12350 | Column12351 | Column12352 | Column12353 | Column12354 | Column12355 | Column12356 | Column12357 | Column12358 | Column12359 | Column12360 | Column12361 | Column12362 | Column12363 | Column12364 | Column12365 | Column12366 | Column12367 | Column12368 | Column12369 | Column12370 | Column12371 | Column12372 | Column12373 | Column12374 | Column12375 | Column12376 | Column12377 | Column12378 | Column12379 | Column12380 | Column12381 | Column12382 | Column12383 | Column12384 | Column12385 | Column12386 | Column12387 | Column12388 | Column12389 | Column12390 | Column12391 | Column12392 | Column12393 | Column12394 | Column12395 | Column12396 | Column12397 | Column12398 | Column12399 | Column12400 | Column12401 | Column12402 | Column12403 | Column12404 | Column12405 | Column12406 | Column12407 | Column12408 | Column12409 | Column12410 | Column12411 | Column12412 | Column12413 | Column12414 | Column12415 | Column12416 | Column12417 | Column12418 | Column12419 | Column12420 | Column12421 | Column12422 | Column12423 | Column12424 | Column12425 | Column12426 | Column12427 | Column12428 | Column12429 | Column12430 | Column12431 | Column12432 | Column12433 | Column12434 | Column12435 | Column12436 | Column12437 | Column12438 | Column12439 | Column12440 | Column12441 | Column12442 | Column12443 | Column12444 | Column12445 | Column12446 | Column12447 | Column12448 | Column12449 | Column12450 | Column12451 | Column12452 | Column12453 | Column12454 | Column12455 | Column12456 | Column12457 | Column12458 | Column12459 | Column12460 | Column12461 | Column12462 | Column12463 | Column12464 | Column12465 | Column12466 | Column12467 | Column12468 | Column12469 | Column12470 | Column12471 | Column12472 | Column12473 | Column12474 | Column12475 | Column12476 | Column12477 | Column12478 | Column12479 | Column12480 | Column12481 | Column12482 | Column12483 | Column12484 | Column12485 | Column12486 | Column12487 | Column12488 | Column12489 | Column12490 | Column12491 | Column12492 | Column12493 | Column12494 | Column12495 | Column12496 | Column12497 | Column12498 | Column12499 | Column12500 | Column12501 | Column12502 | Column12503 | Column12504 | Column12505 | Column12506 | Column12507 | Column12508 | Column12509 | Column12510 | Column12511 | Column12512 | Column12513 | Column12514 | Column12515 | Column12516 | Column12517 | Column12518 | Column12519 | Column12520 | Column12521 | Column12522 | Column12523 | Column12524 | Column12525 | Column12526 | Column12527 | Column12528 | Column12529 | Column12530 | Column12531 | Column12532 | Column12533 | Column12534 | Column12535 | Column12536 | Column12537 | Column12538 | Column12539 | Column12540 | Column12541 | Column12542 | Column12543 | Column12544 | Column12545 | Column12546 | Column12547 | Column12548 | Column12549 | Column12550 | Column12551 | Column12552 | Column12553 | Column12554 | Column12555 | Column12556 | Column12557 | Column12558 | Column12559 | Column12560 | Column12561 | Column12562 | Column12563 | Column12564 | Column12565 | Column12566 | Column12567 | Column12568 | Column12569 | Column12570 | Column12571 | Column12572 | Column12573 | Column12574 | Column12575 | Column12576 | Column12577 | Column12578 | Column12579 | Column12580 | Column12581 | Column12582 | Column12583 | Column12584 | Column12585 | Column12586 | Column12587 | Column12588 | Column12589 | Column12590 | Column12591 | Column12592 | Column12593 | Column12594 | Column12595 | Column12596 | Column12597 | Column12598 | Column12599 | Column12600 | Column12601 | Column12602 | Column12603 | Column12604 | Column12605 | Column12606 | Column12607 | Column12608 | Column12609 | Column12610 | Column12611 | Column12612 | Column12613 | Column12614 | Column12615 | Column12616 | Column12617 | Column12618 | Column12619 | Column12620 | Column12621 | Column12622 | Column12623 | Column12624 | Column12625 | Column12626 | Column12627 | Column12628 | Column12629 | Column12630 | Column12631 | Column12632 | Column12633 | Column12634 | Column12635 | Column12636 | Column12637 | Column12638 | Column12639 | Column12640 | Column12641 | Column12642 | Column12643 | Column12644 | Column12645 | Column12646 | Column12647 | Column12648 | Column12649 | Column12650 | Column12651 | Column12652 | Column12653 | Column12654 | Column12655 | Column12656 | Column12657 | Column12658 | Column12659 | Column12660 | Column12661 | Column12662 | Column12663 | Column12664 | Column12665 | Column12666 | Column12667 | Column12668 | Column12669 | Column12670 | Column12671 | Column12672 | Column12673 | Column12674 | Column12675 | Column12676 | Column12677 | Column12678 | Column12679 | Column12680 | Column12681 | Column12682 | Column12683 | Column12684 | Column12685 | Column12686 | Column12687 | Column12688 | Column12689 | Column12690 | Column12691 | Column12692 | Column12693 | Column12694 | Column12695 | Column12696 | Column12697 | Column12698 | Column12699 | Column12700 | Column12701 | Column12702 | Column12703 | Column12704 | Column12705 | Column12706 | Column12707 | Column12708 | Column12709 | Column12710 | Column12711 | Column12712 | Column12713 | Column12714 | Column12715 | Column12716 | Column12717 | Column12718 | Column12719 | Column12720 | Column12721 | Column12722 | Column12723 | Column12724 | Column12725 | Column12726 | Column12727 | Column12728 | Column12729 | Column12730 | Column12731 | Column12732 | Column12733 | Column12734 | Column12735 | Column12736 | Column12737 | Column12738 | Column12739 | Column12740 | Column12741 | Column12742 | Column12743 | Column12744 | Column12745 | Column12746 | Column12747 | Column12748 | Column12749 | Column12750 | Column12751 | Column12752 | Column12753 | Column12754 | Column12755 | Column12756 | Column12757 | Column12758 | Column12759 | Column12760 | Column12761 | Column12762 | Column12763 | Column12764 | Column12765 | Column12766 | Column12767 | Column12768 | Column12769 | Column12770 | Column12771 | Column12772 | Column12773 | Column12774 | Column12775 | Column12776 | Column12777 | Column12778 | Column12779 | Column12780 | Column12781 | Column12782 | Column12783 | Column12784 | Column12785 | Column12786 | Column12787 | Column12788 | Column12789 | Column12790 | Column12791 | Column12792 | Column12793 | Column12794 | Column12795 | Column12796 | Column12797 | Column12798 | Column12799 | Column12800 | Column12801 | Column12802 | Column12803 | Column12804 | Column12805 | Column12806 | Column12807 | Column12808 | Column12809 | Column12810 | Column12811 | Column12812 | Column12813 | Column12814 | Column12815 | Column12816 | Column12817 | Column12818 | Column12819 | Column12820 | Column12821 | Column12822 | Column12823 | Column12824 | Column12825 | Column12826 | Column12827 | Column12828 | Column12829 | Column12830 | Column12831 | Column12832 | Column12833 | Column12834 | Column12835 | Column12836 | Column12837 | Column12838 | Column12839 | Column12840 | Column12841 | Column12842 | Column12843 | Column12844 | Column12845 | Column12846 | Column12847 | Column12848 | Column12849 | Column12850 | Column12851 | Column12852 | Column12853 | Column12854 | Column12855 | Column12856 | Column12857 | Column12858 | Column12859 | Column12860 | Column12861 | Column12862 | Column12863 | Column12864 | Column12865 | Column12866 | Column12867 | Column12868 | Column12869 | Column12870 | Column12871 | Column12872 | Column12873 | Column12874 | Column12875 | Column12876 | Column12877 | Column12878 | Column12879 | Column12880 | Column12881 | Column12882 | Column12883 | Column12884 | Column12885 | Column12886 | Column12887 | Column12888 | Column12889 | Column12890 | Column12891 | Column12892 | Column12893 | Column12894 | Column12895 | Column12896 | Column12897 | Column12898 | Column12899 | Column12900 | Column12901 | Column12902 | Column12903 | Column12904 | Column12905 | Column12906 | Column12907 | Column12908 | Column12909 | Column12910 | Column12911 | Column12912 | Column12913 | Column12914 | Column12915 | Column12916 | Column12917 | Column12918 | Column12919 | Column12920 | Column12921 | Column12922 | Column12923 | Column12924 | Column12925 | Column12926 | Column12927 | Column12928 | Column12929 | Column12930 | Column12931 | Column12932 | Column12933 | Column12934 | Column12935 | Column12936 | Column12937 | Column12938 | Column12939 | Column12940 | Column12941 | Column12942 | Column12943 | Column12944 | Column12945 | Column12946 | Column12947 | Column12948 | Column12949 | Column12950 | Column12951 | Column12952 | Column12953 | Column12954 | Column12955 | Column12956 | Column12957 | Column12958 | Column12959 | Column12960 | Column12961 | Column12962 | Column12963 | Column12964 | Column12965 | Column12966 | Column12967 | Column12968 | Column12969 | Column12970 | Column12971 | Column12972 | Column12973 | Column12974 | Column12975 | Column12976 | Column12977 | Column12978 | Column12979 | Column12980 | Column12981 | Column12982 | Column12983 | Column12984 | Column12985 | Column12986 | Column12987 | Column12988 | Column12989 | Column12990 | Column12991 | Column12992 | Column12993 | Column12994 | Column12995 | Column12996 | Column12997 | Column12998 | Column12999 | Column13000 | Column13001 | Column13002 | Column13003 | Column13004 | Column13005 | Column13006 | Column13007 | Column13008 | Column13009 | Column13010 | Column13011 | Column13012 | Column13013 | Column13014 | Column13015 | Column13016 | Column13017 | Column13018 | Column13019 | Column13020 | Column13021 | Column13022 | Column13023 | Column13024 | Column13025 | Column13026 | Column13027 | Column13028 | Column13029 | Column13030 | Column13031 | Column13032 | Column13033 | Column13034 | Column13035 | Column13036 | Column13037 | Column13038 | Column13039 | Column13040 | Column13041 | Column13042 | Column13043 | Column13044 | Column13045 | Column13046 | Column13047 | Column13048 | Column13049 | Column13050 | Column13051 | Column13052 | Column13053 | Column13054 | Column13055 | Column13056 | Column13057 | Column13058 | Column13059 | Column13060 | Column13061 | Column13062 | Column13063 | Column13064 | Column13065 | Column13066 | Column13067 | Column13068 | Column13069 | Column13070 | Column13071 | Column13072 | Column13073 | Column13074 | Column13075 | Column13076 | Column13077 | Column13078 | Column13079 | Column13080 | Column13081 | Column13082 | Column13083 | Column13084 | Column13085 | Column13086 | Column13087 | Column13088 | Column13089 | Column13090 | Column13091 | Column13092 | Column13093 | Column13094 | Column13095 | Column13096 | Column13097 | Column13098 | Column13099 | Column13100 | Column13101 | Column13102 | Column13103 | Column13104 | Column13105 | Column13106 | Column13107 | Column13108 | Column13109 | Column13110 | Column13111 | Column13112 | Column13113 | Column13114 | Column13115 | Column13116 | Column13117 | Column13118 | Column13119 | Column13120 | Column13121 | Column13122 | Column13123 | Column13124 | Column13125 | Column13126 | Column13127 | Column13128 | Column13129 | Column13130 | Column13131 | Column13132 | Column13133 | Column13134 | Column13135 | Column13136 | Column13137 | Column13138 | Column13139 | Column13140 | Column13141 | Column13142 | Column13143 | Column13144 | Column13145 | Column13146 | Column13147 | Column13148 | Column13149 | Column13150 | Column13151 | Column13152 | Column13153 | Column13154 | Column13155 | Column13156 | Column13157 | Column13158 | Column13159 | Column13160 | Column13161 | Column13162 | Column13163 | Column13164 | Column13165 | Column13166 | Column13167 | Column13168 | Column13169 | Column13170 | Column13171 | Column13172 | Column13173 | Column13174 | Column13175 | Column13176 | Column13177 | Column13178 | Column13179 | Column13180 | Column13181 | Column13182 | Column13183 | Column13184 | Column13185 | Column13186 | Column13187 | Column13188 | Column13189 | Column13190 | Column13191 | Column13192 | Column13193 | Column13194 | Column13195 | Column13196 | Column13197 | Column13198 | Column13199 | Column13200 | Column13201 | Column13202 | Column13203 | Column13204 | Column13205 | Column13206 | Column13207 | Column13208 | Column13209 | Column13210 | Column13211 | Column13212 | Column13213 | Column13214 | Column13215 | Column13216 | Column13217 | Column13218 | Column13219 | Column13220 | Column13221 | Column13222 | Column13223 | Column13224 | Column13225 | Column13226 | Column13227 | Column13228 | Column13229 | Column13230 | Column13231 | Column13232 | Column13233 | Column13234 | Column13235 | Column13236 | Column13237 | Column13238 | Column13239 | Column13240 | Column13241 | Column13242 | Column13243 | Column13244 | Column13245 | Column13246 | Column13247 | Column13248 | Column13249 | Column13250 | Column13251 | Column13252 | Column13253 | Column13254 | Column13255 | Column13256 | Column13257 | Column13258 | Column13259 | Column13260 | Column13261 | Column13262 | Column13263 | Column13264 | Column13265 | Column13266 | Column13267 | Column13268 | Column13269 | Column13270 | Column13271 | Column13272 | Column13273 | Column13274 | Column13275 | Column13276 | Column13277 | Column13278 | Column13279 | Column13280 | Column13281 | Column13282 | Column13283 | Column13284 | Column13285 | Column13286 | Column13287 | Column13288 | Column13289 | Column13290 | Column13291 | Column13292 | Column13293 | Column13294 | Column13295 | Column13296 | Column13297 | Column13298 | Column13299 | Column13300 | Column13301 | Column13302 | Column13303 | Column13304 | Column13305 | Column13306 | Column13307 | Column13308 | Column13309 | Column13310 | Column13311 | Column13312 | Column13313 | Column13314 | Column13315 | Column13316 | Column13317 | Column13318 | Column13319 | Column13320 | Column13321 | Column13322 | Column13323 | Column13324 | Column13325 | Column13326 | Column13327 | Column13328 | Column13329 | Column13330 | Column13331 | Column13332 | Column13333 | Column13334 | Column13335 | Column13336 | Column13337 | Column13338 | Column13339 | Column13340 | Column13341 | Column13342 | Column13343 | Column13344 | Column13345 | Column13346 | Column13347 | Column13348 | Column13349 | Column13350 | Column13351 | Column13352 | Column13353 | Column13354 | Column13355 | Column13356 | Column13357 | Column13358 | Column13359 | Column13360 | Column13361 | Column13362 | Column13363 | Column13364 | Column13365 | Column13366 | Column13367 | Column13368 | Column13369 | Column13370 | Column13371 | Column13372 | Column13373 | Column13374 | Column13375 | Column13376 | Column13377 | Column13378 | Column13379 | Column13380 | Column13381 | Column13382 | Column13383 | Column13384 | Column13385 | Column13386 | Column13387 | Column13388 | Column13389 | Column13390 | Column13391 | Column13392 | Column13393 | Column13394 | Column13395 | Column13396 | Column13397 | Column13398 | Column13399 | Column13400 | Column13401 | Column13402 | Column13403 | Column13404 | Column13405 | Column13406 | Column13407 | Column13408 | Column13409 | Column13410 | Column13411 | Column13412 | Column13413 | Column13414 | Column13415 | Column13416 | Column13417 | Column13418 | Column13419 | Column13420 | Column13421 | Column13422 | Column13423 | Column13424 | Column13425 | Column13426 | Column13427 | Column13428 | Column13429 | Column13430 | Column13431 | Column13432 | Column13433 | Column13434 | Column13435 | Column13436 | Column13437 | Column13438 | Column13439 | Column13440 | Column13441 | Column13442 | Column13443 | Column13444 | Column13445 | Column13446 | Column13447 | Column13448 | Column13449 | Column13450 | Column13451 | Column13452 | Column13453 | Column13454 | Column13455 | Column13456 | Column13457 | Column13458 | Column13459 | Column13460 | Column13461 | Column13462 | Column13463 | Column13464 | Column13465 | Column13466 | Column13467 | Column13468 | Column13469 | Column13470 | Column13471 | Column13472 | Column13473 | Column13474 | Column13475 | Column13476 | Column13477 | Column13478 | Column13479 | Column13480 | Column13481 | Column13482 | Column13483 | Column13484 | Column13485 | Column13486 | Column13487 | Column13488 | Column13489 | Column13490 | Column13491 | Column13492 | Column13493 | Column13494 | Column13495 | Column13496 | Column13497 | Column13498 | Column13499 | Column13500 | Column13501 | Column13502 | Column13503 | Column13504 | Column13505 | Column13506 | Column13507 | Column13508 | Column13509 | Column13510 | Column13511 | Column13512 | Column13513 | Column13514 | Column13515 | Column13516 | Column13517 | Column13518 | Column13519 | Column13520 | Column13521 | Column13522 | Column13523 | Column13524 | Column13525 | Column13526 | Column13527 | Column13528 | Column13529 | Column13530 | Column13531 | Column13532 | Column13533 | Column13534 | Column13535 | Column13536 | Column13537 | Column13538 | Column13539 | Column13540 | Column13541 | Column13542 | Column13543 | Column13544 | Column13545 | Column13546 | Column13547 | Column13548 | Column13549 | Column13550 | Column13551 | Column13552 | Column13553 | Column13554 | Column13555 | Column13556 | Column13557 | Column13558 | Column13559 | Column13560 | Column13561 | Column13562 | Column13563 | Column13564 | Column13565 | Column13566 | Column13567 | Column13568 | Column13569 | Column13570 | Column13571 | Column13572 | Column13573 | Column13574 | Column13575 | Column13576 | Column13577 | Column13578 | Column13579 | Column13580 | Column13581 | Column13582 | Column13583 | Column13584 | Column13585 | Column13586 | Column13587 | Column13588 | Column13589 | Column13590 | Column13591 | Column13592 | Column13593 | Column13594 | Column13595 | Column13596 | Column13597 | Column13598 | Column13599 | Column13600 | Column13601 | Column13602 | Column13603 | Column13604 | Column13605 | Column13606 | Column13607 | Column13608 | Column13609 | Column13610 | Column13611 | Column13612 | Column13613 | Column13614 | Column13615 | Column13616 | Column13617 | Column13618 | Column13619 | Column13620 | Column13621 | Column13622 | Column13623 | Column13624 | Column13625 | Column13626 | Column13627 | Column13628 | Column13629 | Column13630 | Column13631 | Column13632 | Column13633 | Column13634 | Column13635 | Column13636 | Column13637 | Column13638 | Column13639 | Column13640 | Column13641 | Column13642 | Column13643 | Column13644 | Column13645 | Column13646 | Column13647 | Column13648 | Column13649 | Column13650 | Column13651 | Column13652 | Column13653 | Column13654 | Column13655 | Column13656 | Column13657 | Column13658 | Column13659 | Column13660 | Column13661 | Column13662 | Column13663 | Column13664 | Column13665 | Column13666 | Column13667 | Column13668 | Column13669 | Column13670 | Column13671 | Column13672 | Column13673 | Column13674 | Column13675 | Column13676 | Column13677 | Column13678 | Column13679 | Column13680 | Column13681 | Column13682 | Column13683 | Column13684 | Column13685 | Column13686 | Column13687 | Column13688 | Column13689 | Column13690 | Column13691 | Column13692 | Column13693 | Column13694 | Column13695 | Column13696 | Column13697 | Column13698 | Column13699 | Column13700 | Column13701 | Column13702 | Column13703 | Column13704 | Column13705 | Column13706 | Column13707 | Column13708 | Column13709 | Column13710 | Column13711 | Column13712 | Column13713 | Column13714 | Column13715 | Column13716 | Column13717 | Column13718 | Column13719 | Column13720 | Column13721 | Column13722 | Column13723 | Column13724 | Column13725 | Column13726 | Column13727 | Column13728 | Column13729 | Column13730 | Column13731 | Column13732 | Column13733 | Column13734 | Column13735 | Column13736 | Column13737 | Column13738 | Column13739 | Column13740 | Column13741 | Column13742 | Column13743 | Column13744 | Column13745 | Column13746 | Column13747 | Column13748 | Column13749 | Column13750 | Column13751 | Column13752 | Column13753 | Column13754 | Column13755 | Column13756 | Column13757 | Column13758 | Column13759 | Column13760 | Column13761 | Column13762 | Column13763 | Column13764 | Column13765 | Column13766 | Column13767 | Column13768 | Column13769 | Column13770 | Column13771 | Column13772 | Column13773 | Column13774 | Column13775 | Column13776 | Column13777 | Column13778 | Column13779 | Column13780 | Column13781 | Column13782 | Column13783 | Column13784 | Column13785 | Column13786 | Column13787 | Column13788 | Column13789 | Column13790 | Column13791 | Column13792 | Column13793 | Column13794 | Column13795 | Column13796 | Column13797 | Column13798 | Column13799 | Column13800 | Column13801 | Column13802 | Column13803 | Column13804 | Column13805 | Column13806 | Column13807 | Column13808 | Column13809 | Column13810 | Column13811 | Column13812 | Column13813 | Column13814 | Column13815 | Column13816 | Column13817 | Column13818 | Column13819 | Column13820 | Column13821 | Column13822 | Column13823 | Column13824 | Column13825 | Column13826 | Column13827 | Column13828 | Column13829 | Column13830 | Column13831 | Column13832 | Column13833 | Column13834 | Column13835 | Column13836 | Column13837 | Column13838 | Column13839 | Column13840 | Column13841 | Column13842 | Column13843 | Column13844 | Column13845 | Column13846 | Column13847 | Column13848 | Column13849 | Column13850 | Column13851 | Column13852 | Column13853 | Column13854 | Column13855 | Column13856 | Column13857 | Column13858 | Column13859 | Column13860 | Column13861 | Column13862 | Column13863 | Column13864 | Column13865 | Column13866 | Column13867 | Column13868 | Column13869 | Column13870 | Column13871 | Column13872 | Column13873 | Column13874 | Column13875 | Column13876 | Column13877 | Column13878 | Column13879 | Column13880 | Column13881 | Column13882 | Column13883 | Column13884 | Column13885 | Column13886 | Column13887 | Column13888 | Column13889 | Column13890 | Column13891 | Column13892 | Column13893 | Column13894 | Column13895 | Column13896 | Column13897 | Column13898 | Column13899 | Column13900 | Column13901 | Column13902 | Column13903 | Column13904 | Column13905 | Column13906 | Column13907 | Column13908 | Column13909 | Column13910 | Column13911 | Column13912 | Column13913 | Column13914 | Column13915 | Column13916 | Column13917 | Column13918 | Column13919 | Column13920 | Column13921 | Column13922 | Column13923 | Column13924 | Column13925 | Column13926 | Column13927 | Column13928 | Column13929 | Column13930 | Column13931 | Column13932 | Column13933 | Column13934 | Column13935 | Column13936 | Column13937 | Column13938 | Column13939 | Column13940 | Column13941 | Column13942 | Column13943 | Column13944 | Column13945 | Column13946 | Column13947 | Column13948 | Column13949 | Column13950 | Column13951 | Column13952 | Column13953 | Column13954 | Column13955 | Column13956 | Column13957 | Column13958 | Column13959 | Column13960 | Column13961 | Column13962 | Column13963 | Column13964 | Column13965 | Column13966 | Column13967 | Column13968 | Column13969 | Column13970 | Column13971 | Column13972 | Column13973 | Column13974 | Column13975 | Column13976 | Column13977 | Column13978 | Column13979 | Column13980 | Column13981 | Column13982 | Column13983 | Column13984 | Column13985 | Column13986 | Column13987 | Column13988 | Column13989 | Column13990 | Column13991 | Column13992 | Column13993 | Column13994 | Column13995 | Column13996 | Column13997 | Column13998 | Column13999 | Column14000 | Column14001 | Column14002 | Column14003 | Column14004 | Column14005 | Column14006 | Column14007 | Column14008 | Column14009 | Column14010 | Column14011 | Column14012 | Column14013 | Column14014 | Column14015 | Column14016 | Column14017 | Column14018 | Column14019 | Column14020 | Column14021 | Column14022 | Column14023 | Column14024 | Column14025 | Column14026 | Column14027 | Column14028 | Column14029 | Column14030 | Column14031 | Column14032 | Column14033 | Column14034 | Column14035 | Column14036 | Column14037 | Column14038 | Column14039 | Column14040 | Column14041 | Column14042 | Column14043 | Column14044 | Column14045 | Column14046 | Column14047 | Column14048 | Column14049 | Column14050 | Column14051 | Column14052 | Column14053 | Column14054 | Column14055 | Column14056 | Column14057 | Column14058 | Column14059 | Column14060 | Column14061 | Column14062 | Column14063 | Column14064 | Column14065 | Column14066 | Column14067 | Column14068 | Column14069 | Column14070 | Column14071 | Column14072 | Column14073 | Column14074 | Column14075 | Column14076 | Column14077 | Column14078 | Column14079 | Column14080 | Column14081 | Column14082 | Column14083 | Column14084 | Column14085 | Column14086 | Column14087 | Column14088 | Column14089 | Column14090 | Column14091 | Column14092 | Column14093 | Column14094 | Column14095 | Column14096 | Column14097 | Column14098 | Column14099 | Column14100 | Column14101 | Column14102 | Column14103 | Column14104 | Column14105 | Column14106 | Column14107 | Column14108 | Column14109 | Column14110 | Column14111 | Column14112 | Column14113 | Column14114 | Column14115 | Column14116 | Column14117 | Column14118 | Column14119 | Column14120 | Column14121 | Column14122 | Column14123 | Column14124 | Column14125 | Column14126 | Column14127 | Column14128 | Column14129 | Column14130 | Column14131 | Column14132 | Column14133 | Column14134 | Column14135 | Column14136 | Column14137 | Column14138 | Column14139 | Column14140 | Column14141 | Column14142 | Column14143 | Column14144 | Column14145 | Column14146 | Column14147 | Column14148 | Column14149 | Column14150 | Column14151 | Column14152 | Column14153 | Column14154 | Column14155 | Column14156 | Column14157 | Column14158 | Column14159 | Column14160 | Column14161 | Column14162 | Column14163 | Column14164 | Column14165 | Column14166 | Column14167 | Column14168 | Column14169 | Column14170 | Column14171 | Column14172 | Column14173 | Column14174 | Column14175 | Column14176 | Column14177 | Column14178 | Column14179 | Column14180 | Column14181 | Column14182 | Column14183 | Column14184 | Column14185 | Column14186 | Column14187 | Column14188 | Column14189 | Column14190 | Column14191 | Column14192 | Column14193 | Column14194 | Column14195 | Column14196 | Column14197 | Column14198 | Column14199 | Column14200 | Column14201 | Column14202 | Column14203 | Column14204 | Column14205 | Column14206 | Column14207 | Column14208 | Column14209 | Column14210 | Column14211 | Column14212 | Column14213 | Column14214 | Column14215 | Column14216 | Column14217 | Column14218 | Column14219 | Column14220 | Column14221 | Column14222 | Column14223 | Column14224 | Column14225 | Column14226 | Column14227 | Column14228 | Column14229 | Column14230 | Column14231 | Column14232 | Column14233 | Column14234 | Column14235 | Column14236 | Column14237 | Column14238 | Column14239 | Column14240 | Column14241 | Column14242 | Column14243 | Column14244 | Column14245 | Column14246 | Column14247 | Column14248 | Column14249 | Column14250 | Column14251 | Column14252 | Column14253 | Column14254 | Column14255 | Column14256 | Column14257 | Column14258 | Column14259 | Column14260 | Column14261 | Column14262 | Column14263 | Column14264 | Column14265 | Column14266 | Column14267 | Column14268 | Column14269 | Column14270 | Column14271 | Column14272 | Column14273 | Column14274 | Column14275 | Column14276 | Column14277 | Column14278 | Column14279 | Column14280 | Column14281 | Column14282 | Column14283 | Column14284 | Column14285 | Column14286 | Column14287 | Column14288 | Column14289 | Column14290 | Column14291 | Column14292 | Column14293 | Column14294 | Column14295 | Column14296 | Column14297 | Column14298 | Column14299 | Column14300 | Column14301 | Column14302 | Column14303 | Column14304 | Column14305 | Column14306 | Column14307 | Column14308 | Column14309 | Column14310 | Column14311 | Column14312 | Column14313 | Column14314 | Column14315 | Column14316 | Column14317 | Column14318 | Column14319 | Column14320 | Column14321 | Column14322 | Column14323 | Column14324 | Column14325 | Column14326 | Column14327 | Column14328 | Column14329 | Column14330 | Column14331 | Column14332 | Column14333 | Column14334 | Column14335 | Column14336 | Column14337 | Column14338 | Column14339 | Column14340 | Column14341 | Column14342 | Column14343 | Column14344 | Column14345 | Column14346 | Column14347 | Column14348 | Column14349 | Column14350 | Column14351 | Column14352 | Column14353 | Column14354 | Column14355 | Column14356 | Column14357 | Column14358 | Column14359 | Column14360 | Column14361 | Column14362 | Column14363 | Column14364 | Column14365 | Column14366 | Column14367 | Column14368 | Column14369 | Column14370 | Column14371 | Column14372 | Column14373 | Column14374 | Column14375 | Column14376 | Column14377 | Column14378 | Column14379 | Column14380 | Column14381 | Column14382 | Column14383 | Column14384 | Column14385 | Column14386 | Column14387 | Column14388 | Column14389 | Column14390 | Column14391 | Column14392 | Column14393 | Column14394 | Column14395 | Column14396 | Column14397 | Column14398 | Column14399 | Column14400 | Column14401 | Column14402 | Column14403 | Column14404 | Column14405 | Column14406 | Column14407 | Column14408 | Column14409 | Column14410 | Column14411 | Column14412 | Column14413 | Column14414 | Column14415 | Column14416 | Column14417 | Column14418 | Column14419 | Column14420 | Column14421 | Column14422 | Column14423 | Column14424 | Column14425 | Column14426 | Column14427 | Column14428 | Column14429 | Column14430 | Column14431 | Column14432 | Column14433 | Column14434 | Column14435 | Column14436 | Column14437 | Column14438 | Column14439 | Column14440 | Column14441 | Column14442 | Column14443 | Column14444 | Column14445 | Column14446 | Column14447 | Column14448 | Column14449 | Column14450 | Column14451 | Column14452 | Column14453 | Column14454 | Column14455 | Column14456 | Column14457 | Column14458 | Column14459 | Column14460 | Column14461 | Column14462 | Column14463 | Column14464 | Column14465 | Column14466 | Column14467 | Column14468 | Column14469 | Column14470 | Column14471 | Column14472 | Column14473 | Column14474 | Column14475 | Column14476 | Column14477 | Column14478 | Column14479 | Column14480 | Column14481 | Column14482 | Column14483 | Column14484 | Column14485 | Column14486 | Column14487 | Column14488 | Column14489 | Column14490 | Column14491 | Column14492 | Column14493 | Column14494 | Column14495 | Column14496 | Column14497 | Column14498 | Column14499 | Column14500 | Column14501 | Column14502 | Column14503 | Column14504 | Column14505 | Column14506 | Column14507 | Column14508 | Column14509 | Column14510 | Column14511 | Column14512 | Column14513 | Column14514 | Column14515 | Column14516 | Column14517 | Column14518 | Column14519 | Column14520 | Column14521 | Column14522 | Column14523 | Column14524 | Column14525 | Column14526 | Column14527 | Column14528 | Column14529 | Column14530 | Column14531 | Column14532 | Column14533 | Column14534 | Column14535 | Column14536 | Column14537 | Column14538 | Column14539 | Column14540 | Column14541 | Column14542 | Column14543 | Column14544 | Column14545 | Column14546 | Column14547 | Column14548 | Column14549 | Column14550 | Column14551 | Column14552 | Column14553 | Column14554 | Column14555 | Column14556 | Column14557 | Column14558 | Column14559 | Column14560 | Column14561 | Column14562 | Column14563 | Column14564 | Column14565 | Column14566 | Column14567 | Column14568 | Column14569 | Column14570 | Column14571 | Column14572 | Column14573 | Column14574 | Column14575 | Column14576 | Column14577 | Column14578 | Column14579 | Column14580 | Column14581 | Column14582 | Column14583 | Column14584 | Column14585 | Column14586 | Column14587 | Column14588 | Column14589 | Column14590 | Column14591 | Column14592 | Column14593 | Column14594 | Column14595 | Column14596 | Column14597 | Column14598 | Column14599 | Column14600 | Column14601 | Column14602 | Column14603 | Column14604 | Column14605 | Column14606 | Column14607 | Column14608 | Column14609 | Column14610 | Column14611 | Column14612 | Column14613 | Column14614 | Column14615 | Column14616 | Column14617 | Column14618 | Column14619 | Column14620 | Column14621 | Column14622 | Column14623 | Column14624 | Column14625 | Column14626 | Column14627 | Column14628 | Column14629 | Column14630 | Column14631 | Column14632 | Column14633 | Column14634 | Column14635 | Column14636 | Column14637 | Column14638 | Column14639 | Column14640 | Column14641 | Column14642 | Column14643 | Column14644 | Column14645 | Column14646 | Column14647 | Column14648 | Column14649 | Column14650 | Column14651 | Column14652 | Column14653 | Column14654 | Column14655 | Column14656 | Column14657 | Column14658 | Column14659 | Column14660 | Column14661 | Column14662 | Column14663 | Column14664 | Column14665 | Column14666 | Column14667 | Column14668 | Column14669 | Column14670 | Column14671 | Column14672 | Column14673 | Column14674 | Column14675 | Column14676 | Column14677 | Column14678 | Column14679 | Column14680 | Column14681 | Column14682 | Column14683 | Column14684 | Column14685 | Column14686 | Column14687 | Column14688 | Column14689 | Column14690 | Column14691 | Column14692 | Column14693 | Column14694 | Column14695 | Column14696 | Column14697 | Column14698 | Column14699 | Column14700 | Column14701 | Column14702 | Column14703 | Column14704 | Column14705 | Column14706 | Column14707 | Column14708 | Column14709 | Column14710 | Column14711 | Column14712 | Column14713 | Column14714 | Column14715 | Column14716 | Column14717 | Column14718 | Column14719 | Column14720 | Column14721 | Column14722 | Column14723 | Column14724 | Column14725 | Column14726 | Column14727 | Column14728 | Column14729 | Column14730 | Column14731 | Column14732 | Column14733 | Column14734 | Column14735 | Column14736 | Column14737 | Column14738 | Column14739 | Column14740 | Column14741 | Column14742 | Column14743 | Column14744 | Column14745 | Column14746 | Column14747 | Column14748 | Column14749 | Column14750 | Column14751 | Column14752 | Column14753 | Column14754 | Column14755 | Column14756 | Column14757 | Column14758 | Column14759 | Column14760 | Column14761 | Column14762 | Column14763 | Column14764 | Column14765 | Column14766 | Column14767 | Column14768 | Column14769 | Column14770 | Column14771 | Column14772 | Column14773 | Column14774 | Column14775 | Column14776 | Column14777 | Column14778 | Column14779 | Column14780 | Column14781 | Column14782 | Column14783 | Column14784 | Column14785 | Column14786 | Column14787 | Column14788 | Column14789 | Column14790 | Column14791 | Column14792 | Column14793 | Column14794 | Column14795 | Column14796 | Column14797 | Column14798 | Column14799 | Column14800 | Column14801 | Column14802 | Column14803 | Column14804 | Column14805 | Column14806 | Column14807 | Column14808 | Column14809 | Column14810 | Column14811 | Column14812 | Column14813 | Column14814 | Column14815 | Column14816 | Column14817 | Column14818 | Column14819 | Column14820 | Column14821 | Column14822 | Column14823 | Column14824 | Column14825 | Column14826 | Column14827 | Column14828 | Column14829 | Column14830 | Column14831 | Column14832 | Column14833 | Column14834 | Column14835 | Column14836 | Column14837 | Column14838 | Column14839 | Column14840 | Column14841 | Column14842 | Column14843 | Column14844 | Column14845 | Column14846 | Column14847 | Column14848 | Column14849 | Column14850 | Column14851 | Column14852 | Column14853 | Column14854 | Column14855 | Column14856 | Column14857 | Column14858 | Column14859 | Column14860 | Column14861 | Column14862 | Column14863 | Column14864 | Column14865 | Column14866 | Column14867 | Column14868 | Column14869 | Column14870 | Column14871 | Column14872 | Column14873 | Column14874 | Column14875 | Column14876 | Column14877 | Column14878 | Column14879 | Column14880 | Column14881 | Column14882 | Column14883 | Column14884 | Column14885 | Column14886 | Column14887 | Column14888 | Column14889 | Column14890 | Column14891 | Column14892 | Column14893 | Column14894 | Column14895 | Column14896 | Column14897 | Column14898 | Column14899 | Column14900 | Column14901 | Column14902 | Column14903 | Column14904 | Column14905 | Column14906 | Column14907 | Column14908 | Column14909 | Column14910 | Column14911 | Column14912 | Column14913 | Column14914 | Column14915 | Column14916 | Column14917 | Column14918 | Column14919 | Column14920 | Column14921 | Column14922 | Column14923 | Column14924 | Column14925 | Column14926 | Column14927 | Column14928 | Column14929 | Column14930 | Column14931 | Column14932 | Column14933 | Column14934 | Column14935 | Column14936 | Column14937 | Column14938 | Column14939 | Column14940 | Column14941 | Column14942 | Column14943 | Column14944 | Column14945 | Column14946 | Column14947 | Column14948 | Column14949 | Column14950 | Column14951 | Column14952 | Column14953 | Column14954 | Column14955 | Column14956 | Column14957 | Column14958 | Column14959 | Column14960 | Column14961 | Column14962 | Column14963 | Column14964 | Column14965 | Column14966 | Column14967 | Column14968 | Column14969 | Column14970 | Column14971 | Column14972 | Column14973 | Column14974 | Column14975 | Column14976 | Column14977 | Column14978 | Column14979 | Column14980 | Column14981 | Column14982 | Column14983 | Column14984 | Column14985 | Column14986 | Column14987 | Column14988 | Column14989 | Column14990 | Column14991 | Column14992 | Column14993 | Column14994 | Column14995 | Column14996 | Column14997 | Column14998 | Column14999 | Column15000 | Column15001 | Column15002 | Column15003 | Column15004 | Column15005 | Column15006 | Column15007 | Column15008 | Column15009 | Column15010 | Column15011 | Column15012 | Column15013 | Column15014 | Column15015 | Column15016 | Column15017 | Column15018 | Column15019 | Column15020 | Column15021 | Column15022 | Column15023 | Column15024 | Column15025 | Column15026 | Column15027 | Column15028 | Column15029 | Column15030 | Column15031 | Column15032 | Column15033 | Column15034 | Column15035 | Column15036 | Column15037 | Column15038 | Column15039 | Column15040 | Column15041 | Column15042 | Column15043 | Column15044 | Column15045 | Column15046 | Column15047 | Column15048 | Column15049 | Column15050 | Column15051 | Column15052 | Column15053 | Column15054 | Column15055 | Column15056 | Column15057 | Column15058 | Column15059 | Column15060 | Column15061 | Column15062 | Column15063 | Column15064 | Column15065 | Column15066 | Column15067 | Column15068 | Column15069 | Column15070 | Column15071 | Column15072 | Column15073 | Column15074 | Column15075 | Column15076 | Column15077 | Column15078 | Column15079 | Column15080 | Column15081 | Column15082 | Column15083 | Column15084 | Column15085 | Column15086 | Column15087 | Column15088 | Column15089 | Column15090 | Column15091 | Column15092 | Column15093 | Column15094 | Column15095 | Column15096 | Column15097 | Column15098 | Column15099 | Column15100 | Column15101 | Column15102 | Column15103 | Column15104 | Column15105 | Column15106 | Column15107 | Column15108 | Column15109 | Column15110 | Column15111 | Column15112 | Column15113 | Column15114 | Column15115 | Column15116 | Column15117 | Column15118 | Column15119 | Column15120 | Column15121 | Column15122 | Column15123 | Column15124 | Column15125 | Column15126 | Column15127 | Column15128 | Column15129 | Column15130 | Column15131 | Column15132 | Column15133 | Column15134 | Column15135 | Column15136 | Column15137 | Column15138 | Column15139 | Column15140 | Column15141 | Column15142 | Column15143 | Column15144 | Column15145 | Column15146 | Column15147 | Column15148 | Column15149 | Column15150 | Column15151 | Column15152 | Column15153 | Column15154 | Column15155 | Column15156 | Column15157 | Column15158 | Column15159 | Column15160 | Column15161 | Column15162 | Column15163 | Column15164 | Column15165 | Column15166 | Column15167 | Column15168 | Column15169 | Column15170 | Column15171 | Column15172 | Column15173 | Column15174 | Column15175 | Column15176 | Column15177 | Column15178 | Column15179 | Column15180 | Column15181 | Column15182 | Column15183 | Column15184 | Column15185 | Column15186 | Column15187 | Column15188 | Column15189 | Column15190 | Column15191 | Column15192 | Column15193 | Column15194 | Column15195 | Column15196 | Column15197 | Column15198 | Column15199 | Column15200 | Column15201 | Column15202 | Column15203 | Column15204 | Column15205 | Column15206 | Column15207 | Column15208 | Column15209 | Column15210 | Column15211 | Column15212 | Column15213 | Column15214 | Column15215 | Column15216 | Column15217 | Column15218 | Column15219 | Column15220 | Column15221 | Column15222 | Column15223 | Column15224 | Column15225 | Column15226 | Column15227 | Column15228 | Column15229 | Column15230 | Column15231 | Column15232 | Column15233 | Column15234 | Column15235 | Column15236 | Column15237 | Column15238 | Column15239 | Column15240 | Column15241 | Column15242 | Column15243 | Column15244 | Column15245 | Column15246 | Column15247 | Column15248 | Column15249 | Column15250 | Column15251 | Column15252 | Column15253 | Column15254 | Column15255 | Column15256 | Column15257 | Column15258 | Column15259 | Column15260 | Column15261 | Column15262 | Column15263 | Column15264 | Column15265 | Column15266 | Column15267 | Column15268 | Column15269 | Column15270 | Column15271 | Column15272 | Column15273 | Column15274 | Column15275 | Column15276 | Column15277 | Column15278 | Column15279 | Column15280 | Column15281 | Column15282 | Column15283 | Column15284 | Column15285 | Column15286 | Column15287 | Column15288 | Column15289 | Column15290 | Column15291 | Column15292 | Column15293 | Column15294 | Column15295 | Column15296 | Column15297 | Column15298 | Column15299 | Column15300 | Column15301 | Column15302 | Column15303 | Column15304 | Column15305 | Column15306 | Column15307 | Column15308 | Column15309 | Column15310 | Column15311 | Column15312 | Column15313 | Column15314 | Column15315 | Column15316 | Column15317 | Column15318 | Column15319 | Column15320 | Column15321 | Column15322 | Column15323 | Column15324 | Column15325 | Column15326 | Column15327 | Column15328 | Column15329 | Column15330 | Column15331 | Column15332 | Column15333 | Column15334 | Column15335 | Column15336 | Column15337 | Column15338 | Column15339 | Column15340 | Column15341 | Column15342 | Column15343 | Column15344 | Column15345 | Column15346 | Column15347 | Column15348 | Column15349 | Column15350 | Column15351 | Column15352 | Column15353 | Column15354 | Column15355 | Column15356 | Column15357 | Column15358 | Column15359 | Column15360 | Column15361 | Column15362 | Column15363 | Column15364 | Column15365 | Column15366 | Column15367 | Column15368 | Column15369 | Column15370 | Column15371 | Column15372 | Column15373 | Column15374 | Column15375 | Column15376 | Column15377 | Column15378 | Column15379 | Column15380 | Column15381 | Column15382 | Column15383 | Column15384 | Column15385 | Column15386 | Column15387 | Column15388 | Column15389 | Column15390 | Column15391 | Column15392 | Column15393 | Column15394 | Column15395 | Column15396 | Column15397 | Column15398 | Column15399 | Column15400 | Column15401 | Column15402 | Column15403 | Column15404 | Column15405 | Column15406 | Column15407 | Column15408 | Column15409 | Column15410 | Column15411 | Column15412 | Column15413 | Column15414 | Column15415 | Column15416 | Column15417 | Column15418 | Column15419 | Column15420 | Column15421 | Column15422 | Column15423 | Column15424 | Column15425 | Column15426 | Column15427 | Column15428 | Column15429 | Column15430 | Column15431 | Column15432 | Column15433 | Column15434 | Column15435 | Column15436 | Column15437 | Column15438 | Column15439 | Column15440 | Column15441 | Column15442 | Column15443 | Column15444 | Column15445 | Column15446 | Column15447 | Column15448 | Column15449 | Column15450 | Column15451 | Column15452 | Column15453 | Column15454 | Column15455 | Column15456 | Column15457 | Column15458 | Column15459 | Column15460 | Column15461 | Column15462 | Column15463 | Column15464 | Column15465 | Column15466 | Column15467 | Column15468 | Column15469 | Column15470 | Column15471 | Column15472 | Column15473 | Column15474 | Column15475 | Column15476 | Column15477 | Column15478 | Column15479 | Column15480 | Column15481 | Column15482 | Column15483 | Column15484 | Column15485 | Column15486 | Column15487 | Column15488 | Column15489 | Column15490 | Column15491 | Column15492 | Column15493 | Column15494 | Column15495 | Column15496 | Column15497 | Column15498 | Column15499 | Column15500 | Column15501 | Column15502 | Column15503 | Column15504 | Column15505 | Column15506 | Column15507 | Column15508 | Column15509 | Column15510 | Column15511 | Column15512 | Column15513 | Column15514 | Column15515 | Column15516 | Column15517 | Column15518 | Column15519 | Column15520 | Column15521 | Column15522 | Column15523 | Column15524 | Column15525 | Column15526 | Column15527 | Column15528 | Column15529 | Column15530 | Column15531 | Column15532 | Column15533 | Column15534 | Column15535 | Column15536 | Column15537 | Column15538 | Column15539 | Column15540 | Column15541 | Column15542 | Column15543 | Column15544 | Column15545 | Column15546 | Column15547 | Column15548 | Column15549 | Column15550 | Column15551 | Column15552 | Column15553 | Column15554 | Column15555 | Column15556 | Column15557 | Column15558 | Column15559 | Column15560 | Column15561 | Column15562 | Column15563 | Column15564 | Column15565 | Column15566 | Column15567 | Column15568 | Column15569 | Column15570 | Column15571 | Column15572 | Column15573 | Column15574 | Column15575 | Column15576 | Column15577 | Column15578 | Column15579 | Column15580 | Column15581 | Column15582 | Column15583 | Column15584 | Column15585 | Column15586 | Column15587 | Column15588 | Column15589 | Column15590 | Column15591 | Column15592 | Column15593 | Column15594 | Column15595 | Column15596 | Column15597 | Column15598 | Column15599 | Column15600 | Column15601 | Column15602 | Column15603 | Column15604 | Column15605 | Column15606 | Column15607 | Column15608 | Column15609 | Column15610 | Column15611 | Column15612 | Column15613 | Column15614 | Column15615 | Column15616 | Column15617 | Column15618 | Column15619 | Column15620 | Column15621 | Column15622 | Column15623 | Column15624 | Column15625 | Column15626 | Column15627 | Column15628 | Column15629 | Column15630 | Column15631 | Column15632 | Column15633 | Column15634 | Column15635 | Column15636 | Column15637 | Column15638 | Column15639 | Column15640 | Column15641 | Column15642 | Column15643 | Column15644 | Column15645 | Column15646 | Column15647 | Column15648 | Column15649 | Column15650 | Column15651 | Column15652 | Column15653 | Column15654 | Column15655 | Column15656 | Column15657 | Column15658 | Column15659 | Column15660 | Column15661 | Column15662 | Column15663 | Column15664 | Column15665 | Column15666 | Column15667 | Column15668 | Column15669 | Column15670 | Column15671 | Column15672 | Column15673 | Column15674 | Column15675 | Column15676 | Column15677 | Column15678 | Column15679 | Column15680 | Column15681 | Column15682 | Column15683 | Column15684 | Column15685 | Column15686 | Column15687 | Column15688 | Column15689 | Column15690 | Column15691 | Column15692 | Column15693 | Column15694 | Column15695 | Column15696 | Column15697 | Column15698 | Column15699 | Column15700 | Column15701 | Column15702 | Column15703 | Column15704 | Column15705 | Column15706 | Column15707 | Column15708 | Column15709 | Column15710 | Column15711 | Column15712 | Column15713 | Column15714 | Column15715 | Column15716 | Column15717 | Column15718 | Column15719 | Column15720 | Column15721 | Column15722 | Column15723 | Column15724 | Column15725 | Column15726 | Column15727 | Column15728 | Column15729 | Column15730 | Column15731 | Column15732 | Column15733 | Column15734 | Column15735 | Column15736 | Column15737 | Column15738 | Column15739 | Column15740 | Column15741 | Column15742 | Column15743 | Column15744 | Column15745 | Column15746 | Column15747 | Column15748 | Column15749 | Column15750 | Column15751 | Column15752 | Column15753 | Column15754 | Column15755 | Column15756 | Column15757 | Column15758 | Column15759 | Column15760 | Column15761 | Column15762 | Column15763 | Column15764 | Column15765 | Column15766 | Column15767 | Column15768 | Column15769 | Column15770 | Column15771 | Column15772 | Column15773 | Column15774 | Column15775 | Column15776 | Column15777 | Column15778 | Column15779 | Column15780 | Column15781 | Column15782 | Column15783 | Column15784 | Column15785 | Column15786 | Column15787 | Column15788 | Column15789 | Column15790 | Column15791 | Column15792 | Column15793 | Column15794 | Column15795 | Column15796 | Column15797 | Column15798 | Column15799 | Column15800 | Column15801 | Column15802 | Column15803 | Column15804 | Column15805 | Column15806 | Column15807 | Column15808 | Column15809 | Column15810 | Column15811 | Column15812 | Column15813 | Column15814 | Column15815 | Column15816 | Column15817 | Column15818 | Column15819 | Column15820 | Column15821 | Column15822 | Column15823 | Column15824 | Column15825 | Column15826 | Column15827 | Column15828 | Column15829 | Column15830 | Column15831 | Column15832 | Column15833 | Column15834 | Column15835 | Column15836 | Column15837 | Column15838 | Column15839 | Column15840 | Column15841 | Column15842 | Column15843 | Column15844 | Column15845 | Column15846 | Column15847 | Column15848 | Column15849 | Column15850 | Column15851 | Column15852 | Column15853 | Column15854 | Column15855 | Column15856 | Column15857 | Column15858 | Column15859 | Column15860 | Column15861 | Column15862 | Column15863 | Column15864 | Column15865 | Column15866 | Column15867 | Column15868 | Column15869 | Column15870 | Column15871 | Column15872 | Column15873 | Column15874 | Column15875 | Column15876 | Column15877 | Column15878 | Column15879 | Column15880 | Column15881 | Column15882 | Column15883 | Column15884 | Column15885 | Column15886 | Column15887 | Column15888 | Column15889 | Column15890 | Column15891 | Column15892 | Column15893 | Column15894 | Column15895 | Column15896 | Column15897 | Column15898 | Column15899 | Column15900 | Column15901 | Column15902 | Column15903 | Column15904 | Column15905 | Column15906 | Column15907 | Column15908 | Column15909 | Column15910 | Column15911 | Column15912 | Column15913 | Column15914 | Column15915 | Column15916 | Column15917 | Column15918 | Column15919 | Column15920 | Column15921 | Column15922 | Column15923 | Column15924 | Column15925 | Column15926 | Column15927 | Column15928 | Column15929 | Column15930 | Column15931 | Column15932 | Column15933 | Column15934 | Column15935 | Column15936 | Column15937 | Column15938 | Column15939 | Column15940 | Column15941 | Column15942 | Column15943 | Column15944 | Column15945 | Column15946 | Column15947 | Column15948 | Column15949 | Column15950 | Column15951 | Column15952 | Column15953 | Column15954 | Column15955 | Column15956 | Column15957 | Column15958 | Column15959 | Column15960 | Column15961 | Column15962 | Column15963 | Column15964 | Column15965 | Column15966 | Column15967 | Column15968 | Column15969 | Column15970 | Column15971 | Column15972 | Column15973 | Column15974 | Column15975 | Column15976 | Column15977 | Column15978 | Column15979 | Column15980 | Column15981 | Column15982 | Column15983 | Column15984 | Column15985 | Column15986 | Column15987 | Column15988 | Column15989 | Column15990 | Column15991 | Column15992 | Column15993 | Column15994 | Column15995 | Column15996 | Column15997 | Column15998 | Column15999 | Column16000 | Column16001 | Column16002 | Column16003 | Column16004 | Column16005 | Column16006 | Column16007 | Column16008 | Column16009 | Column16010 | Column16011 | Column16012 | Column16013 | Column16014 | Column16015 | Column16016 | Column16017 | Column16018 | Column16019 | Column16020 | Column16021 | Column16022 | Column16023 | Column16024 | Column16025 | Column16026 | Column16027 | Column16028 | Column16029 | Column16030 | Column16031 | Column16032 | Column16033 | Column16034 | Column16035 | Column16036 | Column16037 | Column16038 | Column16039 | Column16040 | Column16041 | Column16042 | Column16043 | Column16044 | Column16045 | Column16046 | Column16047 | Column16048 | Column16049 | Column16050 | Column16051 | Column16052 | Column16053 | Column16054 | Column16055 | Column16056 | Column16057 | Column16058 | Column16059 | Column16060 | Column16061 | Column16062 | Column16063 | Column16064 | Column16065 | Column16066 | Column16067 | Column16068 | Column16069 | Column16070 | Column16071 | Column16072 | Column16073 | Column16074 | Column16075 | Column16076 | Column16077 | Column16078 | Column16079 | Column16080 | Column16081 | Column16082 | Column16083 | Column16084 | Column16085 | Column16086 | Column16087 | Column16088 | Column16089 | Column16090 | Column16091 | Column16092 | Column16093 | Column16094 | Column16095 | Column16096 | Column16097 | Column16098 | Column16099 | Column16100 | Column16101 | Column16102 | Column16103 | Column16104 | Column16105 | Column16106 | Column16107 | Column16108 | Column16109 | Column16110 | Column16111 | Column16112 | Column16113 | Column16114 | Column16115 | Column16116 | Column16117 | Column16118 | Column16119 | Column16120 | Column16121 | Column16122 | Column16123 | Column16124 | Column16125 | Column16126 | Column16127 | Column16128 | Column16129 | Column16130 | Column16131 | Column16132 | Column16133 | Column16134 | Column16135 | Column16136 | Column16137 | Column16138 | Column16139 | Column16140 | Column16141 | Column16142 | Column16143 | Column16144 | Column16145 | Column16146 | Column16147 | Column16148 | Column16149 | Column16150 | Column16151 | Column16152 | Column16153 | Column16154 | Column16155 | Column16156 | Column16157 | Column16158 | Column16159 | Column16160 | Column16161 | Column16162 | Column16163 | Column16164 | Column16165 | Column16166 | Column16167 | Column16168 | Column16169 | Column16170 | Column16171 | Column16172 | Column16173 | Column16174 | Column16175 | Column16176 | Column16177 | Column16178 | Column16179 | Column16180 | Column16181 | Column16182 | Column16183 | Column16184 | Column16185 | Column16186 | Column16187 | Column16188 | Column16189 | Column16190 | Column16191 | Column16192 | Column16193 | Column16194 | Column16195 | Column16196 | Column16197 | Column16198 | Column16199 | Column16200 | Column16201 | Column16202 | Column16203 | Column16204 | Column16205 | Column16206 | Column16207 | Column16208 | Column16209 | Column16210 | Column16211 | Column16212 | Column16213 | Column16214 | Column16215 | Column16216 | Column16217 | Column16218 | Column16219 | Column16220 | Column16221 | Column16222 | Column16223 | Column16224 | Column16225 | Column16226 | Column16227 | Column16228 | Column16229 | Column16230 | Column16231 | Column16232 | Column16233 | Column16234 | Column16235 | Column16236 | Column16237 | Column16238 | Column16239 | Column16240 | Column16241 | Column16242 | Column16243 | Column16244 | Column16245 | Column16246 | Column16247 | Column16248 | Column16249 | Column16250 | Column16251 | Column16252 | Column16253 | Column16254 | Column16255 | Column16256 | Column16257 | Column16258 | Column16259 | Column16260 | Column16261 | Column16262 | Column16263 | Column16264 | Column16265 | Column16266 | Column16267 | Column16268 | Column16269 | Column16270 | Column16271 | Column16272 | Column16273 | Column16274 | Column16275 | Column16276 | Column16277 | Column16278 | Column16279 | Column16280 | Column16281 | Column16282 | Column16283 | Column16284 | Column16285 | Column16286 | Column16287 | Column16288 | Column16289 | Column16290 | Column16291 | Column16292 | Column16293 | Column16294 | Column16295 | Column16296 | Column16297 | Column16298 | Column16299 | Column16300 | Column16301 | Column16302 | Column16303 | Column16304 | Column16305 | Column16306 | Column16307 | Column16308 | Column16309 | Column16310 | Column16311 | Column16312 | Column16313 | Column16314 | Column16315 | Column16316 | Column16317 | Column16318 | Column16319 | Column16320 | Column16321 | Column16322 | Column16323 | Column16324 | Column16325 | Column16326 | Column16327 | Column16328 | Column16329 | Column16330 | Column16331 | Column16332 | Column16333 | Column16334 | Column16335 | Column16336 | Column16337 | Column16338 | Column16339 | Column16340 | Column16341 | Column16342 | Column16343 | Column16344 | Column16345 | Column16346 | Column16347 | Column16348 | Column16349 | Column16350 | Column16351 | Column16352 | Column16353 | Column16354 | Column16355 | Column16356 | Column16357 | Column16358 | Column16359 | Column16360 | Column16361 | Column16362 | Column16363 | Column16364 | Column16365
|  |  | Project Milestone | ME | Common | TS1 | Project Engineering | Detail Design | Customer Spec Review |  |  | 2026-01-01 | 1 | 3% |  | Team Lead
|  |  | Project Submittals | ME | Common | TS1 | Project Engineering | Detail Design | Kick-off Project Meeting (BC Internal) - EE Review |  |  | 2026-04-03 | 8 |  |  | Team Lead |  | Layout must be handed frozen at this stage. Any changes after this meeting will impact the schedule
|  |  |  | ME | Common | TS1 | Project Engineering | Detail Design | Interface Power Requirements |  |  | 2026-04-04 | 4 |  |  | Team Lead
|  |  |  | ME | Common | TS1 | Project Engineering | Detail Design | Power/Network Interface to Scanner if appliable to BC |  |  | 2026-04-04 | 4 |  |  | Team Lead
|  |  |  | ME | BGLS | TS2 | Design Engineering | Detail Design | Ordering Tool - BOM List Review (EE) |  |  | 2026-04-17 | 16 | 51% |  | Andre Resende
|  |  |  | ME | BGLS | TS2 | Design Engineering | Detail Design | Ordering Tool - E-Stop Review (EE) |  |  | 2026-04-17 | 8 |  |  | Andre Resende
|  |  |  | ME | Common | TS2 | Design Engineering | Detail Design | Chute Electrical - BOM List (Master Data) |  |  | 2026-04-24 | 32 |  |  | Pedro Resende
|  |  |  | ME | Common | TS2 | Design Engineering | Detail Design | Create +/- List to BDK procurement |  |  | 2026-04-24 | 16 |  |  | Pedro Resende
|  |  |  | ME | Common | TS2 | Design Engineering | Documentation | Power calculation - System 24VDC |  |  | 2026-04-25 | 4 |  |  | Abraham
|  |  |  | ME | Common | TS2 | Design Engineering | Documentation | Power calculation - System 480VAC |  |  | 2026-04-25 | 4 |  |  | Abraham
|  |  |  | ME | Common | TS2 | Design Engineering | Documentation | Reference Designation RDS |  |  | 2026-04-26 | 4 |  |  | Abraham
|  |  |  | ME | Common | TS2 | Design Engineering | Documentation | Electrical Permit Package |  |  | 2026-04-26 | 6 |  |  | Abraham
|  |  |  | EE | Common | TS2 | Design Engineering | Documentation | E-Stop Interface Document |  |  | 2026-04-27 | 4 |  |  | Abraham
|  |  |  | ME | Common | TS2 | Design Engineering | Documentation | Network Architecture - EE Review |  |  | 2026-04-29 | 10 |  |  | Nina
|  |  |  | ME | Common | TS2 | Design Engineering | Detail Design | Network Drop Layout and Specification |  |  | 2026-04-29 | 6 |  |  | Abraham
|  |  |  | ME | Common | TS2 | Design Engineering | Detail Design | ECO Layout (dwg) - EE Review |  |  | 2026-05-03 | 24 |  |  | Pedro Resende
|  |  |  | ME | Common | TS2 | Design Engineering | Detail Design | Destination Hardware E-Layout |  |  | 2026-05-06 | 8 |  |  | Pedro Resende
|  |  |  | EE | Common | TS2 | Design Engineering | Installation Drawings | Test Measurement Point (TMP) ME/EE |  |  | 2026-05-06 | 4 |  |  | Daniele
|  |  |  | EE | Common | TS2 | Design Engineering | Detail Design | E-Brackets list to ME team |  |  | 2026-05-06 | 6 |  |  | Pedro Resende
|  |  |  | EE | Common | TS2 | Design Engineering | Detail Design | Chute Cable Trays / Routing - Installation Instruction EE/ME |  |  | 2026-05-06 | 8 |  |  | Pedro Resende
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | BID Package - EE support |  |  | - | 8 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | Online MRF - Cable pre-fabricated |  |  | 2026-05-13 | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | Online MRF - Control Stations |  |  | 2026-05-13 | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | Online MRF - Intrumentation |  |  | 2026-05-13 | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | Online MRF - Stack Light |  |  | 2026-05-13 | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Design Engineering | MRF | Online MRF - System Labels |  |  | 2026-05-13 | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS2 | Project Engineering | Detail Design | General Project Meetings (Internal) - EE Hours |  |  | - | 98 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Design Engineering | System Components | Calculate the cable lengths (CAD) |  |  | 2026-05-13 | 16 |  |  | Jonathan
|  |  |  | EE | Common | TS3 | Design Engineering | Detail Design | EPLAN Electrical Schematic |  |  | 2026-07-02 | 40 | 46% |  | Jonathan
|  |  |  | EE | Common | TS3 | Design Engineering | System Components | BDK Cabinet Rating plates Request |  |  | 2026-07-02 | 4 |  |  | Jonathan
|  |  |  | EE | Common | TS3 | Design Engineering | Installation Drawings | Cable grafical overview Excel - Power/control |  |  | 2026-07-02 | 20 |  |  | Uriel
|  |  |  | EE | Common | TS3 | Design Engineering | Detail Design | IO-List |  |  | 2026-07-02 | 24 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Design Engineering | Documentation | Functional Specification (TPM) - EE Review |  |  | - | 6 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Design Engineering | Documentation | Critical Asset List - Support TPM |  |  | - | 6 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 1 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 2 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 3 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 4 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 5 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Check list - Design Review 6 - EE support |  |  | - | 2 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | System Components | Electrical installation binders |  |  | 2026-07-12 | 6 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | Detail Design | Generate EPLAN Cable Labels |  |  | 2026-07-12 | 6 |  |  | Jonathan
|  |  |  | EE | Common | TS3 | Project Engineering | Detail Design | Generate EPLAN Device Labels |  |  | 2026-07-12 | 6 |  |  | Jonathan
|  |  |  | EE | Common | TS3 | Project Engineering | Installation Drawings | Level 6 Check List |  |  | 2026-07-12 | 8 |  |  | Abraham
|  |  |  | EE | Common | TS3 | Documentation | System Components | Spare Parts |  |  | 2026-07-12 | 8 |  |  | Abraham
|  |  |  | EE | Common | TS3 | Documentation | Installation Drawings | Asbuilt Electrical Documentation |  |  | 2026-08-11 | 40 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Documentation | System Components | eDoc - EE Review |  |  | 2027-01-28 | 8 |  |  | Team Lead
|  |  |  | EE | Common | TS3 | Project Engineering | Detail Design | General Project Trip - EE Hours |  |  | - | 40 |  |  | Team Lead
[5 empty] | Common | TS3 | Project Engineering | Detail Design | General Project SI team Support - EE Hours |  |  | - | 40 |  |  | Team Lead
[5 empty] | BGS |  |  |  | Reviewing Proposal/ As-sold
[5 empty] | BGS |  |  |  | Reviewing Project Data List
[5 empty] | BGS |  |  |  | Reference Naming Sketch
[5 empty] | BGS |  |  |  | Reference Naming Doc
[5 empty] | BGS |  |  |  | Power Calculation - No. of LSM/CR
[5 empty] | BGS |  |  |  | Power Specification Doc
[5 empty] | BGS |  |  |  | Scanner Request For Purchase document
[5 empty] | BGS |  |  |  | Scanner order entry - MRF
[5 empty] | BGS |  |  |  | Review PLC selection
[5 empty] | BGS |  |  |  | Co-ordination with Induction Team at BDK (regarding addition of components, replacting components - based on project requirements)
[5 empty] | Chute |  |  |  | Reviewing Proposal/ As-sold
[5 empty] | Customer Realated Task |  |  |  | Reference Naming Sketch (Incorporate Amazon Naming as per the convention)
[5 empty] | BGS |  |  |  | Network Drops and 120V layout
[5 empty] | BGS |  |  |  | Component List
[5 empty] | BGS |  |  |  | Preliminary e-layout (Electrical Device, E-stops, Network Switches, CCHs)
[5 empty] | BGS |  |  |  | Chute Device Layout
[5 empty] | BGS |  |  |  | Short Circuit Calculation
[5 empty] | BGS |  |  |  | 24V Power Consumption Calculation (Chutes)
[5 empty] | BGS |  |  |  | Graphical Cable Overview
[5 empty] | BGS |  |  |  | Cable Tray Routing sketch and alignment with ME
[5 empty] | BGS |  |  |  | Chute Overview
[5 empty] | BGS |  |  |  | PE's and hardware selection for Destination
[5 empty] | BGS |  |  |  | Create Electrical Master Data
[5 empty] | BGS |  |  |  | MCC Electrical Schematics EPLAN
[5 empty] | BGS |  |  |  | FLM Electrical Schematics EPLAN
[5 empty] | BGS |  |  |  | FCR Electrical Schematics EPLAN
[5 empty] | BGS |  |  |  | Chute Macros - eplan
[5 empty] | BGS |  |  |  | BESD Cabling
[5 empty] | BGS |  |  |  | IO list
[5 empty] | BGS |  |  |  | Overall alignment with MC
[5 empty] | Chute |  |  |  | PE's and hardware selection for Destination
[5 empty] | Chute |  |  |  | 24V Power Consumption Calculation (Chutes)
[5 empty] | Chute |  |  |  | Chute Macros - eplan
[5 empty] | Chute |  |  |  | Chute Device Layout
[5 empty] | BGS |  |  |  | Cable Checklist
[5 empty] | BGS |  |  |  | Auto generate Project eplan
[5 empty] | BGS |  |  |  | VQ checklist
[5 empty] | BGS |  |  |  | Cable Overview - for SI/EC via Eplan
[5 empty] | BGS |  |  |  | Generate Level 6 Testsheet
[5 empty] | BGS |  |  |  | Ordering materials locally via MRF creation
[5 empty] | BGS |  |  |  | Ordering materials from BDK via TOS/SAP - filling out BOM document
[5 empty] | BGS |  |  |  | Generate EC Bid Package
[5 empty] | BGS |  |  |  | Make Installation Binder
[5 empty] | BGS |  |  |  | Generate Labels file and print
[5 empty] | BGS |  |  |  | Design Review 4 - meeting
[5 empty] | BGS |  |  |  | Site support/calls/JIRA
[5 empty] | Customer Realated Task |  |  |  | VQ checklist
Formulas:
Schedule = [Schedule, row above]+1
Schedule = [Schedule, row above]

## ME Workflow
Division | Customer | Integ | Name | System | Task Sequence | Task Category | Column1 | Project Category | Deliverable | Status | Review Date | Schedule | Estimated Duration | Project phase Duration | Project phase Duration2 | Project Lead | Area Owner | Execution Owner | Comments
|  |  |  | Common | 1 | Project Engineering |  | System Layouts | System Layout Submittal |  |  |  | 16 | Design | 254
|  |  |  | Common | 2 | Project Engineering |  | Documentation | Project Meetings |  |  |  | 54 | Design
|  |  |  | BGLS | 3 | Project Engineering |  | Documentation | BGLS Ordering Tool - ME |  |  |  | 8 | Design
|  |  |  | Common | 4 | Project Engineering |  | Documentation | Site Survey |  |  |  | 16 | Design
|  |  |  | Common | 5 | Project Engineering |  | System Components | Cabinet Location |  |  |  | 4 | Design
|  |  |  | BGLS | 6 | Project Engineering |  | System Components | BGLS Sorter Length |  |  |  | 4 | Design
|  |  |  | Common | 7 | Project Engineering |  | System Components | Operator and Maintenace Area |  |  |  | 4 | Design
|  |  |  | Common | 8 | Project Engineering |  | System Components | Point Load Layout |  |  |  | 8 | Design
|  |  |  | Common | 9 | Project Engineering |  | System Components | Induction Unit |  |  |  | 4 | Design
|  |  |  | Common | 10 | Project Engineering |  | System Components | Safety Equipment |  |  |  | 4 | Design
|  |  |  | Common | 11 | Project Engineering |  | System Components | Safety Fencing |  |  |  | 16 | Design
|  |  |  | Common | 12 | Project Engineering |  | System Components | Sorter Support |  |  |  | 4 | Design
|  |  |  | Common | 13 | Project Engineering |  | System Components | System Interface |  |  |  | 4 | Design
|  |  |  | Common | 14 | Project Engineering |  | System Components | Destination |  |  |  | 16 | Design
|  |  |  | Common | 15 | Project Engineering |  | System Components | ECO Layout |  |  |  | 16 | Design
|  |  |  | Common | 16 | Project Engineering |  | System Components | Sorter Section |  |  |  | 4 | Design
|  |  |  | Common | 17 | Design Engineering |  | Chute Design | Static Chute |  |  |  | 16 | Design
|  |  |  | Common | 18 | Documentation |  | MRF | Steel |  |  |  | 4 | Production | 264
|  |  |  | Common | 19 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 20 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 14 | Project Engineering |  | System Components | Destination |  |  |  | 16 | Design
|  |  |  | Common | 21 | Design Engineering |  | Chute Design | Induction Chute |  |  |  | 16 | Design
|  |  |  | Common | 22 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 23 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 24 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 25 | Design Engineering |  | Chute Design | Mobile Chute |  |  |  | 16 | Design
|  |  |  | Common | 26 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 27 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 28 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 29 | Design Engineering |  | Chute Design | Recirculation Line |  |  |  | 16 | Design
|  |  |  | Common | 30 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 31 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 32 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 33 | Design Engineering |  | Chute Design | End of Line Chute |  |  |  | 16 | Design
|  |  |  | Common | 34 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 35 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 36 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 37 | Design Engineering |  | Detail Design | Sorter Supports |  |  |  | 16 | Design
|  |  |  | Common | 38 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 39 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 40 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 41 | Design Engineering |  | Detail Design | EE Device Brackets |  |  |  | 16 | Design
|  |  |  | Common | 42 | Documentation |  | MRF | Steel |  |  |  | 4 | Production
|  |  |  | Common | 43 | Documentation |  | MRF | Hardware |  |  |  | 4 | Production
|  |  |  | Common | 44 | Documentation |  | MRF | Purchased Items |  |  |  | 4 | Production
|  |  |  | Common | 45 | Documentation |  | MRF | Safety Fencing |  |  |  | 4 | Production
|  |  |  | Common | 46 | Documentation |  | MRF | Safety Equipment |  |  |  | 4 | Production
|  |  |  | Common | 47 | Documentation |  | MRF | Safety Labels |  |  |  | 4 | Production
|  |  |  | Common | 48 | Project Engineering |  | Documentation | Risk Assessment |  |  |  | 16 | Design
|  |  |  | Common | 49 | Project Layouts |  | Installation Drawings | Datum |  |  |  | 4 | Production
|  |  |  | Common | 50 | Project Layouts |  | Installation Drawings | DES ECO Layout |  |  |  | 8 | Production
|  |  |  | Common | 51 | Project Layouts |  | Installation Drawings | Destination Chutes |  |  |  | 16 | Production
|  |  |  | Common | 52 | Project Layouts |  | Installation Drawings | Destination Transitions |  |  |  | 8 | Production
|  |  |  | Common | 53 | Project Layouts |  | Installation Drawings | Egress, Maintenance Operator |  |  |  | 4 | Production
|  |  |  | Common | 54 | Project Layouts |  | Installation Drawings | Induction Unit |  |  |  | 4 | Production
|  |  |  | BGLS | 55 | Project Layouts |  | Installation Drawings | LNS ECO Layout |  |  |  | 16 | Production
|  |  |  | BGLS | 56 | Project Layouts |  | Installation Drawings | LNS Sorter Section |  |  |  | 8 | Production
|  |  |  | Common | 57 | Project Layouts |  | Installation Drawings | Safety Fencing |  |  |  | 16 | Production
|  |  |  | Common | 58 | Project Layouts |  | Installation Drawings | Safety Labels |  |  |  | 4 | Production
|  |  |  | Common | 59 | Project Layouts |  | Installation Drawings | Sorter Support |  |  |  | 8 | Production
|  |  |  | Common | 60 | Project Layouts |  | Documentation | Installation Book |  |  |  | 16 | Production
|  |  |  | Common | 61 | Project Layouts |  | Documentation | As-Builds |  |  |  | 8 | Comissioning | 12
|  |  |  | Common | 62 | Project Engineering |  | Documentation | Spare Parts List |  |  |  | 4 | Comissioning
546
530
[8 empty] | Layout Hours | 120 | hrs |  |  | Sold Hours | 530
[13 empty] | Design | 0% | 0 | 50% | 265 | 132.5
[8 empty] | pre-markup | 160 | 19200 |  |  | Production | 47.92% | 254 | 30% | 159 | 53
[8 empty] | After mark-up | 216 | 25920 |  |  | Installation | 0% | 0 | 15% | 79.5 | 26.5
[13 empty] | Comissioning | 2.264% | 12 | 5% | 26.5
[13 empty] | Support | 0% | 0 |  | 0
[14 empty] | 0.50189 |  | 1
79.5
[14 empty] | Design | 0
0
[14 empty] | Production | 84.6667
84.6667
84.6667
Installation
12
Comissioning
[14 empty] | Support | 0
266

## MT Structure
Team Leads | Detail Design | Loop Sorter | BGLS | CS Projects
Project Owner (Engineer) | All Projects
Sub-System / Project Scope | Sorter Supports | Destination 1 | Platform / Steel Structure | Sorter (Name) | System Layouts | System Safety | Project Activities | BGLS | Induction Unit | Project Milestones | BG Conveyor | Loop Srtr | Misc Eqpt | Prototype
| Detail Design | Detail Design | Xref - Platform | Sorter Layout Design - xref | System Layout Submittal | Risk Assessment | Project Meetings | BGLS Ordering Tool - ME | Induction - Xef | Sorter Layout Freeze |  |  |  | ( Time range)
All are multiplyable | Xref (Sysm Comp) | Xref (Sysm Comp) | MRF - Platform | Sorter Detail Design | Navisworks | Safety Labels | Site Survey | Cabinet Location | Induction Design | System Layout Freeze
| MRF | MRF | Platform Design Planning | Xref - Sorter Components | Building Xref | Safety Fence - Eng Planning | PPP - Creation | BGLS Sorter Length | Induction MRF | Chute Position Freeze
| Installation Drawing | Installation Drawing | Instal dwg - Platform | Instal dwg - Sorter | Datum Xref | Safety Fence - Xref | Site Travel | Sorter Section | Interface drawing | Induction Freeze
|  |  |  | Scanner Design - EE | Point Load Layout | Safety Fence MRF | Project Design Reviews
|  |  |  | Xref - Scanner | System Interface | Instal dwg - Safety Fence | PPP - Meetings |  |  | Installation Start
|  |  |  | MRF - Sorter |  | Operator and Maintenace Area | Installation Support |  |  | Commissioning Start
|  |  |  | Cable Tray Xref |  | Safety Equipment - Xref - MRF - Design |  |  |  | Sales Handover Date
Project Start
|  |  |  | Cable Tray MRF |  | E-Stop Pull Cords - Xref
E-Stop Pull Cords - MRF
E-Stop Pull Cords - Design
Area Owner | Detail Design | Chute Design | Engineering Planning | Project Layouts | Installation Drawings | Sorter Design | System Components | System Safety | MRFs (Project Owner) | Prototype
| Sorter Supports | Detail Design | Platform Design Planning | System Layout Submittal | Installation Drawing | Sorter Layout Design - xref | Xref (Sysm Comp) | Risk Assessment | MRF
| Destination 1 |  |  | Navisworks | Installation Drawing | Sorter Detail Design | MRF | Safety Labels | Xref (Sysm Comp)
| Platform / Steel Structure |  |  | Point Load Layout | Instal dwg - Platform | Xref - Sorter Components | Xref - Platform |  | MRF - Platform
[5 empty] | Instal dwg - Sorter |  | Sorter Layout Design - xref |  | Safety Fence MRF
[5 empty] | Instal dwg - Safety Fence |  | Safety Fence - Xref |  | MRF - Sorter
Building Xref
Datum Xref
Xref - Scanner
Execution Eng
Pending | Planning
Cable Trays | Scope / Area Naming | [6 empty] | May 1st | 2026-05-29 | install
BG Conveyor - Internal External | EE Integration
Site Surveys | WBS Task Conversion (milestones)
Installation Support | Execution Dates
Pull cords | Dependent Tasks
Device Brackets | Structure of department
Safety equip / guard
Cabinet
Spare parts list
Design Reviews
Operator and maintenance area
Egress
ECO Layout
Redlines
Point Load / PE Permit
Chute Interface
Induction Units
Lessons Learned
Sorter Supports
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner | Detail Design
Detail Design |  | 3 | 2026-06-23 |  |  | Chute Design
Xref (Sysm Comp) |  | 7 | 2026-06-26 |  |  | System Component (Xref)
MRF |  | 7 | 2026-06-30 |  |  | MRF
Installation Drawing |  | 14 | 2026-07-07 |  |  | Installation Drawing
Milestone - Sorter Support Layout |  | 56 | 2026-08-25 | Install Start |  | Project Milestone
Sorter Design
(Name) Chute | [6 empty] | (Name) Chute
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner | MHE Design | Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Detail Design | [5 empty] | System Layout | Destination ECO Review
Xref (Sysm Comp) | [5 empty] | System Safety | Master Data
MRF | [5 empty] | Project Activity | MRF
Installation Drawing | [5 empty] | BGLS | Installation Drawing
Installation Date
Induction Unit
Platform / Steel Structure | [6 empty] | Platform / Steel Structure
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner |  | Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Engineering Planning | [6 empty] | TMP Planning
Xref (Sysm Comp) | [6 empty] | Xref review
MRF | [6 empty] | MRF
Installation Drawing | [6 empty] | Installation Drawing
(Name) Sorter | [6 empty] | (Name) Sorter
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner |  | Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Sorter Design | [6 empty] | Sorter ECO Layout
Xref (Sorter Layout) | [6 empty] | Plus and Minus List BDK
Xref (System Components) | [6 empty] | Ordering Tool
MRF (Sorter) | [6 empty] | Master Data
Installation Drawing (Sorter) | [6 empty] | Eplan
Scanner Design (EE) | [6 empty] | IO List
Xref (Scanner) | [6 empty] | Customer Interface
Xref (Cable Tray) | [6 empty] | Scanner Design TPM
MRF (Cable Tray) | [6 empty] | MRF Scanners
System Layouts
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
System Layout (Sorter 1)
System Layout - Navisowrks
Xref (Building)
Xref (Datum)
Point Load Layout (Sorter 1)
System Interface (Sorter 1)
System Safety
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Risk Assessment
Safety Labels
Engineering Planning (Safety Fence)
Xref (Safety Fence)
MRF (Safety Fence)
Installation Drawing (Safety Fence)
Installation Drawing (Operator and Maintenance Area)
Xref (Safety Equipment)
MRF (Safety Equipment)
Detail Design (Safety Equipment)
Xref (E- Stop Pull Cord)
MRF (E-Stop Pull Cord)
Detail Desing (E-Stop Pull Cord)
Project Activity
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Project Meetings
Site Survey
PPP - Creation
PPP - Meetings
Site Travel
Project Design Reviews
Installation Support
BGLS
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
BGLS - Ordering Tool
Xref (Cabinet Location)
BGLS - Sorter Length
Xref (Sorter Sections)
Induction Units
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Xref (Induction)
Detail Design - Induction
MRF - Induction
Interface Drawing
Project Milestone
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Sorter Layout Freeze
System Layout Freeze
Chute Position Freeze
Induction Layout Freeze
Installation Start
Comissioning Start
Project Start
DES / Sortr ECO Layouts
Template
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Chute Design
Xref (Sysm Comp)
Engineering Planning
System Safety
MRF
Project Engineering
Project Milestone
Installation Drawing
Project Milestone
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Area Owner | Execution Owner
Sorter Layout Freeze
System Layout Freeze
Chute Position Freeze
Induction Freeze
Installation Start
Commissioning Start
Sales Handover Date
Gaylord Chute
Areas | Start (Expected) | End (Drop dead) | Due (Eng Target) | Department | Area Owner | Execution Owner
Chute Design
Xref (Sysm Comp)
MRF
Installation Drawing
Design and Fabrication
Areas
Detail Design
Xref (Sysm Comp)
MRF
Installation Drawing
Milestone - Sorter Support Layout
Area List
Detail Design, Chute Design, System Component (Xref), MRF, Installation Drawing, Project Milestone, Sorter Design, MHE Design, System Layout, System Safety, Project Activity, BGLS, Loop Sorter, Induction Unit, BG Conveyor
Detail Design, Chute, System Component (Xref), MRF, Installation Drawing, Project Milestone, Sorter, MHE Design, System Layout, System Safety, Project Activity, BGLS, Scanner, Induction Unit, BG Conveyor, Platform
Task Category List | Project Engineering, Project Layouts, Design Engineering, Documentation
Contact List | Alex Raff, Deep Gajjar, Xin Liu, Pierre Damis, Andrea Hosna, Kenleigh Dickinson, Rasmus Sorensen, James Bragg, David Blanco, Svaraj Patel, Jameson Fitzpatrick, Connor Bowman, Xavior Hakes
AEO Project Scope | Sorter Design
BGLS
Fencing and Safety Guarding
Platform
Chute Design
Project Milestone
BG Conveyor
Point Loads / Permitting
Chute Deisgn
Gaylord
Load Lane
Hospital
Recirculation
Detail Design, Chute Design, System Component (Xref), MRF, Installation Drawing, Project Milestone, Sorter, MHE Design, System Layout, System Safety, Project Activity, BGLS, Loop Sorter, Induction Unit, BG Conveyor
Formulas:
BGLS = [BGLS, row above]+[Loop Sorter, row above]

## MT Sub Systems
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Comments
1 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Systems Engineering | BGLS Sorter | [10 empty] | Sub - System
2 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Layout Freeze | BGLS Sorter | [10 empty] | Sorter BGLS | 1
3 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Document | BGLS Ordering Tool | [10 empty] | BG Conveyor | 2
4 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | MRF | BDK Supply Chain | [10 empty] | Chute | 3
5 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Systems Engineering | MCC Location | [10 empty] | General Project | 4
6 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Systems Engineering | Cable Tray | [10 empty] | Mechanical Permit | 5
7 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | MRF | Cable Tray | [10 empty] | Platform | 6
8 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Installation Drawing | LNS Sorter Section | [10 empty] | Project Activity | 7
9 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Installation Drawing | LNS ECO Layout | [10 empty] | Project Schedule | 8
10 | Logistics | Customer Name | Project Name | Sorter System | Sorter BGLS | ME | Install Date | Sorter Installation | [10 empty] | Safety Fence | 9
11 | Logistics | Customer Name | Project Name | Sorter System | Sorter Supports | ME | Detail Design | Sorter Supports | [10 empty] | Scanner | 10
12 | Logistics | Customer Name | Project Name | Sorter System | Sorter Supports | ME | Installation Drawing | Sorter Support Layout | [10 empty] | Sorter Supports | 11
13 | Logistics | Customer Name | Project Name | Sorter System | Sorter Supports | ME | MRF | ME Components | [10 empty] | System Layout | 12
14 | Logistics | Customer Name | Project Name | Sorter System | Sorter Supports | ME | MRF | Anchors | [10 empty] | System Safety | 13
20 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | Detail Design | Scanner | [10 empty] | Electrical Permit | 14
21 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | Systems Engineering | Scanner | [10 empty] | Electrical Documentation | 15
22 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | MRF | Scanner | [10 empty] | Installation Phase | 16
23 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | Design Approval | Scanner | [11 empty] | 17
24 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | Installation Drawing | Scanner Layout | [11 empty] | 18
25 | Logistics | Customer Name | Project Name | Sorter System | Scanner | ME | Install Date | Scanner Installation | [11 empty] | 19
30 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | Detail Design | Safety Fence | [11 empty] | 20
31 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | Install Date | Safety Fence Installation | [11 empty] | 21
32 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | Installation Drawing | Safety Fence Layout | [11 empty] | 22
33 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | Layout Freeze | Safety Fence | [11 empty] | 23
34 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | MRF | Safety Fence | [11 empty] | 24
35 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | MRF | Anchors | [11 empty] | 25
36 | Logistics | Customer Name | Project Name | Sorter System | Safety Fence | ME | Systems Engineering | Safety Fence
40 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | Detail Design | Platform | [10 empty] | Areas
41 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | Install Date | Platform Installation | [10 empty] | Activity | 1
42 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | Installation Drawing | Platform Layout | [10 empty] | As-Builds | 2
43 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | Layout Freeze | Platform | [10 empty] | Detail Design | 3
44 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | MRF | Platform | [10 empty] | Document | 4
45 | Logistics | Customer Name | Project Name | Sorter System | Platform | ME | Systems Engineering | Platform | [10 empty] | Installation Drawing | 5
50 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Systems Engineering | Gaylord Chute | [10 empty] | Installation Phase | 6
51 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Design Approval | Gaylord Chute | [10 empty] | Design Approval | 7
52 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Detail Design | Gaylord Chute | [10 empty] | Install Date | 8
53 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Install Date | Gaylord Chute Installation | [10 empty] | Layout Freeze | 9
54 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Installation Drawing | Destination Layout | [10 empty] | Project Milestone | 10
55 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | Layout Freeze | Gaylord Chute | [10 empty] | MRF | 11
56 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | MRF | ME Components | [10 empty] | Point Load | 12
57 | Logistics | Customer Name | Project Name | Sorter System | Chute | ME | MRF | Anchors | [10 empty] | Systems Engineering | 13
60 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | System Layout: AEO BGLS | [10 empty] | System Layout | 14
61 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | System Layout : Navisworks | [10 empty] | Document | 15
62 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | Building | [10 empty] | Installation Phase | 16
63 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | Datum Line | [11 empty] | 17
64 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | As-Builds | System As-Builds : AEO BGLS | [11 empty] | 18
65 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Installation Drawing | Datum Line | [11 empty] | 19
66 | Logistics | Customer Name | Project Name | Sorter System | System Layout | ME | Layout Freeze | System Layout: AEO BGLS | [11 empty] | 20
70 | Logistics | Customer Name | Project Name | Sorter System | Mechanical Permit | ME | Systems Engineering | Point Loads | [11 empty] | 21
71 | Logistics | Customer Name | Project Name | Sorter System | Mechanical Permit | ME | MRF | PE Stamp and Calculations | [11 empty] | 22
72 | Logistics | Customer Name | Project Name | Sorter System | Mechanical Permit | ME | Project Milestone | ME Permit Package | [11 empty] | 23
80 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Project Meetings | [11 empty] | 24
81 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Site Survey | [11 empty] | 25
82 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Activity | PPP - Meetings
83 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Site Travel | [10 empty] | Contats
84 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Install: On Site Support | [10 empty] | Alex Raff | 1
85 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Document | PPP - Creation | [10 empty] | Deep Gajjar | 2
86 | Logistics | Customer Name | Project Name | Sorter System | General Project | ME | Document | Create ECTR Project Folder | [10 empty] | Xin Liu | 3
90 | Logistics | Customer Name | Project Name | Sorter System | Sorter Supports | ME | Systems Engineering | Sorter Supports | [10 empty] | Pierre Damis | 4
100 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Project Start | [10 empty] | Andrea Hosna | 5
101 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Site Available | [10 empty] | Kenleigh Dickenson | 6
102 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Electrical Installation | [10 empty] | Rasmus Sorensen | 7
103 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Comissioning | [10 empty] | James Bragg | 8
104 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | System Handover | [10 empty] | David Blanco | 9
105 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Installation Book | [10 empty] | Svaraj Patel | 10
106 | Logistics | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Installation Kickoff:Design Review 6 | [10 empty] | Jameson Fitzpatrick | 11
110 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Systems Engineering | BG Conveyor | [10 empty] | Connor Bowman | 12
111 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Detail Design | BG Conveyor | [10 empty] | Xavier Hakes | 13
112 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Document | MEL List | [10 empty] | Prolaan : Partick Herp | 15
113 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Install Date | BG Conveyor Installation | [10 empty] | Prolaan : Igor Strukan | 16
114 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Installation Drawing | BG Conveyor Layout | [10 empty] | Uriel Oliveiros | 17
115 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | Layout Freeze | BG Conveyor | [10 empty] | Pedro Resende | 18
116 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | MRF | BG Conveyor - BCH Supply Chain | [10 empty] | Andre Resende | 19
117 | Logistics | Customer Name | Project Name | Sorter System | BG Conveyor | ME | MRF | Anchors | [10 empty] | Tiera Foreman | 20
120 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | Document | Risk Assessment | [11 empty] | 21
121 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | Installation Drawing | Safety Labels | [11 empty] | 22
122 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | Installation Drawing | E-Stop Devices | [11 empty] | 23
123 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | MRF | Safety Labels | [11 empty] | 24
124 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | MRF | E-Stop Devices | [11 empty] | 25
125 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | Systems Engineering | Safety Labels
126 | Logistics | Customer Name | Project Name | Sorter System | System Safety | ME | Systems Engineering | E-Stop Devices

## DRAFT_ AEO
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Comments
1 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Systems Engineering | BGLS Sorter | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman |  | Sorter Length & Position, Destination Position & Count | Sub - System
2 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Systems Engineering | MCC Location | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman |  | ME/EE Coordination | Sorter BGLS | 1
3 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Systems Engineering | Cable Tray | [5 empty] | TBD | Connor Bowman | Connor Bowman |  | ME/EE Coordination | BG Conveyor | 2
4 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Document | BGLS Ordering Tool | [5 empty] | 2026-08-06 | Connor Bowman | Connor Bowman |  | BDK provided target date Aug 6, 2026 (TF) This Date is before sorter approval. OT on 8/15, FE approval 8/21 (PD) | Chute | 3
5 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | Document | BGLS Ordering Tool EE | [5 empty] | 2026-08-06 | Pedro Resende | Pedro Resende |  | After ME, EE needs to validate quantities and electrical devices before final list is released. | General Project | 4
6 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | Document | Master Data | [5 empty] | 2026-08-06 | Pedro Resende | Uriel Oliveiros |  | System and destinations devices quantites and definitions | Mechanical Permit | 5
7 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Installation Drawing | LNS Sorter Section | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  |  | Platform | 6
8 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Installation Drawing | LNS ECO Layout | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  |  | Project Activity | 7
9 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Install Date | Sorter Installation | [5 empty] | 2027-01-09 | Connor Bowman | Tiera Foreman |  |  | Project Schedule | 8
10 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Layout Freeze | BGLS Sorter | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman |  | Sorter Length & Position, Destination Position & Count | Safety Fence | 9
11 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | MRF | BDK Supply Chain | [5 empty] | 2026-08-06 | Connor Bowman | Connor Bowman |  |  | Scanner | 10
12 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | MRF | BDK Plus and Minus list | [5 empty] | 2026-08-06 | Pedro Resende | Uriel Oliveiros |  | Material list not included in the Ordering Tool that needs to be provided by BDK | Sorter Supports | 11
13 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | MRF | Cable Tray | [5 empty] | TBD | Connor Bowman | Connor Bowman |  | EE | System Layout | 12
14 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Systems Engineering | Scanner | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco |  |  | System Safety | 13
15 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Detail Design | Scanner | [5 empty] | 2026-08-29 | Connor Bowman | Connor Bowman |  | ME/EE/TPM Coordination | Electrical Permit | 14
16 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Installation Drawing | Scanner Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco |  |  | Electrical Documentation | 15
17 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Design Approval | Scanner | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman |  |  | Installation Phase | 16
18 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Install Date | Scanner Installation | [5 empty] | 2027-02-25 | Connor Bowman | Tiera Foreman |  |  | Chute: Recirc | 17
19 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | MRF | Scanner | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  | ME/EE/TPM Coordination | Chute: Load Lane | 18
20 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Systems Engineering | Safety Fence | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco |  |  | Chute: Hospital | 19
21 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Detail Design | Safety Fence | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  |  | Chute: Gaylord | 20
22 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Installation Drawing | Safety Fence Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco |  |  |  | 21
23 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Install Date | Safety Fence Installation | [5 empty] | 2027-02-20 | Connor Bowman | Tiera Foreman |  |  |  | 22
24 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Layout Freeze | Safety Fence | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman |  |  |  | 23
25 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | MRF | Safety Fence | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  |  |  | 24
26 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | MRF | Anchors | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman |  | Platform mounting |  | 25
27 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Project Start | [5 empty] | 2026-06-23 | Connor Bowman | Tiera Foreman
28 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Site Available | [5 empty] | 2027-01-09 | Connor Bowman | Tiera Foreman |  |  | Areas
29 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Electrical Installation | [5 empty] | 2027-01-29 | Connor Bowman | Tiera Foreman |  |  | Activity | 1
30 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Comissioning | [5 empty] | 2027-03-05 | Connor Bowman | Tiera Foreman |  |  | As-Builds | 2
31 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | System Handover | [5 empty] | 2027-04-08 | Connor Bowman | Tiera Foreman |  |  | Detail Design | 3
32 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Installation Book | [5 empty] | 2026-09-11 | Connor Bowman | Connor Bowman |  | Mechanical Instalaltion Package??? What is required? | Document | 4
33 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Installation Kickoff:Design Review 6 | [5 empty] | 2026-12-03 | Connor Bowman | Connor Bowman |  | Engineering to Installation Handover | Installation Drawing | 5
34 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 1 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | Installation Phase | 6
35 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 2 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | Design Approval | 7
36 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 3 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | Install Date | 8
37 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 4 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | Layout Freeze | 9
38 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 5 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | Project Milestone | 10
39 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 6 - EE support | [5 empty] | 2026-11-08 | Pedro Resende | Pedro Resende |  | EE/ME to run the meeting with TPMs | MRF | 11
40 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Systems Engineering | Platform | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco |  |  | Point Load | 12
41 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Detail Design | Platform | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman |  | May need beams under BGLS / Fencing at EOL chute. We can make a prelim suggestion for platform area | Systems Engineering | 13
42 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Installation Drawing | Platform Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco |  |  | System Layout | 14
43 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Install Date | Platform Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar |  | Document | 15
44 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Layout Freeze | Platform | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman |  |  | Installation Phase | 16
45 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | MRF | Platform | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 17
46 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | Systems Engineering | Point Loads | [5 empty] | 2026-08-03 | Connor Bowman | David Blanco |  |  |  | 18
47 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | Project Milestone | ME Permit Package | [5 empty] | 2026-09-18 | Connor Bowman | Tiera Foreman |  | Completed calculations and stamping |  | 19
48 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | MRF | PE Stamp and Calculations | [5 empty] | 2026-08-21 | Connor Bowman | Connor Bowman |  |  |  | 20
49 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Electrical installation binders | [5 empty] | 2026-11-18 | Pedro Resende | Pedro Resende |  |  |  | 21
50 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Generate EPLAN Cable Labels | [5 empty] | 2026-11-18 | Pedro Resende | Uriel Oliveiros |  |  |  | 22
51 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Generate EPLAN Device Labels | [5 empty] | 2026-11-18 | Pedro Resende | Uriel Oliveiros |  |  |  | 23
52 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Level 6 Check List | [5 empty] | 2026-11-18 | Pedro Resende | Pedro Resende |  | To be ready for installation |  | 24
53 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Spare Parts | [5 empty] | 2026-11-28 | Pedro Resende | Pedro Resende |  |  |  | 25
54 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Asbuilt Electrical Documentation | [5 empty] | TBD | Pedro Resende | Pedro Resende
55 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | eDoc - EE Review | [5 empty] | TBD | Pedro Resende | Pedro Resende |  |  | Contats
56 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | BID Package - EE support | [5 empty] | TBD | Pedro Resende | Andre Resende |  | Procurment team to define date | Alex Raff | 1
57 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Chute Cable Trays / Routing - Installation Instruction EE/ME | [5 empty] | 2026-11-18 | Pedro Resende | Andre Resende |  |  | Deep Gajjar | 2
58 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Project Meetings | [5 empty] | TBD | Connor Bowman | Connor Bowman |  |  | Xin Liu | 3
59 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | Project Meetings | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros |  |  | Pierre Damis | 4
60 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Site Survey | [5 empty] | 2026-07-20 | Connor Bowman | Connor Bowman |  |  | Andrea Hosna | 5
61 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | PPP - Meetings | [5 empty] | TBD | Connor Bowman | Connor Bowman |  |  | Kenleigh Dickenson | 6
62 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | PPP - Meetings | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros |  |  | Rasmus Sorensen | 7
63 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Site Travel | [5 empty] | TBD | Connor Bowman | Connor Bowman |  |  | James Bragg | 8
64 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Install: On Site Support | [5 empty] | 2026-12-21 | Connor Bowman | Connor Bowman |  |  | David Blanco | 9
65 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Document | PPP - Creation | [5 empty] | 2026-07-15 | Connor Bowman | Connor Bowman |  |  | Svaraj Patel | 10
66 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Document | PPP - Creation | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros |  |  | Jameson Fitzpatrick | 11
67 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Document | Create ECTR Project Folder | [5 empty] | 2026-06-24 | Connor Bowman | Pierre Damis |  |  | Connor Bowman | 12
68 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Permit | EE | Project Milestone | EE Permit Package | [5 empty] | 2026-08-23 | Pedro Resende | Uriel Oliveiros |  |  | Xavier Hakes | 13
69 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Permit | EE | MRF | PE Stamp | [5 empty] | 2026-08-23 | Pedro Resende | Uriel Oliveiros |  |  | Prolaan : Partick Herp | 15
70 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | Power calculation - System 24VDC | [5 empty] | 2026-08-22 | Pedro Resende | Uriel Oliveiros |  | To include all system power reference to the calculation | Prolaan : Igor Strukan | 16
71 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | Power calculation - System 480VAC | [5 empty] | 2026-08-22 | Pedro Resende | Uriel Oliveiros |  | To include all system power reference to the calculation | Uriel Oliveiros | 17
72 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | Reference Designation RDS | [5 empty] | 2026-08-22 | Pedro Resende | Pedro Resende |  | BG Standard documentation | Pedro Resende | 18
73 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | E-Stop Interface Document | [5 empty] | 2026-08-22 | Pedro Resende | Pedro Resende |  | BG Standard documentation | Andre Resende | 19
74 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | EPLAN Electrical Schematic | [5 empty] | 2026-10-29 | Pedro Resende | Uriel Oliveiros |  |  | Tiera Foreman | 20
75 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Systems Engineering | BDK Cabinet Rating plates Request | [5 empty] | 2026-10-29 | Pedro Resende | Uriel Oliveiros |  | Request BDK to print the cabinet Rating plate |  | 21
76 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | E-Brackets list to ME team | [5 empty] | 2026-08-30 | Pedro Resende | Pedro Resende |  | To share all electrical devices list with ME for brackets confirmation |  | 22
77 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | Cable grafical overview Excel - Power/control | [5 empty] | 2026-10-29 | Pedro Resende | Uriel Oliveiros |  |  |  | 23
78 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | IO-List | [5 empty] | 2026-10-29 | Pedro Resende | Uriel Oliveiros |  |  |  | 24
79 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Installation Drawing | Test Measurement Point (TMP) ME/EE | [5 empty] | 2026-08-22 | Pedro Resende | Pedro Resende |  |  |  | 25
80 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Systems Engineering | Recirculation Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar
81 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Detail Design | Recirculation Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen
82 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
83 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Design Approval | Recirculation Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
84 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Install Date | Recirculation Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
85 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Layout Freeze | Recirculation Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
86 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | EE | MRF | EE Components | [5 empty] | 2026-09-09 | Pedro Resende | Uriel Oliveiros
87 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
88 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
89 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Systems Engineering | Load Lane Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar
90 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Detail Design | Load Lane Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen
91 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
92 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Design Approval | Load Lane Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
93 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Install Date | Load Lane Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
94 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Layout Freeze | Load Lane Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
95 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | EE | MRF | EE Components | [5 empty] | 2026-09-09 | Pedro Resende | Uriel Oliveiros
96 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
97 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
98 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Systems Engineering | Hospital Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar
99 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Detail Design | Hospital Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen
100 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
101 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Design Approval | Hospital Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
102 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Install Date | Hospital Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
103 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Layout Freeze | Hospital Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
104 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | EE | MRF | EE Components | [5 empty] | 2026-09-09 | Pedro Resende | Uriel Oliveiros
105 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
106 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
107 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Systems Engineering | Gaylord Chute | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco
108 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Detail Design | Gaylord Chute | [5 empty] | 2026-07-31 | Connor Bowman | Rasmus Sorensen
109 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
110 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Design Approval | Gaylord Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
111 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Install Date | Gaylord Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
112 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Layout Freeze | Gaylord Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
113 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | EE | MRF | EE Components | [5 empty] | 2026-09-09 | Pedro Resende | Uriel Oliveiros
114 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar | Confirm if brackets are needed
115 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
116 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Systems Engineering | BG Conveyor | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | James Bragg | Reference Designation, conveyor block and attributes
117 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Detail Design | BG Conveyor | [5 empty] | TBD | Connor Bowman | Xin Liu |  | DOC_1561814_1009_2025_06_10T09_18_41_789.docx
118 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Document | MEL List | [5 empty] | TBD | Connor Bowman | Tiera Foreman
119 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Installation Drawing | BG Conveyor Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
120 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Install Date | BG Conveyor Installation | [5 empty] | 2027-02-17 | Tiera Foreman | Tiera Foreman
121 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Layout Freeze | BG Conveyor | [5 empty] | 2026-08-21 | Tiera Foreman | Tiera Foreman
122 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | MRF | BG Conveyor - BCH Supply Chain | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman
123 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | MRF | Anchors | [5 empty] | 2026-11-02 | Connor Bowman | Connor Bowman
124 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | Install: On Site Support | [5 empty] | TBD | Pedro Resende | Andre Resende
125 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Systems Engineering | Safety Labels | [5 empty] | 2026-09-15 | Connor Bowman | David Blanco
126 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Systems Engineering | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman
127 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Detail Design | Safety Labels | [6 empty] | Connor Bowman | Connor Bowman
128 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Document | Risk Assessment | [5 empty] | 2026-09-15 | Connor Bowman | Connor Bowman
129 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Installation Drawing | Safety Labels | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
130 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Installation Drawing | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
131 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | MRF | Safety Labels | [5 empty] | 2026-01-07 | Connor Bowman | Connor Bowman |  | P.D: Pushed back from project schedule plan 9/30
132 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | MRF | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman
133 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Systems Engineering | System Layout: AEO BGLS | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman
134 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Systems Engineering | System Layout : Navisworks | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman
135 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Systems Engineering | Building | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman
136 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | EE | Systems Engineering | Newtwork Layout: Visio | [5 empty] | 2026-08-26 | Pedro Resende | Uriel Oliveiros
137 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | EE | Systems Engineering | Network and Power Drop Layout | [5 empty] | 2026-08-26 | Pedro Resende | Uriel Oliveiros
138 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Systems Engineering | Datum Line | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman
139 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | As-Builds | System As-Builds : AEO BGLS | [5 empty] | TBD | Connor Bowman | David Blanco
140 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Installation Drawing | Datum Line | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
141 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Layout Freeze | System Layout: AEO BGLS | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman
142 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | Systems Engineering | Sorter Supports | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar
143 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | Detail Design | Sorter Supports | [5 empty] | N/A | Connor Bowman | Rasmus Sorensen | Deep Gajjar
144 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | Installation Drawing | Sorter Support Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco
145 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
146 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | MRF | Anchors | [5 empty] | 2026-11-02 | Connor Bowman | Connor Bowman

## DRAFT_ CS_ Adidas
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Comments
0 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Project Schedule | ME | Project Milestone | Project Start | [10 empty] | Sub - System
1 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Detail Design | Apparel Chute | [10 empty] | Sorter BGLS | 1
2 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | General Project | ME | Activity | Install: Kick-Off Design Review | [10 empty] | BG Conveyor | 2
3 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | General Project | ME | Activity | Site Travel | [10 empty] | Chute | 3
4 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | General Project | ME | Systems Engineering | Create ECTR Project Folder | [10 empty] | General Project | 4
5 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Systems Engineering | Adidas_ System Layout | [10 empty] | Mechanical Permit | 5
6 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Systems Engineering | System Layout : Navisworks | [10 empty] | Platform | 6
7 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Systems Engineering | Building | [10 empty] | Project Activity | 7
8 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Systems Engineering | Datum Line | [10 empty] | Project Schedule | 8
9 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Safety | ME | Systems Engineering | Safety Labels | [10 empty] | Safety Fence | 9
10 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Systems Engineering | Apparel Chute | [10 empty] | Scanner | 10
11 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Layout Freeze | System Layout : Adidas Chute Replacement | [10 empty] | Sorter Supports | 11
12 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Layout Freeze | Apparel Chute | [10 empty] | System Layout | 12
13 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Steel | [10 empty] | System Safety | 13
14 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Plastic | [10 empty] | Electrical Permit | 14
15 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Purchased Items | [10 empty] | Electrical Documentation | 15
16 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | FESTO Components | [10 empty] | Installation Phase | 16
17 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Hardware | [11 empty] | 17
18 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Anchors | [11 empty] | 18
19 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | MRF | Wood | [11 empty] | 19
20 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Safety | ME | MRF | Safety Labels | [11 empty] | 20
21 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | Installation Drawing | Datum Line | [11 empty] | 21
22 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Safety | ME | Installation Drawing | Safety Labels | [11 empty] | 22
23 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Installation Drawing | Destination Layout | [11 empty] | 23
24 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Installation Drawing | Pneumatic Layout | [11 empty] | 24
25 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Installation Drawing | Destination Support Layout | [11 empty] | 25
26 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Project Milestone | First Article - Fabrication
27 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Project Milestone | Apparel Chute - First Article | [10 empty] | Areas
28 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Detail Design | Design Updates | [10 empty] | Activity | 1
29 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Project Milestone | Project - Fabrication & Pre-Assembly | [10 empty] | As-Builds | 2
30 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Project Milestone | Staging | [10 empty] | Detail Design | 3
31 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Install Date | Decomission Exisitng Chutes | [10 empty] | Document | 4
32 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | General Project | ME | Activity | Install: On Site Support | [10 empty] | Installation Drawing | 5
33 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Chute | ME | Install Date | Apparel Chute Installation | [10 empty] | Installation Phase | 6
34 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Project Schedule | ME | Project Milestone | Comissioning | [10 empty] | Design Approval | 7
35 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | Project Schedule | ME | Project Milestone | System Handover | [10 empty] | Install Date | 8
36 | Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Layout | ME | As-Builds | System Layout: Adidas Chute Replacement | [9 empty] | RedLine within 5 days of leaving site | Layout Freeze | 9
| Customer Support | Adidas | Adidas Chute Replacement | BS25 - Belt Tray | System Safety | ME | Document | Risk Assessment | [9 empty] | Is this needed? | Project Milestone | 10
[19 empty] | MRF | 11
[19 empty] | Point Load | 12
[19 empty] | Systems Engineering | 13
[19 empty] | System Layout | 14
[19 empty] | Document | 15
[19 empty] | Installation Phase | 16
17
18
19
20
21
22
23
24
25
Contats
[19 empty] | Alex Raff | 1
[19 empty] | Deep Gajjar | 2
[19 empty] | Xin Liu | 3
[19 empty] | Pierre Damis | 4
[19 empty] | Andrea Hosna | 5
[19 empty] | Kenleigh Dickenson | 6
[19 empty] | Rasmus Sorensen | 7
[19 empty] | James Bragg | 8
[19 empty] | David Blanco | 9
[19 empty] | Svaraj Patel | 10
[19 empty] | Jameson Fitzpatrick | 11
[19 empty] | Connor Bowman | 12
[19 empty] | Xavier Hakes | 13
[19 empty] | Prolaan : Partick Herp | 15
[19 empty] | Prolaan : Igor Strukan | 16
[19 empty] | Uriel Oliveiros | 17
[19 empty] | Pedro Resende | 18
[19 empty] | Andre Resende | 19
[19 empty] | Tiera Foreman | 20
21
22
23
24
25

## DRAFT_CS_AEO
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Comments
10 | Customer Support | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Site Survey | Completed | [5 empty] | James Bragg |  |  |  | Sub - System
12 | Customer Support | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Site Travel | Pending Update | [5 empty] | James Bragg |  |  |  | Sorter BGLS | 1
13 | Customer Support | Customer Name | Project Name | Sorter System | General Project | ME | Activity | Install: On Site Support | Pending Update | [5 empty] | James Bragg |  |  |  | BG Conveyor | 2
31 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | As-Builds | System As-Builds : AEO | Pending Update | [5 empty] | James Bragg |  |  |  | Chute | 3
1 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | Detail Design | Gaylord Chute | Completed | [5 empty] | James Bragg |  |  |  | General Project | 4
21 | Customer Support | Customer Name | Project Name | Sorter System | Sorter Netting | ME | Detail Design | Netting | On schedule | [5 empty] | James Bragg |  |  | Steel and Netting Pending | Mechanical Permit | 5
35 |  |  |  |  | Chute | ME | Detail Design | Robot Units Frame | On schedule | [5 empty] | James Bragg |  |  |  | Platform | 6
8 | Customer Support | Customer Name | Project Name | Sorter System | General Project | ME | Document | Create ECTR Project Folder | Pending Update | [5 empty] | James Bragg |  |  | Confirm If needed | Project Activity | 7
4 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | Install Date | Gaylord Chute Installation | Pending Update | [5 empty] | James Bragg |  |  | Pending Team Meeting 7/21 | Project Schedule | 8
5 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | Installation Drawing | Destination Layout | On schedule | [5 empty] | James Bragg |  |  |  | Safety Fence | 9
25 | Customer Support | Customer Name | Project Name | Sorter System | Sorter Netting | ME | Installation Drawing | Netting Layout | On schedule | [5 empty] | James Bragg |  |  |  | Scanner | 10
26 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | Installation Drawing | Datum Line | Completed | [5 empty] | James Bragg |  |  |  | Sorter Supports | 11
32 | Customer Support | Customer Name | Project Name | Sorter System | System Safety | ME | Installation Drawing | Safety Labels | Pending Update | [5 empty] | James Bragg |  |  |  | System Layout | 12
38 |  |  |  |  | Chute | ME | Installation Drawing | Robot Units Frame | On schedule | [5 empty] | James Bragg |  |  |  | System Safety | 13
3 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | MRF | ME Components | Completed | [5 empty] | James Bragg |  |  |  | Electrical Permit | 14
4 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | MRF | Anchors | Completed | [5 empty] | James Bragg |  |  |  | Electrical Documentation | 15
23 | Customer Support | Customer Name | Project Name | Sorter System | Sorter Netting | ME | MRF | Steel | On schedule | [5 empty] | James Bragg |  |  |  | Installation Phase | 16
24 | Customer Support | Customer Name | Project Name | Sorter System | Sorter Netting | ME | MRF | Netting Material | On schedule | [5 empty] | James Bragg |  |  |  | Sorter Netting | 17
33 | Customer Support | Customer Name | Project Name | Sorter System | System Safety | ME | MRF | Safety Labels | On schedule | [5 empty] | James Bragg |  |  |  |  | 18
37 |  |  |  |  | Chute | ME | MRF | Robot Units | On schedule | [5 empty] | James Bragg |  |  |  |  | 19
15 | Customer Support | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Site Available | Pending Update | [5 empty] | James Bragg |  |  | Pending Team Meeting 7/21 |  | 20
19 | Customer Support | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Installation Book | On schedule | [5 empty] | James Bragg |  |  |  |  | 21
20 | Customer Support | Customer Name | Project Name | Sorter System | Project Schedule | ME | Project Milestone | Installation Kickoff:Design Review 6 | Pending Update | [5 empty] | James Bragg |  |  |  |  | 22
2 | Customer Support | Customer Name | Project Name | Sorter System | Chute | ME | Systems Engineering | Gaylord Chute | Completed | [5 empty] | James Bragg |  |  |  |  | 23
22 | Customer Support | Customer Name | Project Name | Sorter System | Sorter Netting | ME | Systems Engineering | Netting | On schedule | [5 empty] | James Bragg |  |  |  |  | 24
27 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | System Layout: AEO BGLS | On schedule | [5 empty] | James Bragg |  |  |  |  | 25
28 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | System Layout : Navisworks | On schedule | [5 empty] | James Bragg
29 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | Building | Completed | [5 empty] | James Bragg |  |  |  | Areas
30 | Customer Support | Customer Name | Project Name | Sorter System | System Layout | ME | Systems Engineering | Datum Line | Completed | [5 empty] | James Bragg |  |  |  | Activity | 1
34 | Customer Support | Customer Name | Project Name | Sorter System | System Safety | ME | Systems Engineering | Safety Labels | On schedule | [5 empty] | James Bragg |  |  |  | As-Builds | 2
36 |  |  |  |  | Chute | ME | Systems Engineering | Robot Units | On schedule | [5 empty] | James Bragg |  |  |  | Detail Design | 3
[19 empty] | Document | 4
[19 empty] | Installation Drawing | 5
[19 empty] | Installation Phase | 6
[19 empty] | Design Approval | 7
[19 empty] | Install Date | 8
[19 empty] | Layout Freeze | 9
[19 empty] | Project Milestone | 10
[19 empty] | MRF | 11
[19 empty] | Point Load | 12
[19 empty] | Systems Engineering | 13
[19 empty] | System Layout | 14
[19 empty] | Document | 15
[19 empty] | Installation Phase | 16
17
18
19
20
21
22
23
24
25
Contats
[19 empty] | Alex Raff | 1
[19 empty] | Deep Gajjar | 2
[19 empty] | Xin Liu | 3
[19 empty] | Pierre Damis | 4
[19 empty] | Andrea Hosna | 5
[19 empty] | Kenleigh Dickenson | 6
[19 empty] | Rasmus Sorensen | 7
[19 empty] | James Bragg | 8
[19 empty] | David Blanco | 9
[19 empty] | Svaraj Patel | 10
[19 empty] | Jameson Fitzpatrick | 11
[19 empty] | Connor Bowman | 12
[19 empty] | Xavier Hakes | 13
[19 empty] | Prolaan : Partick Herp | 15
[19 empty] | Prolaan : Igor Strukan | 16
[19 empty] | Uriel Oliveiros | 17
[19 empty] | Pedro Resende | 18
[19 empty] | Andre Resende | 19
[19 empty] | Tiera Foreman | 20
21
22
23
24
25

## DRAFT_ SAX9_ SCL3
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Comments
3 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Detail Design | End of Line Chute | On schedule |  |  |  |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  |  | Sub - System
4 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Detail Design | Induction Chute | On schedule |  |  |  |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  |  | Sorter BGLS | 1
5 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Detail Design | Mobile Chute | On schedule |  |  |  |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  |  | BG Conveyor | 2
6 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Detail Design | Static Chute | On schedule |  |  |  |  | 2026-05-26 | Svaraj Patel | Rasmus Sorensen |  |  | Chute | 3
1 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | Activity | Site Survey | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | General Project | 4
40 | Logistics | Amazon | SCL3 | BGLS | Induction Unit | ME | Systems Engineering | Induction Unit | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Mechanical Permit | 5
41 | Logistics | Amazon | SCL3 | BGLS | Mechanical Permit | ME | Systems Engineering | Point Loads | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Platform | 6
42 | Logistics | Amazon | SCL3 | BGLS | Safety Fence | ME | Systems Engineering | Safety Fence | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Project Activity | 7
14 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Document | BGLS Ordering Tool | Completed |  |  |  |  | 2026-04-15 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Project Schedule | 8
43 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Systems Engineering | BGLS Sorter | Completed |  |  |  |  | 2026-04-15 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Safety Fence | 9
44 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Systems Engineering | ECO Layout | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Scanner | 10
45 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Systems Engineering | MCC Location | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Sorter Supports | 11
8 | Logistics | Amazon | SCL3 | BGLS | Sorter Supports | ME | Detail Design | Sorter Supports | Completed |  |  |  |  | 2026-07-27 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | System Layout | 12
47 | Logistics | Amazon | SCL3 | BGLS | Sorter Supports | ME | Systems Engineering | Sorter Supports | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | System Safety | 13
48 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | Systems Engineering | Building | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Electrical Permit | 14
49 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | Systems Engineering | Datum Line | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Electrical Documentation | 15
50 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | Systems Engineering | System Layout : Navisworks | Completed |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Installation Phase | 16
51 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | Systems Engineering | System Layout: SCL3 | Completed |  |  |  |  | 2026-04-03 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Induction Unit | 17
16 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Installation Drawing | DES ECO Layout | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 18
17 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Installation Drawing | Destination Chutes | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 19
18 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Installation Drawing | Destination Transitions | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 20
19 | Logistics | Amazon | SCL3 | BGLS | Induction Unit | ME | Installation Drawing | Induction Unit | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 21
20 | Logistics | Amazon | SCL3 | BGLS | Safety Fence | ME | Installation Drawing | Safety Fence Layout | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 22
21 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Installation Drawing | LNS ECO Layout | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 23
22 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Installation Drawing | LNS Sorter Section | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 24
23 | Logistics | Amazon | SCL3 | BGLS | Sorter Supports | ME | Installation Drawing | Sorter Support Layout | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  |  | 25
2 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | As-Builds | System As-Builds | On schedule |  |  |  |  | 2026-11-23 | Svaraj Patel | David Blanco
24 | Logistics | Amazon | SCL3 | BGLS | System Layout | ME | Installation Drawing | Datum Line | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  | Areas
25 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | Installation Drawing | Egress, Maintenance Operator | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  | Activity | 1
26 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | Installation Drawing | Safety Labels | On schedule |  |  |  |  | 2026-08-24 | Svaraj Patel | David Blanco | James Bragg |  | As-Builds | 2
11 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | Document | Create ECTR Project Folder | On schedule |  |  |  |  | 2026-04-03 | Svaraj Patel | Pierre Damis | Pierre Damis |  | Detail Design | 3
7 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Detail Design | Recirculation Chute | On schedule |  |  |  |  | 2026-07-27 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Document | 4
12 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | Document | Installation Book | On schedule |  |  |  |  | 2026-09-01 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Installation Drawing | 5
13 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | Document | PPP - Creation | On schedule |  |  |  |  | 2026-04-03 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Installation Phase | 6
27 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | MRF | Installation Drawing Prints | On schedule |  |  |  |  | 2026-09-01 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Design Approval | 7
28 | Logistics | Amazon | SCL3 | BGLS | Mechanical Permit | ME | MRF | PE Stamp and Calculations | On schedule |  |  |  |  | 2026-04-03 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Install Date | 8
38 | Logistics | Amazon | SCL3 | BGLS | Project Schedule | ME | Project Milestone | Installation Kickoff:Design Review 6 | On schedule |  |  |  |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Layout Freeze | 9
30 | Logistics | Amazon | SCL3 | BGLS | Safety Fence | ME | MRF | Anchors | On schedule |  |  |  |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Project Milestone | 10
31 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | MRF | BDK Supply Chain | On schedule |  |  |  |  | 2026-04-03 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | MRF | 11
32 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | MRF | Cable Tray | On schedule |  |  |  |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Point Load | 12
33 | Logistics | Amazon | SCL3 | BGLS | Sorter Supports | ME | MRF | Anchors | On schedule |  |  |  |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Systems Engineering | 13
34 | Logistics | Amazon | SCL3 | BGLS | Sorter Supports | ME | MRF | ME Components | On schedule |  |  |  |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | System Layout | 14
9 | Logistics | Amazon | SCL4 | BGLS | System Safety | ME | Detail Design | EE Device Brackets | On schedule |  |  |  |  | 2026-07-27 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Document | 15
35 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | MRF | EE Device Brackets | On schedule |  |  |  |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  | Installation Phase | 16
36 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | MRF | Safety Equipment | On schedule |  |  |  |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 17
37 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | MRF | Safety Labels | On schedule |  |  |  |  | 2026-08-04 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 18
53 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | Systems Engineering | Safety Labels | On schedule |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 19
15 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | Document | Risk Assessment | Pending Update |  |  |  |  | TBD | Svaraj Patel | Pierre Damis | Pierre Damis |  |  | 20
39 | Logistics | Amazon | SCL3 | BGLS | Chute | ME | Systems Engineering | Destinations | Pending Update |  |  |  |  | 2026-07-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 21
10 | Logistics | Amazon | SCL3 | BGLS | General Project | ME | Document | Spare Parts List | Pending Update |  |  |  |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 22
29 | Logistics | Amazon | SCL3 | BGLS | Safety Fence | ME | MRF | Safety Fence | Pending Update |  |  |  |  | TBD | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 23
46 | Logistics | Amazon | SCL3 | BGLS | Sorter BGLS | ME | Systems Engineering | Cable Tray | Pending Update |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 24
52 | Logistics | Amazon | SCL3 | BGLS | System Safety | ME | Systems Engineering | EE Device Brackets | Pending Update |  |  |  |  | 2026-06-24 | Svaraj Patel | Svaraj Patel | Svaraj Patel |  |  | 25
Contats
[19 empty] | Alex Raff | 1
[19 empty] | Deep Gajjar | 2
[19 empty] | Xin Liu | 3
[19 empty] | Pierre Damis | 4
[19 empty] | Andrea Hosna | 5
[19 empty] | Kenleigh Dickenson | 6
[19 empty] | Rasmus Sorensen | 7
[19 empty] | James Bragg | 8
[19 empty] | David Blanco | 9
[19 empty] | Svaraj Patel | 10
[19 empty] | Jameson Fitzpatrick | 11
[19 empty] | Connor Bowman | 12
[19 empty] | Xavier Hakes | 13
[19 empty] | Prolaan : Partick Herp | 15
[19 empty] | Prolaan : Igor Strukan | 16
[19 empty] | Uriel Oliveiros | 17
[19 empty] | Pedro Resende | 18
[19 empty] | Andre Resende | 19
[19 empty] | Tiera Foreman | 20
21
22
23
24
25

## Delete_ AEO
# | Division | Customer | Project Name | System | Sub System | ENG | Area | Deliverable | Status | Eng Hrs | Duration | Min Date | Max Date | Target Date | Project Lead | Area Owner | Execution Owner | Review Date | Min Note | Schedule Notes | Eng Terminology | Planning Notes | Target Note | Comments
70 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | Power calculation - System 24VDC | [5 empty] | 2026-08-23 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [6 empty] | To include all system power reference to the calculation | Sub - System |  | X
71 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | Power calculation - System 480VAC | [5 empty] | 2026-08-01 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [6 empty] | To include all system power reference to the calculation | Sorter BGLS | 1
72 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | Reference Designation RDS | [5 empty] | 2026-08-23 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | BG Standard documentation | BG Conveyor | 2
73 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | E-Stop Interface Document | [5 empty] | 2026-08-23 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | BG Standard documentation | Chute: Gaylord | 3
74 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | EPLAN Electrical Schematic | [5 empty] | 2026-10-30 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Chute: Hospital | 4
75 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | System Engineering | BDK Cabinet Rating plates Request | [5 empty] | 2026-10-30 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [6 empty] | Request BDK to print the cabinet Rating plate | Chute: Load Lane | 5
136 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | EE | System Engineering | Newtwork Layout: Visio | [5 empty] | 2026-08-27 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Chute: Recirc | 6
137 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | EE | System Engineering | Network and Power Drop Layout | [5 empty] | 2026-08-27 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | General Project | 7
34 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 1 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Mechanical Permit | 8
35 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 2 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Platform | 9
36 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 3 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Project Activity | 10
37 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 4 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Project Schedule | 11
38 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 5 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Safety Fence | 12
39 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Activity | EE | Project Milestone | Check list - Design Review 6 - EE support | [5 empty] | 2026-11-09 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | EE/ME to run the meeting with TPMs | Scanner | 13
68 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Permit | EE | Project Milestone | EE Permit Package | [5 empty] | 2026-08-24 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Sorter Supports | 14
12 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | MRF | BDK Plus and Minus list | [5 empty] | 2026-08-06 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [6 empty] | Material list not included in the Ordering Tool that needs to be provided by BDK | System Layout | 15
69 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Permit | EE | MRF | PE Stamp | [5 empty] | 2026-08-24 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | System Safety | 16
86 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | EE | MRF | EE Components | [5 empty] | 2026-09-10 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Electrical Permit | 17
95 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | EE | MRF | EE Components | [5 empty] | 2026-09-10 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Electrical Documentation | 18
104 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | EE | MRF | EE Components | [5 empty] | 2026-09-10 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Installation phase
113 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | EE | MRF | EE Components | [5 empty] | 2026-09-10 | Pedro Resende | Uriel Oliveiros | Deep Gajjar
49 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Electrical installation binders | [5 empty] | 2026-11-19 | Pedro Resende | Pedro Resende | Deep Gajjar | [8 empty] | 1
50 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Generate EPLAN Cable Labels | [5 empty] | 2026-11-19 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Areas | 2
51 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Generate EPLAN Device Labels | [5 empty] | 2026-11-19 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Activity | 3
52 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Level 6 Check List | [5 empty] | 2026-11-19 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | To be ready for installation | As-Builds | 4
53 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Spare Parts | [5 empty] | 2026-11-29 | Pedro Resende | Pedro Resende | Deep Gajjar | [7 empty] | Chute | 5
54 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Asbuilt Electrical Documentation | [5 empty] | TBD | Pedro Resende | Pedro Resende | Deep Gajjar | [7 empty] | Detail Design | 6
55 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | eDoc - EE Review | [5 empty] | TBD | Pedro Resende | Pedro Resende | Deep Gajjar | [7 empty] | Installation Drawing | 7
56 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | BID Package - EE support | [5 empty] | TBD | Pedro Resende | Andre Resende | Deep Gajjar | [6 empty] | Procurment team to define date | Design Approval | 8
57 | Logistics | AEO | AEO Shipping Sorter | BGLS | Installation phase | EE | Installation phase | Chute Cable Trays / Routing - Installation Instruction EE/ME | [5 empty] | 2026-11-19 | Pedro Resende | Andre Resende | Deep Gajjar | [7 empty] | Install Date | 10
79 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Installation Drawing | Test Measurement Point (TMP) ME/EE | [5 empty] | 2026-08-23 | Pedro Resende | Pedro Resende | Deep Gajjar | [7 empty] | Layout Freeze | 11
5 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | Document | BGLS Ordering Tool EE | [5 empty] | 2026-08-06 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | After ME, EE needs to validate quantities and electrical devices before final list is released. | MRF | 12
6 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | EE | Document | Master Data | [5 empty] | 2026-08-06 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [6 empty] | System and destinations devices quantites and definitions | Point Load | 13
66 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Document | PPP - Creation | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Project Milestone | 14
76 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | E-Brackets list to ME team | [5 empty] | 2026-08-31 | Pedro Resende | Pedro Resende | Deep Gajjar | [6 empty] | To share all electrical devices list with ME for brackets confirmation | System Engineering | 15
77 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | Cable grafical overview Excel - Power/control | [5 empty] | 2026-10-30 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | System Layout | 16
78 | Logistics | AEO | AEO Shipping Sorter | BGLS | Electrical Documentation | EE | Detail Design | IO-List | [5 empty] | 2026-10-30 | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | System Layout | 17
59 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | Project Meetings | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Document | 18
62 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | PPP - Meetings | [5 empty] | TBD | Pedro Resende | Uriel Oliveiros | Deep Gajjar | [7 empty] | Installation phase
124 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | EE | Activity | Install: On Site Support | [5 empty] | TBD | Pedro Resende | Andre Resende | Deep Gajjar
1 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | System Engineering | BGLS Sorter | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  | Project Start - Approval Date | 4.2.1.2 Sorter Layout |  | Pending BDK OT Date |  | Sorter Length & Position, Destination Position & Count |  | 3
2 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | System Engineering | MCC Location | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design | Systems | Ref, System Eng Date |  | ME/EE Coordination | Pending | 6
3 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | System Engineering | Cable Tray | [5 empty] | TBD | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | ME/EE Coordination |  | ME/EE Coordination | ME
14 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | System Engineering | Scanner | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco | Deep Gajjar |  |  |  |  | ME/EE Coordination |  |  | EE
20 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | System Engineering | Safety Fence | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design?
40 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | System Engineering | Platform | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design? |  |  |  |  | Contats
46 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | System Engineering | Point Loads | [5 empty] | 2026-08-03 | Connor Bowman | David Blanco | Deep Gajjar |  |  | Not on schedule |  | Pending ME Permit package date |  |  | Alex Raff | 1
80 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | System Engineering | Recirculation Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design? |  |  |  |  | Deep Gajjar | 2
89 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | System Engineering | Load Lane Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design? |  |  |  |  | Xin Liu | 3
98 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | System Engineering | Hospital Chute | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design? |  |  |  |  | Pierre Damis | 4
107 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | System Engineering | Gaylord Chute | [5 empty] | 2026-07-31 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design? |  |  |  |  | Andrea Hosna | 5
116 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | System Engineering | BG Conveyor | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.1.4 Mechanical Detailed Design |  |  |  | Reference Designation, conveyor block and attributes | Kenleigh Dickenson | 6
125 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | System Engineering | Safety Labels | [5 empty] | 2026-09-15 | Connor Bowman | David Blanco | Deep Gajjar | [7 empty] | Rasmus Sorensen | 7
126 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | System Engineering | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | ME/EE Coordination |  |  | James Bragg | 8
133 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | System Engineering | System Layout: AEO BGLS | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.1.1 Mechanical Layout |  |  |  |  | David Blanco | 9
134 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | System Engineering | System Layout : Navisworks | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.1.1 Mechanical Layout |  |  |  |  | Svaraj Patel | 10
135 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | System Engineering | Building | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.1.1 Mechanical Layout |  |  |  |  | Jameson Fitzpatrick | 11
138 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | System Engineering | Datum Line | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.1.1 Mechanical Layout |  |  |  |  | Connor Bowman | 12
142 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | System Engineering | Sorter Supports | [5 empty] | N/A | Connor Bowman | David Blanco | Deep Gajjar |  |  | No sorter supports |  | Sorter Reinforcement Beams? |  |  | Xavier Hakes | 13
27 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Project Start | [5 empty] | 2026-06-23 | Connor Bowman | Tiera Foreman | Deep Gajjar | [7 empty] | Tiera Foreman | 14
28 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Site Available | [5 empty] | 2027-01-09 | Connor Bowman | Tiera Foreman | Deep Gajjar | [7 empty] | Prolaan : Partick Herp | 15
29 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Electrical Installation | [5 empty] | 2027-01-29 | Connor Bowman | Tiera Foreman | Deep Gajjar | [7 empty] | Prolaan : Igor Strukan | 16
30 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Comissioning | [5 empty] | 2027-03-05 | Connor Bowman | Tiera Foreman | Deep Gajjar | [7 empty] | Uriel Oliveiros | 17
31 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | System Handover | [5 empty] | 2027-04-08 | Connor Bowman | Tiera Foreman | Deep Gajjar | [7 empty] | Pedro Resende | 18
32 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Installation Book | [5 empty] | 2026-09-11 | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | Mechanical Instalaltion Package??? What is required? | Andre Resende | 18
33 | Logistics | AEO | AEO Shipping Sorter | BGLS | Project Schedule | ME | Project Milestone | Installation Kickoff:Design Review 6 | [5 empty] | 2026-12-03 | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | Engineering to Installation Handover | x
47 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | Project Milestone | ME Permit Package | [5 empty] | 2026-09-18 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | Not on schedule |  |  |  | Completed calculations and stamping
11 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | MRF | BDK Supply Chain | [5 empty] | 2026-08-06 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 5.1.3 Sorter Support Production and Shipping |  | Confirm OT date
13 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | MRF | Cable Tray | [5 empty] | TBD | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | EE
19 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | MRF | Scanner | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | ME/EE/TPM Coordination
25 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | MRF | Safety Fence | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar
26 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | MRF | Anchors | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | Platform mounting
45 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | MRF | Platform | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar | [7 empty] | Safety Equipment
48 | Logistics | AEO | AEO Shipping Sorter | BGLS | Mechanical Permit | ME | MRF | PE Stamp and Calculations | [5 empty] | 2026-08-21 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | Pending ME Permit package date |  |  | Print Installation Drawings
87 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
88 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
96 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
97 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
105 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
106 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
114 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | Confirm if brackets are needed
115 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | MRF | Anchors | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar
122 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | MRF | BG Conveyor - BCH Supply Chain | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | Confirm Conveyor Lead Time
123 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | MRF | Anchors | [5 empty] | 2026-11-02 | Connor Bowman | Connor Bowman | Deep Gajjar
131 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | MRF | Safety Labels | [5 empty] | 2026-01-07 | Connor Bowman | Connor Bowman | Deep Gajjar | [6 empty] | P.D: Pushed back from project schedule plan 9/30
132 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | MRF | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | ME/EE Coordination
145 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | MRF | ME Components | [5 empty] | N/A | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | No sorter supports
146 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | MRF | Anchors | [5 empty] | 2026-11-02 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | No sorter supports
10 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Layout Freeze | BGLS Sorter | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval |  | Pending BDK OT Date |  | Sorter Length & Position, Destination Position & Count
24 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Layout Freeze | Safety Fence | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
44 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Layout Freeze | Platform | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
85 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Layout Freeze | Recirculation Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
94 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Layout Freeze | Load Lane Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
103 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Layout Freeze | Hospital Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
112 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Layout Freeze | Gaylord Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
121 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Layout Freeze | BG Conveyor | [5 empty] | 2026-08-21 | Tiera Foreman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
141 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Layout Freeze | System Layout: AEO BGLS | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  | 4.2.7 FE Appproval
7 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Installation Drawing | LNS Sorter Section | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
8 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Installation Drawing | LNS ECO Layout | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
16 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Installation Drawing | Scanner Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
22 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Installation Drawing | Safety Fence Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
42 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Installation Drawing | Platform Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
82 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
91 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
100 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
109 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Installation Drawing | Destination Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
119 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Installation Drawing | BG Conveyor Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
129 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Installation Drawing | Safety Labels | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package
130 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Installation Drawing | E-Stop Devices | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | ME/EE Coordination
140 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | Installation Drawing | Datum Line | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | 4.2.3 Mechanical Installation Package |  | Installaton book + 2 weeks
144 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | Installation Drawing | Sorter Support Layout | [5 empty] | 2026-08-28 | Connor Bowman | David Blanco | Deep Gajjar |  |  | No sorter supports |  | Installaton book + 2 weeks
9 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Install Date | Sorter Installation | [5 empty] | 2027-01-09 | Connor Bowman | Tiera Foreman | Deep Gajjar
18 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Install Date | Scanner Installation | [5 empty] | 2027-02-25 | Connor Bowman | Tiera Foreman | Deep Gajjar
23 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Install Date | Safety Fence Installation | [5 empty] | 2027-02-20 | Connor Bowman | Tiera Foreman | Deep Gajjar
43 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Install Date | Platform Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
84 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Install Date | Recirculation Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
93 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Install Date | Load Lane Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
102 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Install Date | Hospital Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
111 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Install Date | Gaylord Chute Installation | [5 empty] | N/A | Connor Bowman | Tiera Foreman | Deep Gajjar
120 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Install Date | BG Conveyor Installation | [5 empty] | 2027-02-17 | Tiera Foreman | Tiera Foreman | Deep Gajjar
4 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter BGLS | ME | Document | BGLS Ordering Tool | [5 empty] | 2026-08-06 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | Not on schedule |  | Ref Sorter System Eng Date |  | BDK provided target date Aug 6, 2026 (TF) This Date is before sorter approval. OT on 8/15, FE approval 8/21 (PD)
65 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Document | PPP - Creation | [5 empty] | 2026-07-15 | Connor Bowman | Connor Bowman | Deep Gajjar
67 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Document | Create ECTR Project Folder | [5 empty] | 2026-06-24 | Connor Bowman | Pierre Damis | Deep Gajjar
118 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Document | MEL List | [5 empty] | TBD | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  |  |  | ME/EE/BCH Determine date
128 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Document | Risk Assessment | [5 empty] | 2026-09-15 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | Confirm Date
15 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Detail Design | Scanner | [5 empty] | 2026-08-29 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | ME/EE Coordination |  | ME/EE/TPM Coordination
21 | Logistics | AEO | AEO Shipping Sorter | BGLS | Safety Fence | ME | Detail Design | Safety Fence | [5 empty] | 2026-08-28 | Connor Bowman | Connor Bowman | Deep Gajjar
41 | Logistics | AEO | AEO Shipping Sorter | BGLS | Platform | ME | Detail Design | Platform | [5 empty] | 2026-07-31 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  | By Customer |  |  |  | May need beams under BGLS / Fencing at EOL chute. We can make a prelim suggestion for platform area
81 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Detail Design | Recirculation Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen | Deep Gajjar |  |  | By Customer
90 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Detail Design | Load Lane Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen | Deep Gajjar |  |  | By Customer
99 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Detail Design | Hospital Chute | [5 empty] | 2026-08-29 | Connor Bowman | Rasmus Sorensen | Deep Gajjar |  |  | By Customer
108 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Detail Design | Gaylord Chute | [5 empty] | 2026-07-31 | Connor Bowman | Rasmus Sorensen | Deep Gajjar |  |  | By Customer
117 | Logistics | AEO | AEO Shipping Sorter | BGLS | BG Conveyor | ME | Detail Design | BG Conveyor | [5 empty] | TBD | Connor Bowman | Xin Liu | Deep Gajjar |  |  |  |  | ME/EE Coordination |  | MEL List
127 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Safety | ME | Detail Design | Safety Labels | [6 empty] | Connor Bowman | Connor Bowman | Deep Gajjar
143 | Logistics | AEO | AEO Shipping Sorter | BGLS | Sorter Supports | ME | Detail Design | Sorter Supports | [5 empty] | N/A | Connor Bowman | Rasmus Sorensen | Deep Gajjar |  |  | No sorter supports
17 | Logistics | AEO | AEO Shipping Sorter | BGLS | Scanner | ME | Design Approval | Scanner | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar |  |  |  |  | ME/EE Coordination
83 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Recirc | ME | Design Approval | Recirculation Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar
92 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Load Lane | ME | Design Approval | Load Lane Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar
101 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Hospital | ME | Design Approval | Hospital Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar
110 | Logistics | AEO | AEO Shipping Sorter | BGLS | Chute: Gaylord | ME | Design Approval | Gaylord Chute | [5 empty] | 2026-08-21 | Connor Bowman | Tiera Foreman | Deep Gajjar
139 | Logistics | AEO | AEO Shipping Sorter | BGLS | System Layout | ME | As-Builds | System As-Builds : AEO BGLS | [5 empty] | TBD | Connor Bowman | David Blanco | Deep Gajjar
58 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Project Meetings | [5 empty] | TBD | Connor Bowman | Connor Bowman | Deep Gajjar
60 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Site Survey | [5 empty] | 2026-07-20 | Connor Bowman | Connor Bowman | Deep Gajjar
61 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | PPP - Meetings | [5 empty] | TBD | Connor Bowman | Connor Bowman | Deep Gajjar
63 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Site Travel | [5 empty] | TBD | Connor Bowman | Connor Bowman | Deep Gajjar
64 | Logistics | AEO | AEO Shipping Sorter | BGLS | General Project | ME | Activity | Install: On Site Support | [5 empty] | 2026-12-21 | Connor Bowman | Connor Bowman | Deep Gajjar |  |  |  |  | After Design Review 6?

## Delete_ CS_ Adidas
Division | Customer | Tag | Name | System | Sub System | Area | Deliverable | Status | Review Date | Seq | Wks | Days | Min Date | Min Date Notes | Max Date | Notes | Target Date | Target Note | Project Lead | Area Owner | Execution Owner | Comments
|  | 140 |  |  | Project Schedule | Milestone : Sched | Project Start |  |  | 0 | 1 | 7 |  |  |  |  | 2026-07-06 |  | Connor Bowman |  |  |  | Sub - System
Logistics | AEO | 52 | AEO Shipping Sorter | BGLS | Chute: Apparel | Detail Design | Apparel Chute |  |  | 1 | 4 | 28 |  |  |  |  | 2026-07-08 |  | Connor Bowman |  |  |  | Sorter : BGLS | 1
Logistics | AEO | 54 | AEO Shipping Sorter | BGLS | Chute: Apparel | MRF | Steel |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 |  | Connor Bowman |  |  |  | BG Conveyor | 2
|  | 55 |  |  | Chute: Apparel | MRF | Plastic |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 | [5 empty] | Chute: Apparel | 3
|  | 56 |  |  | Chute: Apparel | MRF | Purchased Items |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 | [5 empty] | Chute: Hospital | 4
|  | 57 |  |  | Chute: Apparel | MRF | FESTO Components |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 | [5 empty] | Chute: Load Lane | 5
|  | 58 |  |  | Chute: Apparel | MRF | Hardware |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 | [5 empty] | Chute: Recirculation | 6
|  | 59 | AEO Shipping Sorter | BGLS | Chute: Apparel | MRF | Anchors |  |  | 2 | 1 | 7 |  |  |  |  | 2026-08-05 |  | Connor Bowman |  |  |  | System Safety
|  | 61 |  |  | Chute: Apparel | MRF | Wood |  |  | 2 | 1 | 7 | #REF! |  |  |  | 2026-08-05
|  | 146 |  |  | Chute: Apparel | Milestone : Sched | First Article - Fabrication |  |  | 3 | 0 | 0 |  |  |  |  | 2026-08-12 | [5 empty] | General Project | 7
|  | 50 |  |  | Chute: Apparel | Milestone : Sched | Apparel Chute - First Article |  |  | 4 | 0 | 0 |  |  |  |  | 2026-08-12 | [5 empty] | Mechanical Permit | 8
|  | 60 |  |  | Chute: Apparel | Detail Design | Design Updates |  |  | 5 | 0 | 0 |  |  |  |  | 2026-08-12 | [5 empty] | Platform | 9
|  | 146 |  |  | Chute: Apparel | Milestone : Sched | Project - Fabrication & Pre-Assembly |  |  | 6 | 8 | 56 |  |  |  |  | 2026-08-12 | [5 empty] | Project Activity | 10
|  | 145 |  |  | Chute: Apparel | Milestone : Sched | Staging |  |  | 7 | 1 | 7 |  |  |  |  | 2026-10-07 | [5 empty] | Project Schedule | 11
|  | 58 | AEO Shipping Sorter | BGLS | Chute: Apparel | Milestone : Install Date | Decomission Exisitng Chutes |  |  | 8 | 1 | 7 |  |  |  |  | 2026-10-14 | [5 empty] | Safety Fence | 12
|  | 57 | AEO Shipping Sorter | BGLS | Chute: Apparel | Milestone : Install Date | Apparel Chute Installation |  |  | 9 | 3 | 21 |  |  |  |  | 2026-10-21 |  | Connor Bowman |  |  |  | Scanner | 13
|  | 143 |  |  | Project Schedule | Milestone : Sched | Comissioning |  |  | 10 | 2 | 14 |  |  |  |  | 2026-11-11 |  | Connor Bowman |  |  |  | Sorter Supports | 14
|  | 144 |  |  | Project Schedule | Milestone : Sched | System Handover |  |  | 11 | [6 empty] | 2026-11-25 |  | Connor Bowman
Logistics | AEO | 124 | AEO Shipping Sorter | BGLS | General Project | Activity | Site Travel | [11 empty] | Connor Bowman |  |  |  | System Layout | 15
Logistics | AEO | 125 | AEO Shipping Sorter | BGLS | General Project | Activity | Install: Kick-Off Design Review | [11 empty] | Connor Bowman
Logistics | AEO | 126 | AEO Shipping Sorter | BGLS | General Project | Activity | Install: On Site Support | [11 empty] | Connor Bowman |  |  |  |  | 16
|  | 106 | AEO Shipping Sorter | BGLS | System Layout | As-Builds | System Layout: Adidas Chute Replacement | [11 empty] | Connor Bowman
|  | 170 |  |  | General Project | Document | Create ECTR Project Folder
|  | 160 |  |  | System Safety | Document | Risk Assessment
Logistics | AEO | 56 | AEO Shipping Sorter | BGLS | Chute: Apparel | Installation Drawing | Destination Layout | [11 empty] | Connor Bowman
|  | 62 |  |  | Chute: Apparel | Installation Drawing | Pneumatic Layout | [5 empty] | #REF! | [10 empty] | 17
|  | 63 |  |  | Chute: Apparel | Installation Drawing | Destination Support Layout | [5 empty] | #REF! | [10 empty] | 18
|  | 104 | AEO Shipping Sorter | BGLS | System Layout | Installation Drawing | Datum Line | [11 empty] | Connor Bowman
|  | 163 |  |  | System Safety | Installation Drawing | Safety Labels | [15 empty] | Areas
|  | 51 | AEO Shipping Sorter | BGLS | Chute: Apparel | Milestone : Layout Freeze | Apparel Chute | [11 empty] | Connor Bowman |  |  |  | Activity | 1
|  | 105 | AEO Shipping Sorter | BGLS | System Layout | Milestone : Layout Freeze | System Layout : Adidas Chute Replacement | [11 empty] | Connor Bowman |  |  |  | As-Builds | 2
|  | 162 |  |  | System Safety | MRF | Safety Labels | [15 empty] | Chute | 3
Logistics | AEO | 50 | AEO Shipping Sorter | BGLS | Chute: Apparel | System Engineering | Apparel Chute | [11 empty] | Connor Bowman |  |  |  | Detail Design | 4
|  | 127 | AEO Shipping Sorter | BGLS | General Project | System Engineering | Create ECTR Project Folder | [11 empty] | Connor Bowman |  |  |  | Installation Drawing | 5
|  | 100 |  |  | System Layout | System Engineering | Adidas_ System Layout | [11 empty] | Connor Bowman |  |  |  | Milestone : Design Approval | 6
|  | 101 |  |  | System Layout | System Engineering | System Layout : Navisworks | [11 empty] | Connor Bowman |  |  |  | Milestone : Install Date | 7
Logistics | AEO | 102 | AEO Shipping Sorter | BGLS | System Layout | System Engineering | Building | [11 empty] | Connor Bowman |  |  |  | Milestone : Layout Freeze | 8
Logistics | AEO | 103 | AEO Shipping Sorter | BGLS | System Layout | System Engineering | Datum Line | [15 empty] | Milestone : Sched | 9
|  | 161 |  |  | System Safety | System Engineering | Safety Labels | [15 empty] | MRF | 10
[7 empty] | RedLine within 5 days of leaving site | [5 empty] | #REF! | [9 empty] | Point Load | 11
[13 empty] | #REF! | [9 empty] | Project Milestone | 12
[13 empty] | #REF! | [9 empty] | System Engineering | 13
[23 empty] | System Layout | 14
[17 empty] | Schedule Overlap | [5 empty] | System Layout | 15
[17 empty] | 2 |  |  | Days |  |  | Document | 16
[17 empty] | 0.28571 |  |  | Weeks |  |  |  | 17
18
For a limited time only
[17 empty] | Customer P.O |  |  | 2026-07-08 |  |  | Pending
[23 empty] | Safety Labels | 2
[23 empty] | Safety Equipment | 3
[23 empty] | E-Stop Brackets | 4
[23 empty] | Installation Book | 7
Eng contats
[23 empty] | Alex Raff | 1
[23 empty] | Deep Gajjar | 2
[23 empty] | Xin Liu | 3
[23 empty] | Pierre Damis | 4
[23 empty] | Andrea Hosna | 5
[23 empty] | Kenleigh Dickenson | 6
[23 empty] | Rasmus Sorensen | 7
[23 empty] | James Bragg | 8
[23 empty] | David Blanco | 9
[23 empty] | Svaraj Patel | 10
[23 empty] | Jameson Fitzpatrick | 11
[23 empty] | Connor Bowman | 12
[23 empty] | Xavier Hakes | 13
[23 empty] | PM / TPM | 14
[23 empty] | Prolaan : Detail Design | 15
[23 empty] | Prolaan : Install Dwgs | 16
17
18
Formulas:
Target Date = [Target Date, row below]-Table202225[[#This Row],[Days]]
Target Date = [Target Date, row below]